## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | Installation of Stand-Alone Community Purification Plant at Schools(77 nos.) of Chanchal-II Dev. Block, Malda under Malda Division, PHE Dte. | SM/10384 | School | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for Schools at Malatipur GP of Chanchal-II Dev. Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Junior Engineer | ORD/000502/2022-2023 | 87/MD | 17/01/2023 | 18/03/2023 | DIPAYAN DEY | 95.49 | 83.87 | 87.84 | 67
2 | MALDAH |  | Malda Division | Installation of Stand-Alone Community Purification Plant at Schools(77 nos.) of Chanchal-II Dev. Block, Malda under Malda Division, PHE Dte. | SM/10384 | School | Material Requisition To Resource Division |  |  | RTOR000032/2021-2022 | 727/MD | 25/03/2022 | 25/03/2022 | Resource Division | 71.35 | 0 | 0 | 0
3 | MALDAH |  | Malda Division | Installation of Stand-Alone Community Purification Plant at Schools(77 nos.) of Chanchal-II Dev. Block, Malda under Malda Division, PHE Dte. | SM/10384 | School | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for Schools at Kshempur GP of Chanchal-II Dev. Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000514/2022-2023 | 814/MD | 20/02/2023 | 06/05/2023 | NEOGI ENTERPRISE | 136.67 | 74.12 | 54.23 | 80
4 | MALDAH |  | Malda Division | Installation of Stand-Alone Community Purification Plant at Schools(77 nos.) of Chanchal-II Dev. Block, Malda under Malda Division, PHE Dte. | SM/10384 | School | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for Schools at Bhakri and Gourhand GP of Chanchal-II Dev. Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000513/2022-2023 | 812/MD | 20/02/2023 | 06/05/2023 | NEOGI ENTERPRISE | 136.67 | 115.22 | 84.3 | 100
5 | MALDAH |  | Malda Division | Installation of Stand-Alone Community Purification Plant at Schools(77 nos.) of Chanchal-II Dev. Block, Malda under Malda Division, PHE Dte. | SM/10384 | School | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for Schools at Jalalpur & Chandrapara GP of Chanchal-II Dev. Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Junior Engineer,Mr. Sanjit Sarkar, Junior Engineer | ORD/000500/2022-2023 | 89/MD | 17/01/2023 | 01/09/2025 | MILLENNIUM ENTERPRISR | 129.75 | 0 | 0 | 100
Total | [13 empty] | 569.93 | 273.21 | 47.94