## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | Installation of Stand-Alone Community Purification Plant at Schools(87 nos) of Ratua-I Dev. Block, Malda under Malda Division, PHE Dte. | SM/10385 | School | Material Requisition To Resource Division |  |  | RTOR000024/2021-2022 | 719/MD | 25/03/2022 | 25/03/2022 | Resource Division | 57.3 | 0 | 0 | 0
2 | MALDAH |  | Malda Division | Installation of Stand-Alone Community Purification Plant at Schools(87 nos) of Ratua-I Dev. Block, Malda under Malda Division, PHE Dte. | SM/10385 | School | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for Schools at Bilaimari & Mahanandatala GP of Ratua-I Dev. Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer,Tapan Haldar, Junior Engineer | ORD/000422/2022-2023 | 3193/MD | 27/12/2022 | 12/03/2023 | WATER TECH | 157.2 | 99.87 | 63.53 | 63
3 | MALDAH |  | Malda Division | Installation of Stand-Alone Community Purification Plant at Schools(87 nos) of Ratua-I Dev. Block, Malda under Malda Division, PHE Dte. | SM/10385 | School | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for School at Debipur, Kahala & Baharal GP of Ratua-I Dev. Block under Malda Division, PHE Dte. | Mr. Prosanta Mandal, Assistant Engineer | Mr. Sujit Sarkar, Junior Engineer | ORD/000428/2022-2023 | 3199/MD | 27/12/2022 | 12/03/2023 | USHA ENTERPRISE | 129.85 | 68.24 | 52.55 | 100
4 | MALDAH |  | Malda Division | Installation of Stand-Alone Community Purification Plant at Schools(87 nos) of Ratua-I Dev. Block, Malda under Malda Division, PHE Dte. | SM/10385 | School | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for Schools at Chandmani-I & Chandmani-II GP of Rtua-I Dev. Block under Malda Division, PHE Dte. | Mr. Prasanta Mandal, Assistant Engineer,Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sujit Sarkar, Junior Engineer,Mr. Tilok Roy, Junior Engineer,Tapan Haldar, Junior Engineer | ORD/000515/2022-2023 | 468/MD | 07/02/2023 | 23/04/2023 | MILLENNIUM ENTERPRISR | 136.58 | 42.07 | 30.8 | 100
5 | MALDAH |  | Malda Division | Installation of Stand-Alone Community Purification Plant at Schools(87 nos) of Ratua-I Dev. Block, Malda under Malda Division, PHE Dte. | SM/10385 | School | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for Schools at Bhado, Ratua & Samsi GP of Ratua-I Dev. Block under Malda Division, PHE Dte. | Mr. Prosanta Mandal, Assistant Engineer,Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sujit Sarkar, Junior Engineer,Mr. Tilok Roy, Junior Engineer,Tapan Haldar, Junior Engineer | ORD/000505/2022-2023 | 102/MD | 18/01/2023 | 02/01/2025 | MILLENNIUM ENTERPRISR | 136.58 | 0 | 0 | 100
Total | [13 empty] | 617.5 | 210.18 | 34.04