## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | Installation of Stand-Alone Community Purification Plant at Schools(94 nos) of Habibpur Dev. Block, Malda under Malda Division, PHE Dte. | SM/10386 | School | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for Schools at Aiho, Rishipur & Srirampur GP of Habibpur Dev. Block under Malda Division, PHE Dte. | Mr. Amit Biswas, Assistant Engineer | Sumit Kumar Ganguly, Junior Engineer | ORD/000423/2022-2023 | 3194/MD | 27/12/2022 | 12/03/2023 | M/S GOUTAM CHAKRABORTY | 113.29 | 0 | 0 | 0
2 | MALDAH |  | Malda Division | Installation of Stand-Alone Community Purification Plant at Schools(94 nos) of Habibpur Dev. Block, Malda under Malda Division, PHE Dte. | SM/10386 | School | Material Requisition To Resource Division |  |  | RTOR000029/2021-2022 | 724/MD | 25/03/2022 | 25/03/2022 | Resource Division | 61.91 | 0 | 0 | 0
3 | MALDAH |  | Malda Division | Installation of Stand-Alone Community Purification Plant at Schools(94 nos) of Habibpur Dev. Block, Malda under Malda Division, PHE Dte. | SM/10386 | School |  |  |  | BILL/00566/2022-2023 |  | 24/03/2023 | 24/03/2023 | M/S GOUTAM CHAKRABORTY | 67.74 | 0 | 0 | 0
4 | MALDAH |  | Malda Division | Installation of Stand-Alone Community Purification Plant at Schools(94 nos) of Habibpur Dev. Block, Malda under Malda Division, PHE Dte. | SM/10386 | School | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for School at Mangalpura, Dhumpur & Baidyapur GP of Habibpur Dev. Block under Malda Division, PHE Dte. | Mr. Amit Biswas, Assistant Engineer | Bikash Balo, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000527/2022-2023 | 556/MD | 09/02/2023 | 25/04/2023 | MILLENNIUM ENTERPRISR | 113.21 | 0 | 0 | 45
5 | MALDAH |  | Malda Division | Installation of Stand-Alone Community Purification Plant at Schools(94 nos) of Habibpur Dev. Block, Malda under Malda Division, PHE Dte. | SM/10386 | School | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for Schools at Kanturka & Jajoil GP of Habibpur Dev. Block under Malda Division, PHE Dte. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000578/2022-2023 | 815/MD | 20/02/2023 | 06/05/2023 | GIYASUDDIN SEKH | 118.65 | 0 | 0 | 100
6 | MALDAH |  | Malda Division | Installation of Stand-Alone Community Purification Plant at Schools(94 nos) of Habibpur Dev. Block, Malda under Malda Division, PHE Dte. | SM/10386 | School | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for Schools at Bulbulchandi, Habibpur & Aktail GP of Habibpur Dev. Block under Malda Division, PHE Dte. | Mr. Amit Biswas, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000508/2022-2023 | 197/MD | 19/01/2023 | 04/04/2023 | MILLENNIUM ENTERPRISR | 134.77 | 0 | 0 | 100
Total | [13 empty] | 609.57 | 0 | 0