## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | Installation of Stand-Alone Community Purification Plant at Schools(112 no) of Chanchal-I Dev. Block, Malda under Malda Division, PHE Dte. | SM/10387 | School | Material Requisition To Resource Division |  |  | RTOR000031/2021-2022 | 726/MD | 25/03/2022 | 25/03/2022 | Resource Division | 72.33 | 0 | 0 | 0
2 | MALDAH |  | Malda Division | Installation of Stand-Alone Community Purification Plant at Schools(112 no) of Chanchal-I Dev. Block, Malda under Malda Division, PHE Dte. | SM/10387 | School | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for Schools at Matiharpur & Alihanda GP of Chanchal-I Dev. Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000459/2022-2023 | 42/MD | 16/01/2023 | 01/08/2024 | MILLENNIUM ENTERPRISR | 113.21 | 98.02 | 86.59 | 100
3 | MALDAH |  | Malda Division | Installation of Stand-Alone Community Purification Plant at Schools(112 no) of Chanchal-I Dev. Block, Malda under Malda Division, PHE Dte. | SM/10387 | School | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for Schools at Mokdampur & Koligram GP of Chanchal-I Dev. Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000579/2022-2023 | 816/MD | 20/02/2023 | 06/05/2023 | WIST WATER SOLUTIONS | 105.41 | 94.17 | 89.34 | 75
4 | MALDAH |  | Malda Division | Installation of Stand-Alone Community Purification Plant at Schools(112 no) of Chanchal-I Dev. Block, Malda under Malda Division, PHE Dte. | SM/10387 | School | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for Schools at Bhagabanpur & Kharba GP of Chanchal-I Dev. Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000521/2022-2023 | 479/MD | 07/02/2023 | 23/04/2023 | DUTTA ENTERPRISE | 188.68 | 163.62 | 86.72 | 60
5 | MALDAH |  | Malda Division | Installation of Stand-Alone Community Purification Plant at Schools(112 no) of Chanchal-I Dev. Block, Malda under Malda Division, PHE Dte. | SM/10387 | School | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for Schools at Chanchal & Mahanandapur GP of Chanchal-I Dev. Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000522/2022-2023 | 478/MD | 07/02/2023 | 23/04/2023 | DUTTA ENTERPRISE | 161.73 | 145.53 | 89.99 | 60
Total | [13 empty] | 641.35 | 501.34 | 78.17