## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | Installation of Stand-Alone Community Purification Plant at Schools(100 nos) of Harishchandrapur-I Dev. Block, Malda under Malda Division, PHE Dte. | SM/10388 | School | Material Requisition To Resource Division |  |  | RTOR000026/2021-2022 | 721/MD | 25/03/2022 | 25/03/2022 | Resource Division | 65.74 | 0 | 0 | 0
2 | MALDAH |  | Malda Division | Installation of Stand-Alone Community Purification Plant at Schools(100 nos) of Harishchandrapur-I Dev. Block, Malda under Malda Division, PHE Dte. | SM/10388 | School | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for Schools at Harishchandrapur & Boroi GP of Harishchandrapur-I Dev. Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000499/2022-2023 | 90/MD | 17/01/2023 | 02/04/2023 | MAMATA USHA ENTERPRISE | 188.85 | 128.03 | 67.79 | 97
3 | MALDAH |  | Malda Division | Installation of Stand-Alone Community Purification Plant at Schools(100 nos) of Harishchandrapur-I Dev. Block, Malda under Malda Division, PHE Dte. | SM/10388 | School | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for Schools at Rashidabad & Kushida GP of Harishchandrapur-I Dev. Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000580/2022-2023 | 817/MD | 20/02/2023 | 06/05/2023 | NEOGI ENTERPRISE | 129.47 | 91.67 | 70.8 | 95
4 | MALDAH |  | Malda Division | Installation of Stand-Alone Community Purification Plant at Schools(100 nos) of Harishchandrapur-I Dev. Block, Malda under Malda Division, PHE Dte. | SM/10388 | School | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for Schools at Mahendrapur & Bhingole GP of Harishchandrapur-I Dev. Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000460/2022-2023 | 43/MD | 16/01/2023 | 01/08/2024 | MILLENNIUM ENTERPRISR | 97.04 | 0 | 0 | 100
5 | MALDAH |  | Malda Division | Installation of Stand-Alone Community Purification Plant at Schools(100 nos) of Harishchandrapur-I Dev. Block, Malda under Malda Division, PHE Dte. | SM/10388 | School | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for Schools at Tulshihata GP of Harishchandrapur-I Dev. Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000507/2022-2023 | 198/MD | 19/01/2023 | 01/08/2024 | MILLENNIUM ENTERPRISR | 97.04 | 0 | 0 | 100
Total | [13 empty] | 578.14 | 219.7 | 38