## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | Augmentation of Khusida Piped Water Supply Scheme | SM/10397 | Augmentation | Acceptance cum formal work order for Construction of 3.6mtr.X 3.0mtr Switch Room cum chlorine room with Water Supply and sanitary arragement at 3rd Tube Well site of Kushida Water Supply Scheme under Malda Division, PHE Dte. In the District of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000028/2022-2023 | 1195/MD | 24/05/2022 | 23/06/2022 | RANJIT ADHIKARY | 4.8 | 0 | 0 | 0
2 | MALDAH |  | Malda Division | Augmentation of Khusida Piped Water Supply Scheme | SM/10397 | Augmentation | Acceptance cum formal work order for Construction of 3.6mtr.X 3.0mtr Switch Room cum chlorine room with Water Supply and sanitary arragement at 4th Tube Well site of Kushida Water Supply Scheme under Malda Division, PHE Dte. In the District of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000029/2022-2023 | 1196/MD | 24/05/2022 | 23/06/2022 | RAHANUL ALAM | 4.8 | 0 | 0 | 1
3 | MALDAH |  | Malda Division | Augmentation of Khusida Piped Water Supply Scheme | SM/10397 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000047/2023-2024 | 1811/MD | 27/04/2023 |  | Resource Division | 51.58 | 0 | 0 | 0
4 | MALDAH |  | Malda Division | Augmentation of Khusida Piped Water Supply Scheme | SM/10397 | Augmentation | Laying of Distribution pipe line in connection with Augmentation of Uttar Rampur Mouza (JL-36) under KUSHIDA Piped Water Supply Scheme at Harishchandrapur-I Block of Malda District under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000763/2023-2024 | 5324/MD | 27/12/2023 | 25/02/2024 | SUBHAS CHANDRA KESHARI | 91.57 | 9.48 | 10.36 | 0
5 | MALDAH |  | Malda Mechanical | Augmentation of Khusida Piped Water Supply Scheme | SM/10397 | Augmentation | Supply, installation, and commissioning of electro-mechanical components at T/W no. III & IV of Augmentation of Khusida Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/008174) | Assistant Engineer - II | Junior Engineer-05 | ORD/001799/2023-2024 | 3686/MLMD | 29/11/2023 | 27/05/2024 | KARMAKAR CONSTRICTION. | 25.1 | 10.32 | 41.12 | 0
6 | MALDAH |  | Malda Division | Augmentation of Khusida Piped Water Supply Scheme | SM/10397 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000136/2023-2024 | 115/MD | 05/01/2024 |  | Resource Division | 13.49 | 0 | 0 | 0
7 | MALDAH |  | Malda Division | Augmentation of Khusida Piped Water Supply Scheme | SM/10397 | Augmentation | Formal work order for the work of Laying of Distribution pipe line in connection with Augmentation of Kushida Pipe Water Supply Scheme at Harishchandrapur-I Block in the District of Malda under Malda Division P.H.E. Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000011/2023-2024 | 1568/MD | 10/04/2023 | 25/05/2023 | SUBHAS CHANDRA KESHARI | 434.18 | 253.16 | 58.31 | 40
8 | MALDAH |  | Malda Division | Augmentation of Khusida Piped Water Supply Scheme | SM/10397 | Augmentation | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room corresponding to Tube Well No 3 at KUSHIDA Piped Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000936/2023-2024 | 581/MD | 02/02/2024 | 18/03/2024 | RAHANUL ALAM | 4.19 | 0 | 0 | 0
9 | MALDAH |  | Malda Division | Augmentation of Khusida Piped Water Supply Scheme | SM/10397 | Augmentation | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room corresponding to Tube Well No 4 at KUSHIDA Piped Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000937/2023-2024 | 582/MD | 02/02/2024 | 18/03/2024 | SR ENTERPRISE | 4.19 | 0 | 0 | 0
10 | MALDAH |  | Malda Division | Augmentation of Khusida Piped Water Supply Scheme | SM/10397 | Augmentation | Continuation work order for Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, Chanchal Sub-Division, PHE Dte. (Period from 06/02/2024 to 30/06/2024). | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/001221/2023-2024 | 589/MD | 02/02/2024 | 27/06/2024 | M/S FOUR STAR CONSTRUCTION | 0.71 | 0 | 0 | 0
11 | MALDAH |  | Malda Division | Augmentation of Khusida Piped Water Supply Scheme | SM/10397 | Augmentation | Sinking of 250mm. Dia. x 150 mm. Big dia. Tube Well of 150m Deep at 4th Tubewell site of Kushida PWSS under Harishchandrapur-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000282/2024-2025 | 3233/MD | 28/06/2024 | 12/08/2024 | SAUDAGAR INDIA | 10.14 | 0 | 0 | 0
12 | MALDAH |  | Malda Division | Augmentation of Khusida Piped Water Supply Scheme | SM/10397 | Augmentation | Formal work order for the work of Construction of 700 M3 Capacity OHR with Soil Investigation and FHTC of Kushida Piped Water Supply Scheme at Harishchandrapur-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000009/2023-2024 | 1569/MD | 10/04/2023 | 05/01/2024 | SUBHAS CHANDRA KESHARI | 333.31 | 122.89 | 36.87 | 8
13 | MALDAH |  | Malda Division | Augmentation of Khusida Piped Water Supply Scheme | SM/10397 | Augmentation | Sinking of 250mm. Dia. x 150 mm. Big dia. Tube Well of 150m Deep at 3rd Tubewell site of Kushida PWSS under Harishchandrapur-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation,Mr. Tilok Roy, Junior Engineer | ORD/000305/2024-2025 | 3451/MD | 11/07/2024 | 25/08/2024 | SAUDAGAR INDIA | 10.14 | 0 | 0 | 0
Total | [13 empty] | 988.18 | 395.86 | 40.06