## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Harischandrapur-I | Malda Division | Ground Water Based for Tulshihatta Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/11587 | New | Acceptance cum formal work order for Route survey, design and preparation of DPR of Tulshihatta Zone-II Piped Water Supply Scheme at Harishchandrapur-I Dev. Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000690/2021-2022 | 655/MD | 22/03/2022 | 06/04/2022 | M/S SOBHA & CO. | 3.27 | 3.24 | 99.29 | 1
2 | MALDAH | Harischandrapur-I | Malda Division | Ground Water Based for Tulshihatta Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/11587 | New | Formal work order for the work of Augmentation of TULSHIHATTA ZONE-II Piped Water Supply Scheme at Harishchandrapur-I Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000038/2023-2024 | 1885/MD | 08/05/2023 | 25/12/2025 | MANIK CHANDRA SAHA | 276.32 | 111.69 | 40.42 | 71
3 | MALDAH | Harischandrapur-I | Malda Mechanical | Ground Water Based for Tulshihatta Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/11587 | New | Supply, installation, commissioning of electro-mechanical components at T/W no. I of Tulshihata (zone-II) Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/011277) | Assistant Engineer - II | Junior Engineer-05 | ORD/000699/2023-2024 | 2774/MLMD | 14/08/2023 | 23/09/2026 | SOVA ENTERPRISE. | 7.87 | 6.92 | 87.88 | 88
4 | MALDAH | Harischandrapur-I | Malda Division | Ground Water Based for Tulshihatta Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/11587 | New | Sinking of 250mm. Dia. x 150 mm. Big dia. Tube Well of 160 Mtr. Deep of Tube Well No. 1 at Tulsihatta Zone-II of Harischandrapur - I Block under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000456/2023-2024 | 3397/MD | 31/08/2023 | 30/09/2023 | A. L. ENGINEERING SOLUTION | 10.81 | 10.59 | 97.94 | 96
5 | MALDAH | Harischandrapur-I | Malda Division | Ground Water Based for Tulshihatta Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/11587 | New | Sinking of 250mm. Dia. x 150 mm. Big dia. Tube Well of 160 Mtr. Deep of Tube Well No. 2 at Tulsihatta Zone-II of Harischandrapur - I Block under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000457/2023-2024 | 3398/MD | 31/08/2023 | 30/09/2023 | A. L. ENGINEERING SOLUTION | 10.81 | 10.79 | 99.79 | 95
6 | MALDAH | Harischandrapur-I | Malda Division | Ground Water Based for Tulshihatta Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/11587 | New | Material Requisition To Resource Division |  |  | RTOR000033/2023-2024 | 1806/MD | 27/04/2023 | 27/04/2023 | Resource Division | 17.43 | 0 | 0 | 0
7 | MALDAH | Harischandrapur-I | Malda Division | Ground Water Based for Tulshihatta Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/11587 | New | Construction of Boundary Wall at Head Work site of Tulshihata Zone-II Water Supply Scheme under Harischandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000618/2024-2025 | 5742/MD | 20/11/2024 | 15/02/2026 | M/S BABLU ENTERPRISE | 25.14 | 0 | 0 | 75
8 | MALDAH | Harischandrapur-I | Malda Division | Ground Water Based for Tulshihatta Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/11587 | New | Material Requisition To Resource Division |  |  | RTOR000128/2023-2024 | 98/MD | 05/01/2024 | 05/01/2024 | Resource Division | 6.9 | 0 | 0 | 0
9 | MALDAH | Harischandrapur-I | Malda Mechanical | Ground Water Based for Tulshihatta Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/11587 | New | New service connection at TULSHIHATA PWSS Zone II T/W NO I Under EE/MLMD PHE DTE DIST. Malda.( Harishchandrapur c c c) |  |  | BILL/03760/2023-2024 | BP-2023-24-729 | 28/03/2024 | 28/03/2024 | W.B.S.E.D.C.LTD | 7.47 | 0 | 0 | 0
10 | MALDAH | Harischandrapur-I | Malda Division | Ground Water Based for Tulshihatta Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/11587 | New | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Tulshihatta Zone-II Water Supply Scheme under Harishchandrtapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000757/2024-2025 | 75 | 13/01/2025 | 27/02/2025 | M/S BABLU ENTERPRISE | 24.37 | 0 | 0 | 0
11 | MALDAH | Harischandrapur-I | Malda Division | Ground Water Based for Tulshihatta Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/11587 | New | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room at Pump House No. 2 of Tulshihatta Zone-II Piped Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000073/2025-2026 | 2266/MD | 21/05/2025 | 05/07/2025 | M/S GLOBAL ENTERPRISE | 4.34 | 0 | 0 | 100
12 | MALDAH | Harischandrapur-I | Malda Mechanical | Ground Water Based for Tulshihatta Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/11587 | New | New service connection at TULSHIHATA PWSS T/W NO II Under EE/MLMD PHE DTE DIST. Malda.( Harishchandrapur c c c) |  |  | BILL/03207/2024-2025 | BP-2024-25-640 | 06/02/2025 | 06/02/2025 | W.B.S.E.D.C.LTD | 3.73 | 0 | 0 | 0
Total | [13 empty] | 398.45 | 143.22 | 35.94