## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Harischandrapur-II | Malda Division | Ground Water Based for Kariali Zone-I Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/11588 | New | Acceptance cum formal work order for Route survey, design and preparation of DPR of Kariali Zone-I Piped Water Supply Scheme at Harishchandrapur-II Dev. Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer |  | ORD/000691/2021-2022 | 656/MD | 22/03/2022 | 06/04/2022 | M/S SOBHA & CO. | 3.23 | 0 | 0 | 1
2 | MALDAH | Harischandrapur-II | Malda Division | Ground Water Based for Kariali Zone-I Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/11588 | New | Material Requisition To Resource Division |  |  | RTOR000059/2023-2024 | 1811/MD | 27/04/2023 | 27/04/2023 | Resource Division | 56.72 | 0 | 0 | 0
3 | MALDAH | Harischandrapur-II | Malda Mechanical | Ground Water Based for Kariali Zone-I Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/11588 | New | Supply, installation, commissioning of electro-mechanical components at T/W no. I, II,III of Kariali (zone-I) Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/011278) | Assistant Engineer - II | Junior Engineer-05 | ORD/000681/2023-2024 | 2756/MLMD | 14/08/2023 | 28/01/2026 | DILIP MAHATO. | 43.59 | 0 | 0 | 69
4 | MALDAH | Harischandrapur-II | Malda Division | Ground Water Based for Kariali Zone-I Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/11588 | New | Material Requisition To Resource Division |  |  | RTOR000130/2023-2024 | 100/MD | 05/01/2024 | 05/01/2024 | Resource Division | 25.06 | 0 | 0 | 0
5 | MALDAH | Harischandrapur-II | Malda Division | Ground Water Based for Kariali Zone-I Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/11588 | New | Formal work order for the work of Augmentation of KARIALI ZONE-I Piped Water Supply Scheme at Harishchandrapur-II Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000226/2023-2024 | 2681/MD | 13/07/2023 | 29/10/2025 | KANAN CONSTRUCTION ENTERPRISE | 437.7 | 0 | 0 | 75
6 | MALDAH | Harischandrapur-II | Malda Mechanical | Ground Water Based for Kariali Zone-I Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/11588 | New | Continuation work- Hiring of Inspection vehicle (Diesel driven) for official use of Executive Engineer under office of the Executive Engineer, Malda Mechanical Division, P.H.E. Dte. | Assistant Engineer - II | Junior Engineer-04 | ORD/000646/2024-2025 | 2212/MLMD | 21/08/2024 | 21/10/2024 | NITAI PANDEY | 0.78 | 0 | 0 | 0
7 | MALDAH | Harischandrapur-II | Malda Division | Ground Water Based for Kariali Zone-I Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/11588 | New | Construction of Pump House and Boundary wall at 2nd Tube well and 3rd Tube Well site with dedicated/parallel pipe line for better Functionality of FHTC under KARIALI ZONE-I Water Supply Scheme of Harishchandrapur-II Block under Malda Division P.H.E Dte in the District of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000209/2025-2026 | 3724/MD | 30/07/2025 | 13/10/2025 | VISCOUS ENGINEERS PVT. LTD. | 81.41 | 0 | 0 | 0
Total | [13 empty] | 648.49 | 0 | 0