## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Harischandrapur-II | Malda Division | Ground Water Based for Kariali Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/11589 | New | Acceptance cum formal work order for Route survey, design and preparation of DPR of Kariali Zone-II Piped Water Supply Scheme at Harishchandrapur-II Dev. Block under Malda Division, PHE Dte. |  | Mr. Tilok Roy, Junior Engineer | ORD/000692/2021-2022 | 657/MD | 22/03/2022 | 06/04/2022 | M/S SOBHA & CO. | 2.76 | 0 | 0 | 1
2 | MALDAH | Harischandrapur-II | Malda Mechanical | Ground Water Based for Kariali Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/11589 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. (Zone-II) of Kariali PWSS, Bhaluka C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II |  | ORD/001520/2023-2024 | 3004422637 | 22/09/2023 | 21/12/2023 | W.B.S.E.D.C.LTD | 7.19 | 0 | 0 | 100
3 | MALDAH | Harischandrapur-II | Malda Division | Ground Water Based for Kariali Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/11589 | New | Material Requisition To Resource Division |  |  | RTOR000060/2023-2024 | 1811/MD | 27/04/2023 | 27/04/2023 | Resource Division | 16.83 | 0 | 0 | 0
4 | MALDAH | Harischandrapur-II | Malda Mechanical | Ground Water Based for Kariali Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/11589 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I of Kariali (zone-II) Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/011264) | Assistant Engineer - II | Junior Engineer-05 | ORD/000682/2023-2024 | 2757/MLMD | 14/08/2023 | 10/02/2024 | DEB CONSTRUCTION. | 21.59 | 0 | 0 | 58
5 | MALDAH | Harischandrapur-II | Malda Division | Ground Water Based for Kariali Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/11589 | New | Additional Laying Distribution of UPVC Pipe line of KARIALI ZONE-II Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000612/2023-2024 | 4141/MD | 11/10/2023 | 10/11/2023 | S.S.GHOSH ENTERPRISE & CO. | 2.13 | 0 | 0 | 80
6 | MALDAH | Harischandrapur-II | Malda Division | Ground Water Based for Kariali Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/11589 | New | Construction of Boundary Wall at 3rd Tube well site of Kariali Zone-II Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000607/2024-2025 | 5603/MD | 05/11/2024 | 04/01/2025 | GULJAR CONSTRUCTION | 6.93 | 0 | 0 | 0
7 | MALDAH | Harischandrapur-II | Malda Division | Ground Water Based for Kariali Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/11589 | New | Sinking of 200mm (all through) Big dia. Tube Well of 150m Deep at 3rd Tube well site of Kariali Zone-II Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000609/2024-2025 | 5605/MD | 05/11/2024 | 20/12/2024 | SAUDAGAR INDIA | 9.82 | 0 | 0 | 0
8 | MALDAH | Harischandrapur-II | Malda Division | Ground Water Based for Kariali Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/11589 | New | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room at Kariali Zone-II PWSS under Harishchandrapur-II Block under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000595/2024-2025 | 5599/MD | 05/11/2024 | 04/01/2025 | DIPU DUTTA | 4.53 | 0 | 0 | 0
9 | MALDAH | Harischandrapur-II | Malda Division | Ground Water Based for Kariali Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/11589 | New | Material Requisition To Resource Division |  |  | RTOR000179/2023-2024 | 756/MD | 19/02/2024 | 19/02/2024 | Resource Division | 4.31 | 0 | 0 | 0
10 | MALDAH | Harischandrapur-II | Malda Division | Ground Water Based for Kariali Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/11589 | New | Formal work order for the work of Augmentation of KARIALI ZONE-II Piped Water Supply Scheme at Harishchandrapur-II Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000040/2023-2024 | 1947/MD | 16/05/2023 | 25/06/2026 | UTTAM KUMAR GHOSH | 399.3 | 0 | 0 | 75
11 | MALDAH | Harischandrapur-II | Malda Division | Ground Water Based for Kariali Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/11589 | New | Construction of Boundary Wall at Head Work site of Kariali Zone-II Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000954/2023-2024 | 699/MD | 09/02/2024 | 01/01/2026 | UTTAM KUMAR GHOSH | 16.32 | 0 | 0 | 0
12 | MALDAH | Harischandrapur-II | Malda Division | Ground Water Based for Kariali Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/11589 | New | Laying of Rising Main including Specials and Valves for Kandaran Zone-II Piped Water Supply Scheme at Chanchal-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000955/2023-2024 | 700/MD | 09/02/2024 | 01/01/2026 | UTTAM KUMAR GHOSH | 22.42 | 0 | 0 | 0
13 | MALDAH | Harischandrapur-II | Malda Division | Ground Water Based for Kariali Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/11589 | New | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Kariali Zone-II Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000635/2024-2025 | 5914/MD | 26/11/2024 | 01/05/2026 | UTTAM KUMAR GHOSH | 27.23 | 0 | 0 | 0
Total | [13 empty] | 541.35 | 0 | 0