## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Harischandrapur - I | Malda Division | Ground Water Based for Tulshihatta Zone-I Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/11590 | New | Acceptance cum formal work order for Route survey, design and preparation of DPR of Tulshihatta Zone-I Piped Water Supply Scheme at Harishchandrapur-I Dev. Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000689/2021-2022 | 654/MD | 22/03/2022 | 06/04/2022 | M/S SOBHA & CO. | 3.42 | 3.42 | 100 | 1
2 | MALDAH | Harischandrapur - I | Malda Division | Ground Water Based for Tulshihatta Zone-I Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/11590 | New | Material Requisition To Resource Division |  |  | RTOR000057/2023-2024 | 1811/MD | 27/04/2023 |  | Resource Division | 17.88 | 0 | 0 | 0
3 | MALDAH | Harischandrapur - I | Malda Division | Ground Water Based for Tulshihatta Zone-I Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/11590 | New | Formal work order for the work of Laying Distribution pipe line for TULSHIHATA (ZONE-I) & its adjoining mouzas Piped Water Supply at Harishchandrapur-I Block in the District Malda under Malda Division, PHE Dte. (2nd Call). | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000271/2022-2023 | 2129/MD | 16/09/2022 | 15/11/2022 | BANIK BROTHERS | 168.65 | 101.34 | 60.09 | 36
4 | MALDAH | Harischandrapur - I | Malda Mechanical | Ground Water Based for Tulshihatta Zone-I Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/11590 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I, II of Tulshihata (zone-I) Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/011266) | Assistant Engineer - II | Junior Engineer-05 | ORD/000698/2023-2024 | 2773/MLMD | 14/08/2023 | 10/02/2024 | SUDIP DEY | 25.6 | 10.34 | 40.41 | 0
5 | MALDAH | Harischandrapur - I | Malda Division | Ground Water Based for Tulshihatta Zone-I Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/11590 | New | Material Requisition To Resource Division |  |  | RTOR000015/2022-2023 | 1874/MD | 16/08/2022 |  | Resource Division | 18.81 | 0 | 0 | 0
6 | MALDAH | Harischandrapur - I | Malda Division | Ground Water Based for Tulshihatta Zone-I Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/11590 | New | Material Requisition To Resource Division |  |  | RTOR000103/2023-2024 | 33/MD | 04/01/2024 |  | Resource Division | 12.32 | 0 | 0 | 0
7 | MALDAH | Harischandrapur - I | Malda Division | Ground Water Based for Tulshihatta Zone-I Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/11590 | New | Acceptance cum formal work order for Emergent Laying of pipe line along NH-81 for restoring drinking water supply towards Rarial Village from TULSHIHATTA Piped Water Supply Scheme, Harishchandrapur I Block, under Malda Division, PHE Dte. in the District of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000076/2023-2024 | 2075/MD | 30/05/2023 | 14/06/2023 | S. N. CONSTRUCTION | 10.18 | 0 | 0 | 100
8 | MALDAH | Harischandrapur - I | Malda Division | Ground Water Based for Tulshihatta Zone-I Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/11590 | New | Material Requisition To Resource Division |  |  | RTOR000009/2024-2025 | 3921/MD | 06/08/2024 |  | Resource Division | 4.31 | 0 | 0 | 0
9 | MALDAH | Harischandrapur - I | Malda Division | Ground Water Based for Tulshihatta Zone-I Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/11590 | New | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of Tulshihatta Zone-I Water Supply Scheme at Harishchandrapur-I Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000455/2023-2024 | 3372/MD | 29/08/2023 | 13/10/2023 | M/S SABANA CONSTRUCTION | 80.46 | 36.02 | 44.76 | 85
Total | [13 empty] | 341.65 | 151.13 | 44.23