## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Harischandrapur-I | Malda Division | Ground Water Based for Tulshihatta Zone-I Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/11590 | New | Acceptance cum formal work order for Route survey, design and preparation of DPR of Tulshihatta Zone-I Piped Water Supply Scheme at Harishchandrapur-I Dev. Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000689/2021-2022 | 654/MD | 22/03/2022 | 06/04/2022 | M/S SOBHA & CO. | 3.42 | 0 | 0 | 1
2 | MALDAH | Harischandrapur-I | Malda Division | Ground Water Based for Tulshihatta Zone-I Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/11590 | New | Material Requisition To Resource Division |  |  | RTOR000015/2022-2023 | 1874/MD | 16/08/2022 | 16/08/2022 | Resource Division | 18.81 | 0 | 0 | 0
3 | MALDAH | Harischandrapur-I | Malda Division | Ground Water Based for Tulshihatta Zone-I Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/11590 | New | Material Requisition To Resource Division |  |  | RTOR000057/2023-2024 | 1811/MD | 27/04/2023 | 27/04/2023 | Resource Division | 17.88 | 0 | 0 | 0
4 | MALDAH | Harischandrapur-I | Malda Mechanical | Ground Water Based for Tulshihatta Zone-I Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/11590 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I, II of Tulshihata (zone-I) Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/011266) | Assistant Engineer - II | Junior Engineer-05 | ORD/000698/2023-2024 | 2773/MLMD | 14/08/2023 | 11/06/2026 | SUDIP DEY | 25.6 | 0 | 0 | 85
5 | MALDAH | Harischandrapur-I | Malda Division | Ground Water Based for Tulshihatta Zone-I Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/11590 | New | Material Requisition To Resource Division |  |  | RTOR000103/2023-2024 | 33/MD | 04/01/2024 | 04/01/2024 | Resource Division | 12.32 | 0 | 0 | 0
6 | MALDAH | Harischandrapur-I | Malda Division | Ground Water Based for Tulshihatta Zone-I Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/11590 | New | Material Requisition To Resource Division |  |  | RTOR000009/2024-2025 | 3921/MD | 06/08/2024 | 06/08/2024 | Resource Division | 4.31 | 0 | 0 | 0
7 | MALDAH | Harischandrapur-I | Malda Division | Ground Water Based for Tulshihatta Zone-I Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/11590 | New | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of Tulshihatta Zone-I Water Supply Scheme at Harishchandrapur-I Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000455/2023-2024 | 3372/MD | 29/08/2023 | 02/06/2024 | M/S SABANA CONSTRUCTION | 80.46 | 0 | 0 | 100
8 | MALDAH | Harischandrapur-I | Malda Mechanical | Ground Water Based for Tulshihatta Zone-I Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/11590 | New | Continuation work- Hiring of Inspection vehicle (Diesel driven) for official use of Assistant Engineer-II under office of the Executive Engineer, Malda Mechanical Division, P.H.E. Dte. | Assistant Engineer - II | Junior Engineer-03 | ORD/000968/2024-2025 | 2780/MLMD | 27/08/2024 | 27/10/2024 | SUBRATA SAHA | 0.78 | 0 | 0 | 100
9 | MALDAH | Harischandrapur-I | Malda Division | Ground Water Based for Tulshihatta Zone-I Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/11590 | New | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Tulshihata Zone-I Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000740/2024-2025 | 60 | 08/01/2025 | 15/11/2025 | M/S BABLU ENTERPRISE | 30.36 | 0 | 0 | 30
10 | MALDAH | Harischandrapur-I | Malda Division | Ground Water Based for Tulshihatta Zone-I Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/11590 | New | Erection of Property board related to Jal Jeevan Mission works of Bbairat, Paro, Mabarakpur, Sri Chandrapur, Tulshihatta Zone-I & II, Kismat Barol PWSS under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000958/2024-2025 | 647/MD | 19/02/2025 | 26/02/2025 | RAHANUL ALAM | 0.95 | 0 | 0 | 100
11 | MALDAH | Harischandrapur-I | Malda Division | Ground Water Based for Tulshihatta Zone-I Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/11590 | New | Formal work order for the work of Laying Distribution pipe line for TULSHIHATA (ZONE-I) & its adjoining mouzas Piped Water Supply at Harishchandrapur-I Block in the District Malda under Malda Division, PHE Dte. (2nd Call). | Mr. Sumit Kumar Ghosh, Assistant Engineer ,Sri Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer ,Mr. Tilok Roy, Junior Engineer | ORD/000271/2022-2023 | 2129/MD | 16/09/2022 | 01/01/2024 | BANIK BROTHERS | 168.65 | 0 | 0 | 100
12 | MALDAH | Harischandrapur-I | Malda Division | Ground Water Based for Tulshihatta Zone-I Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/11590 | New | Laying of additional at Tulshihatta Zone-I Water Supply Scheme under Harishchandrtapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000758/2024-2025 | 76 | 13/01/2025 | 21/09/2025 | M/S GHOSH CONSTRUCTION | 12.42 | 0 | 0 | 100
Total | [13 empty] | 375.97 | 0 | 0