## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Maldah (Old) | Malda Division | Sahapur Piped Water Supply Scheme | SM/11968 | New | Acceptance cum formal work order for Design, Preparation & Submission of DPR as per existing route survey data for Augmentation of SAHAPUR Piped Water Supply Scheme under Malda Division, PHE Dte. | Mr. Prosanta Mandal, Assistant Engineer | Biswajit Gosh, Junior Engineer | ORD/000538/2021-2022 | 2692/MD | 09/09/2021 | 16/09/2021 | RADIANT | 1.72 | 1.7 | 98.83 | 1
2 | MALDAH | Maldah (Old) | Malda Division | Sahapur Piped Water Supply Scheme | SM/11968 | New | Jack Pushing of M.S. pipe of 200 mm dia. through 600 mm dia M.S. pipe by Hydraulic Jacking Technique method through RLY. Track at KM 4/6 to 4/7 between Old Malda Station (OLMF) to Malda Court Station (MLFC) for SAHAPUR and it's adjoining Mouzas Water Supply Scheme under Malda Division, PHE Dte. in the district of Malda. | Mr. Amit Biswas, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000607/2023-2024 | 4111/MD | 10/10/2023 | 08/04/2024 | M/S TRILOCHAN CONSTRUCTION CO | 22.05 | 0 | 0 | 0
3 | MALDAH | Maldah (Old) | Malda Division | Sahapur Piped Water Supply Scheme | SM/11968 | New | Material Requisition To Resource Division |  |  | RTOR000055/2023-2024 | 1811/MD | 27/04/2023 | 27/04/2023 | Resource Division | 104.87 | 0 | 0 | 0
4 | MALDAH | Maldah (Old) | Malda Mechanical | Sahapur Piped Water Supply Scheme | SM/11968 | New | Supply, installation, commissioning of electro-mechanical components at T/W no. II,III & IV of Augmentation of Sahapur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/013245) | Assistant Engineer - II | Junior Engineer-03,Junior Engineer-07 | ORD/000691/2023-2024 | 2766/MLMD | 14/08/2023 | 11/06/2026 | HANNAN BUILDERS PVT. LTD. | 31.15 | 26.45 | 84.91 | 84
5 | MALDAH | Maldah (Old) | Malda Division | Sahapur Piped Water Supply Scheme | SM/11968 | New | Material Requisition To Resource Division |  |  | RTOR000186/2023-2024 | 821/MD | 21/02/2024 | 21/02/2024 | Resource Division | 23.62 | 0 | 0 | 0
6 | MALDAH | Maldah (Old) | Malda Division | Sahapur Piped Water Supply Scheme | SM/11968 | New | Jack Pushing of M.S. pipe of 200 mm dia. through 600 mm dia M.S. pipe by Hydraulic Jacking Technique method through RLY. Track at KM 4/6 to 4/7 between Old Malda Station (OLMF) to Malda Court Station (MLFC) for SAHAPUR and it's adjoining Mouzas Water Supply Scheme under Malda Division, PHE Dte. in the district of Malda. |  |  | BILL/00841/2023-2024 | BP-2023-24-461 | 02/02/2024 | 02/02/2024 | RAIL BHOOMI CROSSING SEVA (IR-RBCS), NORTHEAST FRONTIER RAILWAY KATIHAR DIVISION | 0.05 | 0 | 0 | 0
7 | MALDAH | Maldah (Old) | Malda Division | Sahapur Piped Water Supply Scheme | SM/11968 | New | Jack Pushing of M.S. pipe of 200 mm dia. through 600 mm dia M.S. pipe by Hydraulic Jacking Technique method through RLY. Track at KM 4/6 to 4/7 between Old Malda Station (OLMF) to Malda Court Station (MLFC) for SAHAPUR and it's adjoining Mouzas Water Supply Scheme under Malda Division, PHE Dte. in the district of Malda. |  |  | BILL/01127/2023-2024 | BP-2023-24-602 | 28/03/2024 | 28/03/2024 | RAIL BHOOMI CROSSING SEVA (IR-RBCS), NORTHEAST FRONTIER RAILWAY KATIHAR DIVISION | 4.41 | 0 | 0 | 0
8 | MALDAH | Maldah (Old) | Malda Division | Sahapur Piped Water Supply Scheme | SM/11968 | New | Laying of 200 mm dia HDPE water carrying pipe of chainage 327.800 of the NH-34 of Sahapur GhoshparaBypass More of Saha & Adjoining Mouza water supply Scheme under Malda Division, PHE Dte. |  |  | BILL/00880/2023-2024 | BP-2023-24-478 | 15/02/2024 | 15/02/2024 | NATIONAL HIGHWAYS AUTHORITY OF INDIA PAYABLE AT MALDA | 0.56 | 0 | 0 | 0
9 | MALDAH | Maldah (Old) | Malda Division | Sahapur Piped Water Supply Scheme | SM/11968 | New | Laying of Rising Main including Specials and Valves for Sahapur Piped Water Supply Scheme at Old Malda Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Amit Biswas, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000203/2024-2025 | 2990/MD | 11/06/2024 | 22/04/2025 | S. N. CONSTRUCTION | 24.73 | 0 | 0 | 0
10 | MALDAH | Maldah (Old) | Malda Division | Sahapur Piped Water Supply Scheme | SM/11968 | New | Formal work order for the work of Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Sahapur Water Supply Scheme under Old Malda Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000136/2025-2026 | 2534/MD | 30/05/2025 | 27/09/2025 | M/S DAS CONSTRUCTION | 123.11 | 0 | 0 | 0
11 | MALDAH | Maldah (Old) | Malda Division | Sahapur Piped Water Supply Scheme | SM/11968 | New | Augmentation work of Construction of Boundary Wall at Head Work site of Sahapur Water Supply Scheme under Old Malda Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000894/2024-2025 | 1224/MD | 26/03/2025 | 09/06/2025 | SHREE BISHNU CONSTRUCTION | 25.15 | 0 | 0 | 0
12 | MALDAH | Maldah (Old) | Malda Division | Sahapur Piped Water Supply Scheme | SM/11968 | New | Augmentation work of Boundary wall, Pump House and Construction of Toilet at 1st Tube Well Site of SAHAPUR Water Supply Scheme of Old Malda Block under Malda Division, P.H.E.Dte. in the District of Malda. | Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000896/2024-2025 | 1226/MD | 26/03/2025 | 09/06/2025 | M/S AMIT KUMAR GUPTA | 11.48 | 0 | 0 | 0
13 | MALDAH | Maldah (Old) | Malda Division | Sahapur Piped Water Supply Scheme | SM/11968 | New | Augmentation of Boundary wall, Pump House and Construction of Toilet at 3rdd Tube Well Site of SAHAPUR Water Supply Scheme of Old Malda Block under Malda Division, P.H.E.Dte. in the District of Malda. | Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000897/2024-2025 | 1227/MD | 26/03/2025 | 09/06/2025 | M/S AMIT KUMAR GUPTA | 5.02 | 0 | 0 | 0
14 | MALDAH | Maldah (Old) | Malda Division | Sahapur Piped Water Supply Scheme | SM/11968 | New | Material Requisition To Resource Division |  |  | RTOR000021/2025-2026 | 2825/MD | 11/06/2025 | 11/06/2025 | Resource Division | 23.62 | 0 | 0 | 0
15 | MALDAH | Maldah (Old) | Malda Division | Sahapur Piped Water Supply Scheme | SM/11968 | New | Formal work order for the work of Augmentation of SAHAPUR Piped Water Supply Scheme at Old Malda Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Amit Biswas, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000080/2023-2024 | 2093/MD | 02/06/2023 | 21/07/2026 | S DUTTA | 785.2 | 307.41 | 39.15 | 45
16 | MALDAH | Maldah (Old) | Malda Division | Sahapur Piped Water Supply Scheme | SM/11968 | New | Augmentation work of Pump House and Construction of Toilet at Head Work site Site of Sahapur Water Supply Scheme of Old Malda Block under Malda Division, P.H.E.Dte. in the District of Malda. | Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000895/2024-2025 | 1225/MD | 26/03/2025 | 23/08/2025 | M/S S. S. CONSTRUCTION | 3.73 | 0 | 0 | 0
Total | [13 empty] | 1190.5 | 335.56 | 28.19