## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Gazole | Malda Division | Alal Zone-I Piped Water Supply Scheme | SM/12075 | New | Acceptance cum formal work order for Route survey, design and preparation of DPR of Alal Zone-I Piped Water Supply Scheme at Gazole Dev. Block under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Biswajit Gosh, Junior Engineer | ORD/000686/2021-2022 | 651/MD | 22/03/2022 | 06/04/2022 | TECHVISION | 3.42 | 0 | 0 | 1
2 | MALDAH | Gazole | Malda Division | Alal Zone-I Piped Water Supply Scheme | SM/12075 | New | Material Requisition To Resource Division |  |  | RTOR000063/2023-2024 | 1811/MD | 27/04/2023 | 27/04/2023 | Resource Division | 40.31 | 0 | 0 | 0
3 | MALDAH | Gazole | Malda Division | Alal Zone-I Piped Water Supply Scheme | SM/12075 | New | Acceptance cum formal work order for Laying of Distribution of UPVC Pipeline of ALAL ZONE-I Piped Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000100/2023-2024 | 2327/MD | 08/06/2023 | 07/08/2023 | MD. TALEB ALI | 70.61 | 0 | 0 | 40
4 | MALDAH | Gazole | Malda Mechanical | Alal Zone-I Piped Water Supply Scheme | SM/12075 | New | Supply, installation, commissioning of electro-mechanical components at T/W no. I,II, and Supply, installation, commissioning & Trial operation of electro-mechanical components at T/W no III and making compound lighting arrangement at head worksite of Alal Zone-I Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/011887) | Assistant Engineer - II | Junior Engineer-07 | ORD/000511/2023-2024 | 2583/MLMD | 04/08/2023 | 12/10/2025 | ANIMA ENTERPRISE | 28.62 | 0 | 0 | 72
5 | MALDAH | Gazole | Malda Division | Alal Zone-I Piped Water Supply Scheme | SM/12075 | New | Construction of Boundary Wall at Head Work site of Alal zone-l Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000245/2024-2025 | 3051/MD | 13/06/2024 | 31/07/2025 | SAHA CONSTRUCTION | 50.08 | 0 | 0 | 40
6 | MALDAH | Gazole | Malda Division | Alal Zone-I Piped Water Supply Scheme | SM/12075 | New | Material Requisition To Resource Division |  |  | RTOR000154/2023-2024 | 246/MD | 10/01/2024 | 10/01/2024 | Resource Division | 9.71 | 0 | 0 | 0
7 | MALDAH | Gazole | Malda Mechanical | Alal Zone-I Piped Water Supply Scheme | SM/12075 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Alal Zone-I, Gazole CCC in the dist of Malda Under Malda Mechanical Division PHE Dte. |  |  | BILL/03717/2023-2024 | BP-2023-24-710 | 18/03/2024 | 18/03/2024 | W.B.S.E.D.C.LTD | 5.1 | 0 | 0 | 0
8 | MALDAH | Gazole | Malda Division | Alal Zone-I Piped Water Supply Scheme | SM/12075 | New | Formal work order for the work of Augmentation of ALAL ZONE-I Piped Water Supply Scheme at Gazole Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000048/2023-2024 | 1994/MD | 17/05/2023 | 01/02/2026 | UTTAM KUMAR DUTTA | 417.89 | 0 | 0 | 40
9 | MALDAH | Gazole | Malda Division | Alal Zone-I Piped Water Supply Scheme | SM/12075 | New | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Alal Zone-I Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000262/2024-2025 | 3210/MD | 27/06/2024 | 15/11/2025 | EUREKA UNEMPLOYED ENGINEERS CO-OPERATIVE SOCIETY LTD. | 21.15 | 0 | 0 | 0
10 | MALDAH | Gazole | Malda Division | Alal Zone-I Piped Water Supply Scheme | SM/12075 | New | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Alal Zone-I Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000715/2024-2025 | 6406/MD | 19/12/2024 | 16/11/2025 | GOALPARA CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LIMITED. | 16.46 | 0 | 0 | 0
11 | MALDAH | Gazole | Malda Division | Alal Zone-I Piped Water Supply Scheme | SM/12075 | New | Augmentation of Pump House-1 & Pump House-2, at ALAL Water Supply scheme at Gazole Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000890/2024-2025 | 1129/MD | 21/03/2025 | 05/05/2025 | ARUN MUKHERJEE | 2.42 | 0 | 0 | 0
Total | [13 empty] | 665.78 | 0 | 0