## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Harischandrapur-I | Malda Division | Choupaldanga pipe water Supply Scheme | SM/12076 | New | Material Requisition To Resource Division |  |  | RTOR000024/2022-2023 | 2755/MD | 22/11/2022 | 22/11/2022 | Resource Division | 53 | 0 | 0 | 0
2 | MALDAH | Harischandrapur-I | Malda Division | Choupaldanga pipe water Supply Scheme | SM/12076 | New | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. Big dia. and 150 Mtr. deep Tube Well Drilling by Direct Rotary method with 150 mm dia upvc strainer of 30m length all complete including cost of materials at Heads Work Site of CHOUPALDANGA Water Supply Scheme at Harishchandrapur I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000326/2022-2023 | 2348/MD | 29/09/2022 | 29/10/2022 | MECHANO TRADING CO. | 9.65 | 8.71 | 90.28 | 100
3 | MALDAH | Harischandrapur-I | Malda Mechanical | Choupaldanga pipe water Supply Scheme | SM/12076 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of Choupaldanga PWSS, Kushida C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II |  | ORD/000300/2023-2024 | 3004302721 | 21/07/2023 | 19/10/2023 | W.B.S.E.D.C.LTD | 3.2 | 3.2 | 100 | 100
4 | MALDAH | Harischandrapur-I | Malda Division | Choupaldanga pipe water Supply Scheme | SM/12076 | New | Bill for reimbursement of cost of Diesel and Mobil in respect of hired Vehicle Car No. WB61A/3084, For the month of June and July 2023. |  |  | BILL/00330/2023-2024 | BP-2023-24-192 | 07/09/2023 | 07/09/2023 | SHYAMAL KUMAR MAITRA | 0.36 | 0 | 0 | 0
5 | MALDAH | Harischandrapur-I | Malda Division | Choupaldanga pipe water Supply Scheme | SM/12076 | New | Acceptance cum formal work order for Construction of 5.40 mtr.X 3.6mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at Head Work site of CHOUPALDANGA & its adjoining mouza Water Scheme at Harishchandrapur-I Dev. Block under Malda Division, PHE Dte. In the District of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer ,Mr. Tilok Roy, Junior Engineer | ORD/000298/2022-2023 | 2194/MD | 22/09/2022 | 06/11/2022 | M/S EHAN ENTERPRISE | 6.67 | 6.01 | 90.06 | 95
6 | MALDAH | Harischandrapur-I | Malda Division | Choupaldanga pipe water Supply Scheme | SM/12076 | New | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. dia. and 150 Mtr. Deep Big dia Tube well (2 Nos.) at CHOUPALDANGA Water Supply Scheme under Harishchandrapur-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000677/2022-2023 | 1139/MD | 20/03/2023 | 19/04/2023 | DUTTA ENTERPRISE | 20.31 | 20.05 | 98.69 | 95
7 | MALDAH | Harischandrapur-I | Malda Division | Choupaldanga pipe water Supply Scheme | SM/12076 | New | Material Requisition To Resource Division |  |  | RTOR000121/2023-2024 | 91/MD | 05/01/2024 | 05/01/2024 | Resource Division | 10.44 | 0 | 0 | 0
8 | MALDAH | Harischandrapur-I | Malda Mechanical | Choupaldanga pipe water Supply Scheme | SM/12076 | New | New service connection at CHOUPALDANGA Pwss pH NO II Under EE/MLMD PHE DTE DIST. Malda.( kushida c c c) |  |  | BILL/03678/2023-2024 | BP-2023-24-661 | 11/03/2024 | 11/03/2024 | W.B.S.E.D.C.LTD | 3.87 | 0 | 0 | 0
9 | MALDAH | Harischandrapur-I | Malda Mechanical | Choupaldanga pipe water Supply Scheme | SM/12076 | New | New service connection at CHOUPALDANGA Pwss pH NO III Under EE/MLMD PHE DTE DIST. Malda.( kushida c c c) |  |  | BILL/03679/2023-2024 | BP-2023-24-662 | 11/03/2024 | 11/03/2024 | W.B.S.E.D.C.LTD | 4.06 | 0 | 0 | 0
10 | MALDAH | Harischandrapur-I | Malda Division | Choupaldanga pipe water Supply Scheme | SM/12076 | New | Formal work order for the work of Laying of Distribution pipe line of CHOUPALDANGA and its adjoining mouzas Pipe Water Supply Scheme at Harishchandrapur-I Block in the District of Malda under Malda Division P.H.E. Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer ,Mr. Tilok Roy, Junior Engineer | ORD/000335/2022-2023 | 2384/MD | 13/10/2022 | 01/01/2025 | NEOGI ENTERPRISE | 275.7 | 217.53 | 78.9 | 100
11 | MALDAH | Harischandrapur-I | Malda Division | Choupaldanga pipe water Supply Scheme | SM/12076 | New | Formal work order for the work of Construction of 500 M3 Capacity OHR with Soil Investigation and FHTC of CHOUPALDANGA Piped Water Supply Scheme at Harishchandrapur-I Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000044/2023-2024 | 2007/MD | 17/05/2023 | 03/08/2024 | NIRMAN | 243.67 | 59.39 | 24.37 | 65
12 | MALDAH | Harischandrapur-I | Malda Mechanical | Choupaldanga pipe water Supply Scheme | SM/12076 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II & III and making compound lighting arrangement at T/W no. I of Choupaldanga Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/011833) | Assistant Engineer - II | Junior Engineer-05 | ORD/000312/2023-2024 | 2314/MLMD | 26/07/2023 | 27/01/2026 | COMBINE ENTERPRISE | 38.6 | 6.57 | 17.01 | 85
13 | MALDAH | Harischandrapur-I | Malda Division | Choupaldanga pipe water Supply Scheme | SM/12076 | New | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room corresponding to Tube Well No 2 at CHOUPALDANGA Piped Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000934/2023-2024 | 579/MD | 02/02/2024 | 18/03/2024 | GULJAR CONSTRUCTION | 4.19 | 0 | 0 | 100
14 | MALDAH | Harischandrapur-I | Malda Division | Choupaldanga pipe water Supply Scheme | SM/12076 | New | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room corresponding to Tube Well No 3 at CHOUPALDANGA Piped Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000935/2023-2024 | 580/MD | 02/02/2024 | 18/03/2024 | GULJAR CONSTRUCTION | 4.19 | 0 | 0 | 100
15 | MALDAH | Harischandrapur-I | Malda Division | Choupaldanga pipe water Supply Scheme | SM/12076 | New | Construction of Boundary Wall at Head Work site of Choupaldanga Water Supply Scheme under Harischandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. (2nd Call) | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000146/2025-2026 | 2684/MD | 04/06/2025 | 01/11/2025 | GIRIDHARI CONSTRUCTION | 25.91 | 0 | 0 | 0
16 | MALDAH | Harischandrapur-I | Malda Division | Choupaldanga pipe water Supply Scheme | SM/12076 | New | Construction of Boundary Wall at 2nd Tubewell site of Choupaldanga Water Supply Scheme under Harischandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. (2nd Call) | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000147/2025-2026 | 2685/MD | 04/06/2025 | 01/01/2026 | HARUN ALL RASHID & BROTHERS | 17.12 | 0 | 0 | 0
17 | MALDAH | Harischandrapur-I | Malda Division | Choupaldanga pipe water Supply Scheme | SM/12076 | New | Formal work order for the work of Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Choupaldanga Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000063/2025-2026 | 1911/MD | 14/05/2025 | 13/07/2025 | NEOGI ENTERPRISE | 104.36 | 0 | 0 | 0
Total | [13 empty] | 825.31 | 321.45 | 38.95