## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Harischandrapur-I | Malda Division | WARI Piped Water Supply Scheme | SM/12077 | New | Material Requisition To Resource Division |  |  | RTOR000028/2022-2023 | 2753/MD | 22/11/2022 | 22/11/2022 | Resource Division | 42.01 | 0 | 0 | 0
2 | MALDAH | Harischandrapur-I | Malda Division | WARI Piped Water Supply Scheme | SM/12077 | New | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. Big dia. and 150 Mtr. deep Tube Well Drilling by Direct Rotary method with 150 mm dia upvc strainer of 30m length all complete including cost of materials at Heads Work Site of WARI Water Supply Scheme at Harishchandrapur I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000327/2022-2023 | 2349/MD | 29/09/2022 | 29/10/2022 | MECHANO TRADING CO. | 9.65 | 0 | 0 | 100
3 | MALDAH | Harischandrapur-I | Malda Division | WARI Piped Water Supply Scheme | SM/12077 | New | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. dia. and 150 Mtr. Deep Big dia Tube well (2 Nos.) at WARI Water Supply Scheme under Harishchandrapur-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000018/2023-2024 | 1675/MD | 18/04/2023 | 18/05/2023 | SAUDAGAR INDIA | 20.31 | 0 | 0 | 100
4 | MALDAH | Harischandrapur-I | Malda Mechanical | WARI Piped Water Supply Scheme | SM/12077 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of Wari, Kushida C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II |  | ORD/000468/2023-2024 | 3004368704 | 28/07/2023 | 26/10/2023 | W.B.S.E.D.C.LTD | 3.22 | 0 | 0 | 100
5 | MALDAH | Harischandrapur-I | Malda Division | WARI Piped Water Supply Scheme | SM/12077 | New | Formal work order for the work of Laying of Distribution pipe line of WARI and its adjoining mouzas Pipe Water Supply Scheme at Harishchandrapur-I Block in the District of Malda under Malda Division P.H.E. Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000336/2022-2023 | 2396/MD | 14/10/2022 | 12/01/2023 | GHOSH BROTHERS | 379.96 | 0 | 0 | 85
6 | MALDAH | Harischandrapur-I | Malda Division | WARI Piped Water Supply Scheme | SM/12077 | New | Construction of Boundary Wall at 2nd Tube Well site of Wari Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000169/2024-2025 | 2944/MD | 10/06/2024 | 10/07/2024 | MS ENTERPRISE | 9.33 | 0 | 0 | 5
7 | MALDAH | Harischandrapur-I | Malda Division | WARI Piped Water Supply Scheme | SM/12077 | New | Construction of Boundary Wall at 3rd Tube Well site of Wari Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000170/2024-2025 | 2945/MD | 10/06/2024 | 10/07/2024 | MS ENTERPRISE | 9.33 | 0 | 0 | 90
8 | MALDAH | Harischandrapur-I | Malda Division | WARI Piped Water Supply Scheme | SM/12077 | New | Acceptance cum formal work order for Construction of 5.40 mtr.X 3.6mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at Head Work site of WARI & its adjoining mouza Water Scheme at Harishchandrapur-I Dev. Block under Malda Division, PHE Dte. In the District of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000299/2022-2023 | 2195/MD | 22/09/2022 | 06/11/2022 | GOALPARA CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LIMITED. | 6.67 | 0 | 0 | 97
9 | MALDAH | Harischandrapur-I | Malda Division | WARI Piped Water Supply Scheme | SM/12077 | New | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room corresponding to tubewell No 3 at Wari PWSS under Harischandrapur-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000900/2023-2024 | 273/MD | 11/01/2024 | 25/02/2024 | LOKNATH ENTERPRISE | 4.19 | 0 | 0 | 97
10 | MALDAH | Harischandrapur-I | Malda Division | WARI Piped Water Supply Scheme | SM/12077 | New | Material Requisition To Resource Division |  |  | RTOR000131/2023-2024 | 108/MD | 05/01/2024 | 05/01/2024 | Resource Division | 13 | 0 | 0 | 0
11 | MALDAH | Harischandrapur-I | Malda Mechanical | WARI Piped Water Supply Scheme | SM/12077 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of WARI PWSS, Kushida C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. |  |  | BILL/02543/2023-2024 | BP-2023-24-437 | 10/01/2024 | 10/01/2024 | W.B.S.E.D.C.LTD | 3.44 | 0 | 0 | 0
12 | MALDAH | Harischandrapur-I | Malda Mechanical | WARI Piped Water Supply Scheme | SM/12077 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. III of WARI PWSS, Kushida C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. |  |  | BILL/02544/2023-2024 | BP-2023-24-438 | 10/01/2024 | 10/01/2024 | W.B.S.E.D.C.LTD | 6.56 | 0 | 0 | 0
13 | MALDAH | Harischandrapur-I | Malda Division | WARI Piped Water Supply Scheme | SM/12077 | New | Formal work order for the work of Construction of 600 M3 Capacity OHR with soil Investigation and FHTC of WARI Piped Water Supply Scheme at Harishchandrapur-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000007/2023-2024 | 1567/MD | 10/04/2023 | 05/01/2024 | SAMBHU NATH SARKAR | 288.41 | 0 | 0 | 42
14 | MALDAH | Harischandrapur-I | Malda Mechanical | WARI Piped Water Supply Scheme | SM/12077 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II & III and making compound lighting arrangement at T/W no. I of Wari Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/011955) | Assistant Engineer - II | Junior Engineer-05 | ORD/000330/2023-2024 | 2332/MLMD | 26/07/2023 | 29/09/2025 | AHALYA ENGINEERING WORKS | 38.61 | 0 | 0 | 90
15 | MALDAH | Harischandrapur-I | Malda Division | WARI Piped Water Supply Scheme | SM/12077 | New | Construction of Boundary Wall at Head Work site of Wari Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000218/2024-2025 | 3039/MD | 13/06/2024 | 01/01/2026 | SAMBHU NATH SARKAR | 36.41 | 0 | 0 | 90
16 | MALDAH | Harischandrapur-I | Malda Division | WARI Piped Water Supply Scheme | SM/12077 | New | Providing Functional Household Tap Connection (FHTC) & Laying of additional Pipeline in connection with Jal Jeevan Mission (JJM) at Wari Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000801/2024-2025 | 344/MD | 30/01/2025 | 01/04/2026 | GOBINDA ENTERPRISE | 107.02 | 0 | 0 | 0
17 | MALDAH | Harischandrapur-I | Malda Division | WARI Piped Water Supply Scheme | SM/12077 | New | Laying of Rising Main including Specials and Valves for WARI Piped Water Supply Scheme at Harischandrapur-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000921/2023-2024 | 382/MD | 17/01/2024 | 14/10/2024 | MAHA MAYA CONSTRUCTION | 15.4 | 0 | 0 | 72
18 | MALDAH | Harischandrapur-I | Malda Division | WARI Piped Water Supply Scheme | SM/12077 | New | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room corresponding to tubewell No 2 at Wari PWSS under Harischandrapur-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000899/2023-2024 | 166/MD | 08/01/2024 | 22/02/2024 | M/S SAI RAM ENTERPRISE | 4.19 | 0 | 0 | 98
Total | [13 empty] | 997.69 | 0 | 0