## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Chanchal-I | Malda Division | Hatinda Piped Water Supply Scheme. | SM/12078 | New | Acceptance cum formal work order for Construction of 5.40 mtr.X 3.6mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at Head Work site of HATINDA & its adjoining mouza Water Scheme at Chanchal-I Dev. Block under Malda Division, PHE Dte. In the District of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000297/2022-2023 | 2193/MD | 22/09/2022 | 06/11/2022 | M/S. NAYAMEE ENGINEERING & CONSTRUCTIONS | 6.66 | 0 | 0 | 1
2 | MALDAH | Chanchal-I | Malda Division | Hatinda Piped Water Supply Scheme. | SM/12078 | New | Material Requisition To Resource Division |  |  | RTOR000029/2022-2023 | 2754/MD | 22/11/2022 | 22/11/2022 | Resource Division | 25.94 | 0 | 0 | 0
3 | MALDAH | Chanchal-I | Malda Division | Hatinda Piped Water Supply Scheme. | SM/12078 | New | Material Requisition To Resource Division |  |  | RTOR000005/2023-2024 | 1815/MD | 27/04/2023 | 27/04/2023 | Resource Division | 29.46 | 0 | 0 | 0
4 | MALDAH | Chanchal-I | Malda Mechanical | Hatinda Piped Water Supply Scheme. | SM/12078 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I , II & III and making compound lighting arrangement at T/W no. I of Augmentation of Hatinda Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/011729) | Assistant Engineer - II | Junior Engineer-05 | ORD/000262/2023-2024 | 2222/MLMD | 18/07/2023 | 27/05/2026 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIV SOCIETY LTD. | 42.68 | 33.54 | 78.58 | 78
5 | MALDAH | Chanchal-I | Malda Division | Hatinda Piped Water Supply Scheme. | SM/12078 | New | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room corresponding to Tube Well No 3 at HATINDA Piped Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000970/2023-2024 | 829/MD | 21/02/2024 | 06/04/2024 | MD. MANSUR ALI | 4.14 | 0 | 0 | 0
6 | MALDAH | Chanchal-I | Malda Mechanical | Hatinda Piped Water Supply Scheme. | SM/12078 | New | Hiring of Inspection vehicle (Diesel driven) for official use of Assistant Engineer-II under office of the Executive Engineer, Malda Mechanical Division, P.H.E. Dte. | Assistant Engineer - II | Junior Engineer-03 | ORD/003248/2023-2024 | 3887/MLMD | 20/12/2023 | 18/02/2024 | SUBRATA SAHA | 0.77 | 0.72 | 93.01 | 100
7 | MALDAH | Chanchal-I | Malda Division | Hatinda Piped Water Supply Scheme. | SM/12078 | New | Material Requisition To Resource Division |  |  | RTOR000115/2023-2024 | 85/MD | 05/01/2024 | 05/01/2024 | Resource Division | 13.89 | 0 | 0 | 0
8 | MALDAH | Chanchal-I | Malda Division | Hatinda Piped Water Supply Scheme. | SM/12078 | New | Sinking of 250mm. Dia. x 150 mm. Big dia. Tube Well of 160 Mtr. Deep at Head Work Site at HATINDA Piped Water Supply Scheme at Chanchal-I Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000110/2025-2026 | 2410/MD | 27/05/2025 | 11/07/2025 | MONDAL CONSTRUCTION | 10.65 | 0 | 0 | 0
9 | MALDAH | Chanchal-I | Malda Division | Hatinda Piped Water Supply Scheme. | SM/12078 | New | Formal work order for the work of Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Hatinda Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000863/2024-2025 | 1102/MD | 20/03/2025 | 19/05/2025 | USHA ENTERPRISE | 119.77 | 0 | 0 | 0
10 | MALDAH | Chanchal-I | Malda Division | Hatinda Piped Water Supply Scheme. | SM/12078 | New | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. dia. and 160 Mtr. Deep Big dia Tube well (2 Nos.) at HATINDA Water Supply Scheme under Chanchal-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000675/2022-2023 | 1138/MD | 20/03/2023 | 19/01/2025 | DUTTA ENTERPRISE | 21.12 | 0 | 0 | 100
11 | MALDAH | Chanchal-I | Malda Division | Hatinda Piped Water Supply Scheme. | SM/12078 | New | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room corresponding to Tube Well No 2 at HATINDA Piped Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000969/2023-2024 | 828/MD | 21/02/2024 | 15/03/2025 | MD. MANSUR ALI | 4.14 | 0 | 0 | 100
Total | [13 empty] | 279.23 | 34.25 | 12.27