## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Chanchal-I | Malda Division | GAURIA Piped Water Supply Scheme. | SM/12079 | New | Formal work order for the work of Laying of Distribution pipe line of GAURIA and its adjoining mouzas Pipe Water Supply Scheme at Chanchal-I Block in the District of Malda under Malda Division P.H.E. Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Yusuf Sk, Junior Engineer | ORD/000353/2022-2023 | 2412/MD | 17/10/2022 | 15/01/2023 | S DUTTA | 374.04 | 259.84 | 69.47 | 92
2 | MALDAH | Chanchal-I | Malda Division | GAURIA Piped Water Supply Scheme. | SM/12079 | New | Acceptance cum formal work order for Construction of 5.40 mtr.X 3.6mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at Head Work site of GOURIA & its adjoining mouza Water Scheme at Chanchal-I Dev. Block under Malda Division, PHE Dte. In the District of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Rajashree Banarjee, Junior Engineer,Yusuf Sk, Junior Engineer | ORD/000296/2022-2023 | 2192/MD | 22/09/2022 | 28/06/2023 | RAJIB MANI | 6.69 | 4.82 | 72.11 | 100
3 | MALDAH | Chanchal-I | Malda Division | GAURIA Piped Water Supply Scheme. | SM/12079 | New | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. Big dia. and 160 Mtr. deepTube Well Drilling by Direct Rotary method with 150 mm dia upvc strainer of 30m length all complete including cost of materials at Heads Work Site of GOURIA Water Supply Scheme at Chanchal I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Yusuf Sk, Junior Engineer | ORD/000324/2022-2023 | 2346/MD | 29/09/2022 | 29/10/2022 | MECHANO TRADING CO. | 9.96 | 8.77 | 88.05 | 100
4 | MALDAH | Chanchal-I | Malda Division | GAURIA Piped Water Supply Scheme. | SM/12079 | New | Material Requisition To Resource Division |  |  | RTOR000027/2022-2023 | 2757/MD | 22/11/2022 | 22/11/2022 | Resource Division | 45.2 | 0 | 0 | 0
5 | MALDAH | Chanchal-I | Malda Division | GAURIA Piped Water Supply Scheme. | SM/12079 | New | Formal work order for the work of Construction of 600 M3 Capacity Over Head Reservoir with Soil Investigation and FHTC of GAURIA Piped Water Supply Scheme at Chanchal-I Dev. Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Yusuf Sk, Junior Engineer | ORD/000665/2022-2023 | 1036/MD | 13/03/2023 | 01/04/2025 | SOVAN KUMAR ROY | 293.21 | 117.31 | 40.01 | 78
6 | MALDAH | Chanchal-I | Malda Mechanical | GAURIA Piped Water Supply Scheme. | SM/12079 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II & III and making compound lighting arrangement at T/W no. I of Gauria Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/011717) | Assistant Engineer - II | Junior Engineer-05 | ORD/000316/2023-2024 | 2318/MLMD | 26/07/2023 | 11/07/2026 | DIPALI CONSTRUCTION. | 37.94 | 34.01 | 89.64 | 90
7 | MALDAH | Chanchal-I | Malda Division | GAURIA Piped Water Supply Scheme. | SM/12079 | New | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. dia. and 160 Mtr. Deep Big dia Tube well (2 Nos.) at GAURIA Water Supply Scheme under Chanchal-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Yusuf Sk, Junior Engineer | ORD/000674/2022-2023 | 1137/MD | 20/03/2023 | 19/04/2023 | ASHIS CONSTRUCTION | 21.11 | 19.4 | 91.88 | 50
8 | MALDAH | Chanchal-I | Malda Mechanical | GAURIA Piped Water Supply Scheme. | SM/12079 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of Gauria PWSS, Kushida C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II |  | ORD/000299/2023-2024 | 3004302683 | 21/07/2023 | 19/10/2023 | W.B.S.E.D.C.LTD | 2.63 | 2.63 | 100 | 100
9 | MALDAH | Chanchal-I | Malda Division | GAURIA Piped Water Supply Scheme. | SM/12079 | New | Construction of Boundary Wall at 3rd Tube Well site of Gauria Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Yusuf Sk, Junior Engineer | ORD/000672/2024-2025 | 6197/MD | 09/12/2024 | 23/01/2025 | M/S DYNAMIC CONSTRUCTION | 7.23 | 0 | 0 | 0
10 | MALDAH | Chanchal-I | Malda Division | GAURIA Piped Water Supply Scheme. | SM/12079 | New | Construction of Boundary Wall at 2nd Tube Well site of Gauria Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Yusuf Sk, Junior Engineer | ORD/000661/2024-2025 | 6196/MD | 09/12/2024 | 23/01/2025 | M/S GHOSH ENTERPRISE | 7.23 | 0 | 0 | 0
11 | MALDAH | Chanchal-I | Malda Division | GAURIA Piped Water Supply Scheme. | SM/12079 | New | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room corresponding to Tube Well No.- 3 at Gauria PWSS under Chanchal-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Yusuf Sk, Junior Engineer | ORD/000892/2023-2024 | 271/MD | 11/01/2024 | 25/02/2024 | S. M. BUILDER | 4.18 | 4.18 | 99.97 | 100
12 | MALDAH | Chanchal-I | Malda Division | GAURIA Piped Water Supply Scheme. | SM/12079 | New | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room corresponding to Tube Well No.- 2 at Gauria PWSS under Chanchal-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Yusuf Sk, Junior Engineer | ORD/000891/2023-2024 | 165/MD | 08/01/2024 | 22/02/2024 | SK ENTERPRISE | 4.17 | 4.17 | 99.84 | 100
13 | MALDAH | Chanchal-I | Malda Division | GAURIA Piped Water Supply Scheme. | SM/12079 | New | Material Requisition To Resource Division |  |  | RTOR000114/2023-2024 | 84/MD | 05/01/2024 | 05/01/2024 | Resource Division | 13.46 | 0 | 0 | 0
14 | MALDAH | Chanchal-I | Malda Mechanical | GAURIA Piped Water Supply Scheme. | SM/12079 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of GAURIA PWSS, Kushida C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. |  |  | BILL/02537/2023-2024 | BP-2023-24-440 | 10/01/2024 | 10/01/2024 | W.B.S.E.D.C.LTD | 4.22 | 0 | 0 | 0
15 | MALDAH | Chanchal-I | Malda Mechanical | GAURIA Piped Water Supply Scheme. | SM/12079 | New | New service connection at GAURIA PWSS T/W NO III Under EE/MLMD PHE DTE DIST. Malda.(KUSHIDA c c c) |  |  | BILL/00233/2024-2025 | BP-2024-25-97 | 16/04/2024 | 16/04/2024 | W.B.S.E.D.C.LTD | 4.27 | 0 | 0 | 0
16 | MALDAH | Chanchal-I | Malda Division | GAURIA Piped Water Supply Scheme. | SM/12079 | New | Formal work order for the work of Providing Functional Household Tap Connection (FHTC) and Laying of Rising Main including Specials and Valves for Gauria Piped Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Yusuf Sk, Junior Engineer | ORD/000192/2025-2026 | 3384/MD | 10/07/2025 | 06/01/2026 | S DUTTA | 100.31 | 0 | 0 | 0
17 | MALDAH | Chanchal-I | Malda Division | GAURIA Piped Water Supply Scheme. | SM/12079 | New | Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, Chanchal Sub-Division Division, PHE Dte.(Car-2) (Period from 01/01/2026 to 30/06/2026). | Sri Susanta Saha, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000849/2025-2026 | 6435/MD | 31/12/2025 | 30/06/2026 | M/S FOUR STAR CONSTRUCTION | 0.86 | 0 | 0 | 30
18 | MALDAH | Chanchal-I | Malda Division | GAURIA Piped Water Supply Scheme. | SM/12079 | New | Material Requisition To Resource Division |  |  | RTOR000043/2025-2026 | 2869/MD | 16/06/2025 | 16/06/2025 | Resource Division | 12.89 | 0 | 0 | 0
Total | [13 empty] | 949.6 | 455.13 | 47.93