## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Gazole | Malda Mechanical | JIBJALSAR Piped Water Supply Scheme | SM/12182 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I and making compound lighting arrangement at T/W no. I of Jibjalsar Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/013490) | Assistant Engineer - II | Junior Engineer-06,Junior Engineer-07 | ORD/000504/2023-2024 | 2574/MLMD | 04/08/2023 | 02/12/2023 | PABITRA MANDAL | 11.8 | 8.37 | 70.95 | 70
2 | MALDAH | Gazole | Malda Division | JIBJALSAR Piped Water Supply Scheme | SM/12182 | New | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. dia. and 180 Mtr. Deep Big dia Tube well (1 No) at JIBJALSAR Water Supply Scheme under Gazole Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000609/2022-2023 | 927/MD | 27/02/2023 | 29/03/2023 | DUTTA ENTERPRISE | 10.71 | 9.54 | 89.04 | 100
3 | MALDAH | Gazole | Malda Mechanical | JIBJALSAR Piped Water Supply Scheme | SM/12182 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of JIBJALSAR PWSS, Pandua C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II |  | ORD/000781/2023-2024 | 3004387480 | 11/08/2023 | 09/11/2023 | W.B.S.E.D.C.LTD | 3.55 | 3.55 | 100 | 100
4 | MALDAH | Gazole | Malda Division | JIBJALSAR Piped Water Supply Scheme | SM/12182 | New | Material Requisition To Resource Division |  |  | RTOR000017/2023-2024 | 1614/MD | 11/04/2023 | 11/04/2023 | Resource Division | 0.9 | 0 | 0 | 0
5 | MALDAH | Gazole | Malda Division | JIBJALSAR Piped Water Supply Scheme | SM/12182 | New | Material Requisition To Resource Division |  |  | RTOR000003/2023-2024 | 1580 | 10/04/2023 | 10/04/2023 | Resource Division | 0.9 | 0 | 0 | 0
6 | MALDAH | Gazole | Malda Division | JIBJALSAR Piped Water Supply Scheme | SM/12182 | New | Acceptance cum formal work order for Construction of 5.40 mtr.X 3.6 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at Head Work Site of JIBJALSAR Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000480/2022-2023 | 1126/MD | 20/03/2023 | 04/05/2023 | BANIK BROTHERS | 6.57 | 6.56 | 99.83 | 100
7 | MALDAH | Gazole | Malda Division | JIBJALSAR Piped Water Supply Scheme | SM/12182 | New | Material Requisition To Resource Division |  |  | RTOR000152/2023-2024 | 251/MD | 10/01/2024 | 10/01/2024 | Resource Division | 1.03 | 0 | 0 | 0
8 | MALDAH | Gazole | Malda Division | JIBJALSAR Piped Water Supply Scheme | SM/12182 | New | Acceptance cum formal work order for Implementation of JIBJALSAR Piped Water Supply Scheme at Gazole Block of Malda district under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer ,Biswajit Gosh, Junior Engineer | ORD/000487/2022-2023 | 195/MD | 19/01/2023 | 01/10/2025 | ACHARYYA CONSTRUCTION | 25 | 19.67 | 78.68 | 80
9 | MALDAH | Gazole | Malda Division | JIBJALSAR Piped Water Supply Scheme | SM/12182 | New | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of Jibjalsar Water Supply Scheme at Gazole Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000945/2023-2024 | 659/MD | 08/02/2024 | 01/10/2025 | ACHARYYA CONSTRUCTION | 7.36 | 0 | 0 | 0
Total | [13 empty] | 67.82 | 47.68 | 70.31