## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Harischandrapur-I | Malda Division | KHARANGAPUR JABRA Piped Water Supply Scheme | SM/12183 | New | Material Requisition To Resource Division |  |  | RTOR000074/2023-2024 | 1811/MD | 27/04/2023 | 27/04/2023 | Resource Division | 11.42 | 0 | 0 | 0
2 | MALDAH | Harischandrapur-I | Malda Division | KHARANGAPUR JABRA Piped Water Supply Scheme | SM/12183 | New | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. Big dia. and 135 Mtr. deep Tube Well Drilling by Direct Rotary method with 150 mm dia upvc strainer of 30m length all complete including cost of materials at Heads Work Site of KHARANGAPUR JABRA Piped Water Supply Scheme at Harishchandrapur-I Block of Malda District under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000374/2022-2023 | 779/MD | 17/02/2023 | 19/03/2023 | MERCURY ENGINEERING COMPANY | 9.2 | 9.2 | 99.97 | 98
3 | MALDAH | Harischandrapur-I | Malda Division | KHARANGAPUR JABRA Piped Water Supply Scheme | SM/12183 | New | Material Requisition To Resource Division |  |  | RTOR000133/2023-2024 | 110/MD | 05/01/2024 | 05/01/2024 | Resource Division | 4.81 | 0 | 0 | 0
4 | MALDAH | Harischandrapur-I | Malda Mechanical | KHARANGAPUR JABRA Piped Water Supply Scheme | SM/12183 | New | New service connection at KHARANGAPUR JABRA T/W NO I Under EE/MLMD PHE DTE DIST. Malda.( Harishchandrapur c c c) |  |  | BILL/00766/2024-2025 | BP-2024-25-206 | 22/05/2024 | 22/05/2024 | W.B.S.E.D.C.LTD | 3.63 | 0 | 0 | 0
5 | MALDAH | Harischandrapur-I | Malda Mechanical | KHARANGAPUR JABRA Piped Water Supply Scheme | SM/12183 | New | New service connection at KHARANGAPURJABRA PWSS T/W NO II Under EE/MLMD PHE DTE DIST. Malda.( Harishchandrapur c c c) |  |  | BILL/02562/2024-2025 | BP-2024-25-574 | 28/11/2024 | 28/11/2024 | W.B.S.E.D.C.LTD | 3.75 | 0 | 0 | 0
6 | MALDAH | Harischandrapur-I | Malda Mechanical | KHARANGAPUR JABRA Piped Water Supply Scheme | SM/12183 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II and making compound lighting arrangement at T/W no. I of Kharangapur Jabra Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/013445) | Assistant Engineer - II | Junior Engineer-05 | ORD/000319/2023-2024 | 2321/MLMD | 26/07/2023 | 06/11/2025 | DILIP MAHATO. | 26.54 | 19.23 | 72.44 | 85
7 | MALDAH | Harischandrapur-I | Malda Division | KHARANGAPUR JABRA Piped Water Supply Scheme | SM/12183 | New | Construction of Boundary Wall at Head Work site of Kharangapur Jabra Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer ,Mr. Susanta Pal, JE_Deputation,Mr. Tilok Roy, Junior Engineer | ORD/000301/2024-2025 | 3447/MD | 11/07/2024 | 01/09/2025 | GOBINDA ENTERPRISE | 29.37 | 0 | 0 | 70
8 | MALDAH | Harischandrapur-I | Malda Division | KHARANGAPUR JABRA Piped Water Supply Scheme | SM/12183 | New | Restoration of Road of KHARANGAPUR JABRA Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation,Mr. Tilok Roy, Junior Engineer | ORD/000210/2025-2026 | 3725/MD | 30/07/2025 | 29/08/2025 | GOBINDA ENTERPRISE | 29.03 | 0 | 0 | 0
9 | MALDAH | Harischandrapur-I | Malda Division | KHARANGAPUR JABRA Piped Water Supply Scheme | SM/12183 | New | Formal work order for the work of Implementation of KHARANGAPUR JABRA Piped Water Supply Scheme at Harishchandrapur-I Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation,Mr. Tilok Roy, Junior Engineer | ORD/000232/2023-2024 | 2709/MD | 14/07/2023 | 03/07/2025 | GOBINDA ENTERPRISE | 168.68 | 87.75 | 52.02 | 84
10 | MALDAH | Harischandrapur-I | Malda Division | KHARANGAPUR JABRA Piped Water Supply Scheme | SM/12183 | New | Material Requisition To Resource Division |  |  | RTOR000057/2025-2026 | 5594/MD | 30/10/2025 | 30/10/2025 | Resource Division | 3.68 | 0 | 0 | 0
Total | [13 empty] | 290.12 | 116.18 | 40.04