## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Chanchal-I | Malda Division | SERBABAR BALARAMPUR Piped Water Supply Scheme | SM/12184 | New | Material Requisition To Resource Division |  |  | RTOR000031/2022-2023 | 3043/MD | 12/12/2022 | 12/12/2022 | Resource Division | 25.7 | 0 | 0 | 0
2 | MALDAH | Chanchal-I | Malda Division | SERBABAR BALARAMPUR Piped Water Supply Scheme | SM/12184 | New | Material Requisition To Resource Division |  |  | RTOR000024/2023-2024 | 1809/MD | 27/04/2023 | 27/04/2023 | Resource Division | 18.28 | 0 | 0 | 0
3 | MALDAH | Chanchal-I | Malda Division | SERBABAR BALARAMPUR Piped Water Supply Scheme | SM/12184 | New | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Serbabar Balarampur Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000654/2024-2025 | 6364/MD | 17/12/2024 | 31/01/2025 | JAHANGIR ALAM | 58.94 | 0 | 0 | 0
4 | MALDAH | Chanchal-I | Malda Mechanical | SERBABAR BALARAMPUR Piped Water Supply Scheme | SM/12184 | New | New service connection at SERBABBAR BALARAMPUR PWSS T/W NO II Under EE/MLMD PHE DTE DIST. Malda.(CHANCHAL c c c) |  |  | BILL/00232/2024-2025 | BP-2024-25-92 | 16/04/2024 | 16/04/2024 | W.B.S.E.D.C.LTD | 10.05 | 0 | 0 | 0
5 | MALDAH | Chanchal-I | Malda Mechanical | SERBABAR BALARAMPUR Piped Water Supply Scheme | SM/12184 | New | New service connection at serbabbar balarampur under MLMD/PHE Dist. malda (chanchal c.c.c) |  |  | BILL/03547/2023-2024 | BP-2023-24-560 | 16/02/2024 | 16/02/2024 | W.B.S.E.D.C.LTD | 5.87 | 0 | 0 | 0
6 | MALDAH | Chanchal-I | Malda Division | SERBABAR BALARAMPUR Piped Water Supply Scheme | SM/12184 | New | Formal work order for the work of Implementation of SERBABAR BALARAMPUR Water Supply Scheme at Chanchal-I Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer,Yusuf Sk, Junior Engineer | ORD/000065/2023-2024 | 2019/MD | 18/05/2023 | 17/05/2024 | JAHANGIR ALAM | 596.09 | 0 | 0 | 75
7 | MALDAH | Chanchal-I | Malda Mechanical | SERBABAR BALARAMPUR Piped Water Supply Scheme | SM/12184 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Serbabar Balarampur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/013253) | Assistant Engineer - II | Junior Engineer-05 | ORD/000328/2023-2024 | 2330/MLMD | 26/07/2023 | 27/01/2026 | DEY ENTERPRISE.. | 28.99 | 0 | 0 | 84
8 | MALDAH | Chanchal-I | Malda Division | SERBABAR BALARAMPUR Piped Water Supply Scheme | SM/12184 | New | Construction of Boundary Wall at Head Work site of Serbabar Balarampur Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. (2nd Call) | Mr. Sumit Kumar Ghosh, Assistant Engineer | Yusuf Sk, Junior Engineer | ORD/000153/2025-2026 | 2691/MD | 04/06/2025 | 19/07/2025 | JAHANGIR ALAM | 28.62 | 0 | 0 | 0
Total | [13 empty] | 772.52 | 0 | 0