## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Chanchal-I | Malda Mechanical | SWARUPGANJ Piped Water Supply Scheme | SM/12185 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of SWARUPGANJ, Kushida C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II |  | ORD/000466/2023-2024 | 3004368714 | 28/07/2023 | 26/10/2023 | W.B.S.E.D.C.LTD | 4.93 | 0 | 0 | 100
2 | MALDAH | Chanchal-I | Malda Mechanical | SWARUPGANJ Piped Water Supply Scheme | SM/12185 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of SWARUPGANJ, Kushida C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II |  | ORD/000465/2023-2024 | 3004368721 | 28/07/2023 | 26/10/2023 | W.B.S.E.D.C.LTD | 5.49 | 0 | 0 | 100
3 | MALDAH | Chanchal-I | Malda Division | SWARUPGANJ Piped Water Supply Scheme | SM/12185 | New | Material Requisition To Resource Division |  |  | RTOR000076/2023-2024 | 1811/MD | 27/04/2023 | 27/04/2023 | Resource Division | 23.46 | 0 | 0 | 0
4 | MALDAH | Chanchal-I | Malda Mechanical | SWARUPGANJ Piped Water Supply Scheme | SM/12185 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Swarupganj Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/013249) | Assistant Engineer - II | Junior Engineer-05 | ORD/000327/2023-2024 | 2329/MLMD | 26/07/2023 | 28/10/2025 | MERCURY ENGINEERING COMPANY. | 30.4 | 0 | 0 | 84
5 | MALDAH | Chanchal-I | Malda Division | SWARUPGANJ Piped Water Supply Scheme | SM/12185 | New | Construction of Boundary Wall at Head Work site of SWARUPGANJ Piped Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000917/2023-2024 | 379/MD | 17/01/2024 | 02/03/2024 | BANIK BROTHERS | 21.73 | 0 | 0 | 0
6 | MALDAH | Chanchal-I | Malda Division | SWARUPGANJ Piped Water Supply Scheme | SM/12185 | New | Construction of Boundary Wall at 2nd Tube well site of Swarupganj Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000606/2024-2025 | 5602/MD | 05/11/2024 | 04/01/2025 | BANIK BROTHERS | 6.93 | 0 | 0 | 0
7 | MALDAH | Chanchal-I | Malda Division | SWARUPGANJ Piped Water Supply Scheme | SM/12185 | New | Material Requisition To Resource Division |  |  | RTOR000178/2023-2024 | 755/MD | 19/02/2024 | 19/02/2024 | Resource Division | 12.32 | 0 | 0 | 0
8 | MALDAH | Chanchal-I | Malda Division | SWARUPGANJ Piped Water Supply Scheme | SM/12185 | New | Formal work order for the work of Implementation of SWARUPGANJ Water Supply Scheme at Chanchal-I Dev. Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000615/2022-2023 | 952/MD | 28/02/2023 | 23/03/2026 | BANIK BROTHERS | 469.75 | 0 | 0 | 75
9 | MALDAH | Chanchal-I | Malda Division | SWARUPGANJ Piped Water Supply Scheme | SM/12185 | New | Acceptance cum formal work order for Laying of Distribution of UPVC Pipeline of SWARUPGANJ Piped Water Supply Scheme at Chanchal-I Block of Malda District under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000106/2023-2024 | 2333/MD | 08/06/2023 | 07/08/2023 | ABANI BHUSAN GHOSH | 52.67 | 0 | 0 | 65
10 | MALDAH | Chanchal-I | Malda Division | SWARUPGANJ Piped Water Supply Scheme | SM/12185 | New | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Swarupganj Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000756/2024-2025 | 74 | 13/01/2025 | 01/10/2025 | BANIK BROTHERS | 83.72 | 0 | 0 | 0
Total | [13 empty] | 711.41 | 0 | 0