## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Harischandrapur-II | Malda Division | DAKSHIN BHAKURIA Piped Water Supply Scheme | SM/12186 | New | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. Big dia. and 135 Mtr. deep Tube Well Drilling by Direct Rotary method with 150 mm dia upvc strainer of 30m length all complete including cost of materials at Heads Work Site of UTTAR BHAKURIA Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000366/2022-2023 | 2695/MD | 17/11/2022 | 17/12/2022 | ASHIS CONSTRUCTION | 9.2 | 9.2 | 99.94 | 80
2 | MALDAH | Harischandrapur-II | Malda Division | DAKSHIN BHAKURIA Piped Water Supply Scheme | SM/12186 | New | Formal work order for the work of Implementation of DAKSHIN BHAKURIA Piped Water Supply Scheme at Harishchandrapur-I Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000234/2023-2024 | 2707/MD | 14/07/2023 | 09/04/2024 | MOTI RAHAMAN | 202.31 | 84.6 | 41.82 | 42
3 | MALDAH | Harischandrapur-II | Malda Mechanical | DAKSHIN BHAKURIA Piped Water Supply Scheme | SM/12186 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II and making compound lighting arrangement at T/W no. I of Dakshin Bhakuria Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/013248) | Assistant Engineer - II | Junior Engineer-05 | ORD/000314/2023-2024 | 2315/MLMD | 26/07/2023 | 09/11/2025 | DAS CONSTRUCTION | 25.62 | 16.93 | 66.07 | 78
4 | MALDAH | Harischandrapur-II | Malda Division | DAKSHIN BHAKURIA Piped Water Supply Scheme | SM/12186 | New | Material Requisition To Resource Division |  |  | RTOR000078/2023-2024 | 1811/MD | 27/04/2023 | 27/04/2023 | Resource Division | 9.78 | 0 | 0 | 0
5 | MALDAH | Harischandrapur-II | Malda Division | DAKSHIN BHAKURIA Piped Water Supply Scheme | SM/12186 | New | Construction of Boundary Wall at Head Work site of Dakshin Bhakuria Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000490/2024-2025 | 5003/MD | 27/09/2024 | 11/11/2024 | M/S TEWARI CONSTRUCTION | 32.97 | 0 | 0 | 0
6 | MALDAH | Harischandrapur-II | Malda Division | DAKSHIN BHAKURIA Piped Water Supply Scheme | SM/12186 | New | Construction of Boundary Wall at 2nd Tube Well site of Dakshin Bhakuria Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000185/2024-2025 | 2960/MD | 10/06/2024 | 10/07/2024 | SK ENTERPRISE | 6.46 | 0 | 0 | 95
7 | MALDAH | Harischandrapur-II | Malda Division | DAKSHIN BHAKURIA Piped Water Supply Scheme | SM/12186 | New | Material Requisition To Resource Division |  |  | RTOR000135/2023-2024 | 114/MD | 05/01/2024 | 05/01/2024 | Resource Division | 3.7 | 0 | 0 | 0
8 | MALDAH | Harischandrapur-II | Malda Mechanical | DAKSHIN BHAKURIA Piped Water Supply Scheme | SM/12186 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of DAKSHIN BHAKURIA, Bhaluka C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. |  |  | BILL/02462/2023-2024 | BP-2023-24-413 | 03/01/2024 | 03/01/2024 | W.B.S.E.D.C.LTD | 5.87 | 0 | 0 | 0
9 | MALDAH | Harischandrapur-II | Malda Mechanical | DAKSHIN BHAKURIA Piped Water Supply Scheme | SM/12186 | New | New service connection at Dakshin Bhakuria ph II PWSS T/W NO II Under EE/MLMD PHE DTE DIST. Malda.( Bhaluka c c c) |  |  | BILL/00757/2024-2025 | BP-2024-25-205 | 22/05/2024 | 22/05/2024 | W.B.S.E.D.C.LTD | 4.7 | 0 | 0 | 0
10 | MALDAH | Harischandrapur-II | Malda Division | DAKSHIN BHAKURIA Piped Water Supply Scheme | SM/12186 | New | Material Requisition To Resource Division |  |  | RTOR000082/2025-2026 | 5544/MD | 29/10/2025 | 29/10/2025 | Resource Division | 2.27 | 0 | 0 | 0
Total | [13 empty] | 302.88 | 110.72 | 36.56