## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Harischandrapur-II | Malda Mechanical | SAHAPUR Piped Water Supply Scheme | SM/12187 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of SAHAPUR ,Harishchandrapur C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II |  | ORD/000292/2023-2024 | 3004353830 | 17/07/2023 | 15/10/2023 | W.B.S.E.D.C.LTD | 8.31 | 8.31 | 100 | 100
2 | MALDAH | Harischandrapur-II | Malda Division | SAHAPUR Piped Water Supply Scheme | SM/12187 | New | Material Requisition To Resource Division |  |  | RTOR000020/2023-2024 | 1616/MD | 11/04/2023 | 11/04/2023 | Resource Division | 2.45 | 0 | 0 | 0
3 | MALDAH | Harischandrapur-II | Malda Division | SAHAPUR Piped Water Supply Scheme | SM/12187 | New | Material Requisition To Resource Division |  |  | RTOR000081/2023-2024 | 1811/MD | 27/04/2023 | 27/04/2023 | Resource Division | 1.2 | 0 | 0 | 0
4 | MALDAH | Harischandrapur-II | Malda Mechanical | SAHAPUR Piped Water Supply Scheme | SM/12187 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I and making compound lighting arrangement at T/W no. I of Sahapur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/013245) | Assistant Engineer - II | Junior Engineer-05 | ORD/000329/2023-2024 | 2331/MLMD | 26/07/2023 | 29/10/2025 | BEE GEE CONSTRUCTION. | 13.37 | 0 | 0 | 74
5 | MALDAH | Harischandrapur-II | Malda Division | SAHAPUR Piped Water Supply Scheme | SM/12187 | New | Material Requisition To Resource Division |  |  | RTOR000020/2024-2025 | 3996/MD | 08/08/2024 | 08/08/2024 | Resource Division | 2.34 | 0 | 0 | 0
6 | MALDAH | Harischandrapur-II | Malda Division | SAHAPUR Piped Water Supply Scheme | SM/12187 | New | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. Big dia. and 135 Mtr. deep Tube Well Drilling by Direct Rotary method with 150 mm dia upvc strainer of 30m length all complete including cost of materials at Heads Work Site of SAHAPUR Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000375/2022-2023 | 780/MD | 17/02/2023 | 19/03/2023 | SAUDAGAR (INDIA) | 9.2 | 9.18 | 99.71 | 0
7 | MALDAH | Harischandrapur-II | Malda Division | SAHAPUR Piped Water Supply Scheme | SM/12187 | New | Acceptance cum formal work order for Implementation of SAHAPUR Water Supply Scheme at Harishchandrapur-II Block of Malda district under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000490/2022-2023 | 594/MD | 09/02/2023 | 01/09/2024 | M/S /FAIZUL HAQUE BISWAS | 57.62 | 29.26 | 50.79 | 90
Total | [13 empty] | 94.49 | 46.75 | 49.48