## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Chanchal-I | Malda Division | PASCHIM BHAGABANPUR Piped Water Supply Scheme | SM/12188 | New | Material Requisition To Resource Division |  |  | RTOR000085/2023-2024 | 1811/MD | 27/04/2023 | 27/04/2023 | Resource Division | 22.21 | 0 | 0 | 0
2 | MALDAH | Chanchal-I | Malda Division | PASCHIM BHAGABANPUR Piped Water Supply Scheme | SM/12188 | New | Additional Laying Distribution of UPVC pipe line of PASCHIM BHAGABANPUR Piped Water Supply Scheme at Chanchal-I Dev. Block under Malda Division, P.H.E Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000960/2023-2024 | 711/MD | 09/02/2024 | 25/03/2024 | CHAKVIGU VIDYASAGAR SOCIAL WELFARE SOCIETY | 2.15 | 0 | 0 | 90
3 | MALDAH | Chanchal-I | Malda Division | PASCHIM BHAGABANPUR Piped Water Supply Scheme | SM/12188 | New | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 70m³/hr. capacity Pressure type IRON ELIMINATION Plant with Construction of Blower room & backwash water disposal at head work site of Paschim Bhagabanpur Water Supply Scheme of Chanchal-I Block under Malda Division P.H.E Dte in the District of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation,Mr. Tilok Roy, Junior Engineer | ORD/000318/2024-2025 | 3966/MD | 07/08/2024 | 03/02/2025 | SHREE BISHNU CONSTRUCTION | 30.26 | 0 | 0 | 0
4 | MALDAH | Chanchal-I | Malda Division | PASCHIM BHAGABANPUR Piped Water Supply Scheme | SM/12188 | New | Material Requisition To Resource Division |  |  | RTOR000117/2023-2024 | 87/MD | 05/01/2024 | 05/01/2024 | Resource Division | 11.09 | 0 | 0 | 0
5 | MALDAH | Chanchal-I | Malda Mechanical | PASCHIM BHAGABANPUR Piped Water Supply Scheme | SM/12188 | New | Additional quotation for paschim Bhagabanpur ph I DIST- MALDA .(kushida c c c) |  |  | BILL/00764/2024-2025 | BP-2024-25-204 | 22/05/2024 | 22/05/2024 | W.B.S.E.D.C.LTD | 0.1 | 0 | 0 | 0
6 | MALDAH | Chanchal-I | Malda Mechanical | PASCHIM BHAGABANPUR Piped Water Supply Scheme | SM/12188 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of PASCHIM BHAGABANPUR PWSS, Kushida C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. |  |  | BILL/02539/2023-2024 | BP-2023-24-442 | 10/01/2024 | 10/01/2024 | W.B.S.E.D.C.LTD | 6.34 | 0 | 0 | 0
7 | MALDAH | Chanchal-I | Malda Mechanical | PASCHIM BHAGABANPUR Piped Water Supply Scheme | SM/12188 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of PASCHIM BHAGABANPUR PWSS, Kushida C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. |  |  | BILL/02538/2023-2024 | BP-2023-24-441 | 10/01/2024 | 10/01/2024 | W.B.S.E.D.C.LTD | 6.83 | 0 | 0 | 0
8 | MALDAH | Chanchal-I | Malda Division | PASCHIM BHAGABANPUR Piped Water Supply Scheme | SM/12188 | New | Formal work order for the work of Implementation of PASCHIM BHAGABANPUR Water Supply Scheme at Chanchal-I Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000045/2023-2024 | 1995/MD | 17/05/2023 | 01/01/2026 | M/S TECHNICO & CO | 568.26 | 105.95 | 18.64 | 90
9 | MALDAH | Chanchal-I | Malda Mechanical | PASCHIM BHAGABANPUR Piped Water Supply Scheme | SM/12188 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Pascham Bhagabanpur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/013216) | Assistant Engineer - II | Junior Engineer-05 | ORD/000326/2023-2024 | 2328/MLMD | 26/07/2023 | 26/02/2026 | GHOSH BROTHERS... | 28.17 | 0 | 0 | 86
10 | MALDAH | Chanchal-I | Malda Division | PASCHIM BHAGABANPUR Piped Water Supply Scheme | SM/12188 | New | Construction of Boundary Wall at 2nd Tube Well site of Paschim Bhagabanpur Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000446/2024-2025 | 4735/MD | 11/09/2024 | 11/10/2024 | M/S MADHU CONSTRUCTION | 10.76 | 0 | 0 | 15
11 | MALDAH | Chanchal-I | Malda Division | PASCHIM BHAGABANPUR Piped Water Supply Scheme | SM/12188 | New | Sinking of Tubewell, Laying of Distribution Line, Providing FHTC, Construction of Pump House at Paschim Bhagabanpur Piped Water Supply Scheme at Chanchal-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000484/2024-2025 | 5084/MD | 27/09/2024 | 26/11/2024 | M/S TEWARI CONSTRUCTION | 92.44 | 0 | 0 | 20
Total | [13 empty] | 778.61 | 105.95 | 13.61