## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Habibpur | Malda Division | TALPUKUR Piped Water Supply Scheme | SM/12189 | New | Material Requisition To Resource Division |  |  | RTOR000032/2022-2023 | 3044/MD | 12/12/2022 |  | Resource Division | 15.84 | 0 | 0 | 0
2 | MALDAH | Habibpur | Malda Division | TALPUKUR Piped Water Supply Scheme | SM/12189 | New | Material Requisition To Resource Division |  |  | RTOR000025/2023-2024 | 1605/MD | 11/04/2023 |  | Resource Division | 13.49 | 0 | 0 | 0
3 | MALDAH | Habibpur | Malda Mechanical | TALPUKUR Piped Water Supply Scheme | SM/12189 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of Talpukur , Aiho C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II | Junior Engineer-03 | ORD/001907/2023-2024 | 3004501325 | 28/11/2023 | 26/02/2024 | W.B.S.E.D.C.LTD | 3.83 | 3.83 | 100 | 100
4 | MALDAH | Habibpur | Malda Mechanical | TALPUKUR Piped Water Supply Scheme | SM/12189 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Talpukur , Aiho C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II | Junior Engineer-03 | ORD/001906/2023-2024 | 3004501336 | 28/11/2023 | 26/02/2024 | W.B.S.E.D.C.LTD | 6.96 | 6.61 | 94.95 | 100
5 | MALDAH | Habibpur | Malda Division | TALPUKUR Piped Water Supply Scheme | SM/12189 | New | Construction of Boundary Wall at 2nd Tube well Site of Talpukur Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000163/2024-2025 | 2938/MD | 10/06/2024 | 10/07/2024 | BANIK BROTHERS | 8.99 | 0 | 0 | 0
6 | MALDAH | Habibpur | Malda Division | TALPUKUR Piped Water Supply Scheme | SM/12189 | New | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 60m³/hr. capacity Pressure type IRON ELIMINATION Plant with Construction of Blower room & backwash water disposal at head work site of Talpukur Water Supply Scheme of Habibpur Block under Malda Division P.H.E Dte in the District of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000207/2024-2025 | 3028/MD | 13/06/2024 | 10/12/2024 | BANIK BROTHERS | 28.84 | 0 | 0 | 0
7 | MALDAH | Habibpur | Malda Mechanical | TALPUKUR Piped Water Supply Scheme | SM/12189 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Talpukur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/013199) | Assistant Engineer - II | Junior Engineer-03 | ORD/000240/2023-2024 | 2257/MLMD | 18/07/2023 | 15/11/2023 | GHOSH BROTHERS... | 28.3 | 22.52 | 79.6 | 60
8 | MALDAH | Habibpur | Malda Division | TALPUKUR Piped Water Supply Scheme | SM/12189 | New | Formal work order for the work of Implementation of TALPUKUR Water Supply Scheme at Habibpur Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000043/2023-2024 | 1899/MD | 10/05/2023 | 09/05/2024 | BANIK BROTHERS | 523.57 | 335.98 | 64.17 | 71
9 | MALDAH | Habibpur | Malda Division | TALPUKUR Piped Water Supply Scheme | SM/12189 | New | Construction of Boundary Wall at Head Work site of Talpukur Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000883/2023-2024 | 159/MD | 08/01/2024 | 22/02/2024 | BANIK BROTHERS | 22.15 | 0.1 | 0.44 | 100
Total | [13 empty] | 651.97 | 369.04 | 56.6