## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Habibpur | Malda Division | TALPUKUR Piped Water Supply Scheme | SM/12189 | New | Material Requisition To Resource Division |  |  | RTOR000032/2022-2023 | 3044/MD | 12/12/2022 | 12/12/2022 | Resource Division | 15.84 | 0 | 0 | 0
2 | MALDAH | Habibpur | Malda Division | TALPUKUR Piped Water Supply Scheme | SM/12189 | New | Formal work order for the work of Implementation of TALPUKUR Water Supply Scheme at Habibpur Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000043/2023-2024 | 1899/MD | 10/05/2023 | 24/08/2026 | BANIK BROTHERS | 523.57 | 369.01 | 70.48 | 71
3 | MALDAH | Habibpur | Malda Mechanical | TALPUKUR Piped Water Supply Scheme | SM/12189 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Talpukur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/013199) | Assistant Engineer - II | Junior Engineer-03,Junior Engineer-06 | ORD/000240/2023-2024 | 2257/MLMD | 18/07/2023 | 26/02/2026 | GHOSH BROTHERS... | 28.3 | 22.52 | 79.6 | 76
4 | MALDAH | Habibpur | Malda Mechanical | TALPUKUR Piped Water Supply Scheme | SM/12189 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Talpukur , Aiho C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II | Junior Engineer-03 | ORD/001906/2023-2024 | 3004501336 | 28/11/2023 | 26/02/2024 | W.B.S.E.D.C.LTD | 6.96 | 6.96 | 100 | 100
5 | MALDAH | Habibpur | Malda Mechanical | TALPUKUR Piped Water Supply Scheme | SM/12189 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of Talpukur , Aiho C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II | Junior Engineer-03 | ORD/001907/2023-2024 | 3004501325 | 28/11/2023 | 26/02/2024 | W.B.S.E.D.C.LTD | 3.83 | 3.83 | 100 | 100
6 | MALDAH | Habibpur | Malda Division | TALPUKUR Piped Water Supply Scheme | SM/12189 | New | Material Requisition To Resource Division |  |  | RTOR000025/2023-2024 | 1605/MD | 11/04/2023 | 11/04/2023 | Resource Division | 13.49 | 0 | 0 | 0
7 | MALDAH | Habibpur | Malda Division | TALPUKUR Piped Water Supply Scheme | SM/12189 | New | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Talpukur Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000662/2024-2025 | 6162/MD | 05/12/2024 | 19/01/2025 | IDEAL CONSTRUCTION | 26.03 | 0 | 0 | 0
8 | MALDAH | Habibpur | Malda Division | TALPUKUR Piped Water Supply Scheme | SM/12189 | New | Construction of Boundary Wall at Head Work site of Talpukur Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000883/2023-2024 | 159/MD | 08/01/2024 | 22/02/2024 | BANIK BROTHERS | 22.15 | 21.82 | 98.53 | 100
9 | MALDAH | Habibpur | Malda Division | TALPUKUR Piped Water Supply Scheme | SM/12189 | New | Construction of Boundary Wall at 2nd Tube well Site of Talpukur Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000163/2024-2025 | 2938/MD | 10/06/2024 | 10/07/2024 | BANIK BROTHERS | 8.99 | 0 | 0 | 100
10 | MALDAH | Habibpur | Malda Division | TALPUKUR Piped Water Supply Scheme | SM/12189 | New | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 60m³/hr. capacity Pressure type IRON ELIMINATION Plant with Construction of Blower room & backwash water disposal at head work site of Talpukur Water Supply Scheme of Habibpur Block under Malda Division P.H.E Dte in the District of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000207/2024-2025 | 3028/MD | 13/06/2024 | 01/04/2025 | BANIK BROTHERS | 28.84 | 0 | 0 | 100
11 | MALDAH | Habibpur | Malda Division | TALPUKUR Piped Water Supply Scheme | SM/12189 | New | Erection of Property board and dissemination of Property information through wall painting related to Jal Jeevan Mission works of Chaksukur, Dalla, Talpukur, Aiho PWSS under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000955/2024-2025 | 644/MD | 19/02/2025 | 26/02/2025 | SADHANA CONSTRUCTION | 0.81 | 0 | 0 | 0
Total | [13 empty] | 678.81 | 424.15 | 62.48