## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Harischandrapur-I | Malda Division | KISMAT BAROL Piped Water Supply Scheme | SM/12190 | New | Material Requisition To Resource Division |  |  | RTOR000034/2022-2023 | 3046/MD | 12/12/2022 | 12/12/2022 | Resource Division | 22.91 | 0 | 0 | 0
2 | MALDAH | Harischandrapur-I | Malda Division | KISMAT BAROL Piped Water Supply Scheme | SM/12190 | New | Material Requisition To Resource Division |  |  | RTOR000012/2023-2024 | 1612/MD | 11/04/2023 | 11/04/2023 | Resource Division | 14.33 | 0 | 0 | 0
3 | MALDAH | Harischandrapur-I | Malda Mechanical | KISMAT BAROL Piped Water Supply Scheme | SM/12190 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II and making compound lighting arrangement at T/W no. I of Kismat Barol Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/013044) | Assistant Engineer - II | Junior Engineer-05 | ORD/000320/2023-2024 | 2322/MLMD | 26/07/2023 | 23/11/2023 | S. P. CONSTRUCTION | 26.28 | 0 | 0 | 52
4 | MALDAH | Harischandrapur-I | Malda Division | KISMAT BAROL Piped Water Supply Scheme | SM/12190 | New | Construction of Boundary Wall at 2nd Tube Well site of Kismatbarol Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000167/2024-2025 | 2942/MD | 10/06/2024 | 10/07/2024 | S & G CONSTRUCTION | 8.41 | 0 | 0 | 0
5 | MALDAH | Harischandrapur-I | Malda Mechanical | KISMAT BAROL Piped Water Supply Scheme | SM/12190 | New | New service connection at KISMATBAROL Pwss pH NO II Under EE/MLMD PHE DTE DIST. Malda.( kushida c c c) |  |  | BILL/03680/2023-2024 | BP-2023-24-663 | 11/03/2024 | 11/03/2024 | W.B.S.E.D.C.LTD | 8.14 | 0 | 0 | 0
6 | MALDAH | Harischandrapur-I | Malda Mechanical | KISMAT BAROL Piped Water Supply Scheme | SM/12190 | New | New service connection at Kismatbaral PWSS T/W NO I Under EE/MLMD PHE DTE DIST. Malda.(kushida c c c) |  |  | BILL/00758/2024-2025 | BP-2024-25-203 | 22/05/2024 | 22/05/2024 | W.B.S.E.D.C.LTD | 3.79 | 0 | 0 | 0
7 | MALDAH | Harischandrapur-I | Malda Division | KISMAT BAROL Piped Water Supply Scheme | SM/12190 | New | Formal work order for the work of Implementation of KISMAT BAROL Water Supply Scheme at Harishchandrapur-I Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000094/2023-2024 | 2115/MD | 06/06/2023 | 28/01/2025 | MILLENNIUM ENTERPRISR | 463.93 | 0 | 0 | 52
8 | MALDAH | Harischandrapur-I | Malda Division | KISMAT BAROL Piped Water Supply Scheme | SM/12190 | New | Construction of Boundary Wall at Head Work site of Kismatbarol Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000214/2024-2025 | 3035/MD | 13/06/2024 | 01/01/2026 | MILLENNIUM ENTERPRISE | 28.66 | 0 | 0 | 80
9 | MALDAH | Harischandrapur-I | Malda Division | KISMAT BAROL Piped Water Supply Scheme | SM/12190 | New | Dedicated/Parallel Pipe Line for better functionality and road restoration of Kismat Baral Piped Water Supply Scheme at Harishchandrapur-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Sri Susanta Saha, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000690/2025-2026 | 5919/MD | 26/11/2025 | 25/01/2026 | MILLENNIUM ENTERPRISE | 44.43 | 0 | 0 | 0
Total | [13 empty] | 620.87 | 0 | 0