## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Harischandrapur-II | Malda Division | MALIOR PWSS | SM/12192 | New | Material Requisition To Resource Division |  |  | RTOR000038/2022-2023 | 3050/MD | 12/12/2022 | 12/12/2022 | Resource Division | 25.1 | 0 | 0 | 0
2 | MALDAH | Harischandrapur-II | Malda Division | MALIOR PWSS | SM/12192 | New | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. Big dia. and 135 Mtr. deep Tube Well Drilling by Direct Rotary method with 150 mm dia upvc strainer of 30m length all complete including cost of materials at Heads Work Site of MALIOR Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer |  | ORD/000372/2022-2023 | 2700/MD | 17/11/2022 | 17/12/2022 | SAUDAGAR (INDIA) | 9.2 | 9.2 | 100 | 100
3 | MALDAH | Harischandrapur-II | Malda Division | MALIOR PWSS | SM/12192 | New | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. dia. and 150 Mtr. Deep Big dia Tube well (1 No) at MALIOR Water Supply Scheme under Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Junior Engineer | ORD/000604/2022-2023 | 922/MD | 27/02/2023 | 29/03/2023 | MERCURY ENGINEERING COMPANY | 10.13 | 10.01 | 98.79 | 100
4 | MALDAH | Harischandrapur-II | Malda Mechanical | MALIOR PWSS | SM/12192 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No.II of Malior PWSS, Bhaluka C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II |  | ORD/001521/2023-2024 | 3004390586 | 15/09/2023 | 14/12/2023 | W.B.S.E.D.C.LTD | 4.33 | 4.33 | 100 | 100
5 | MALDAH | Harischandrapur-II | Malda Mechanical | MALIOR PWSS | SM/12192 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No.I of Malior PWSS, Bhaluka C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II |  | ORD/001522/2023-2024 | 3004390575 | 15/09/2023 | 14/12/2023 | W.B.S.E.D.C.LTD | 4.14 | 4.14 | 100 | 100
6 | MALDAH | Harischandrapur-II | Malda Division | MALIOR PWSS | SM/12192 | New | Material Requisition To Resource Division |  |  | RTOR000014/2023-2024 | 1618/MD | 11/04/2023 | 11/04/2023 | Resource Division | 17.18 | 0 | 0 | 0
7 | MALDAH | Harischandrapur-II | Malda Division | MALIOR PWSS | SM/12192 | New | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 70m³/hr. capacity Pressure type IRON ELIMINATION Plant with Construction of Blower room & backwash water disposal at head work site of Malior Water Supply Scheme of Harishchandrapur-II Block under Malda Division P.H.E Dte in the District of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation,Mr. Tilok Roy, Junior Engineer | ORD/000319/2024-2025 | 3967/MD | 07/08/2024 | 03/02/2025 | SUBHAS CHANDRA KESHARI | 30.15 | 0 | 0 | 0
8 | MALDAH | Harischandrapur-II | Malda Division | MALIOR PWSS | SM/12192 | New | Material Requisition To Resource Division |  |  | RTOR000004/2024-2025 | 3924/MD | 06/08/2024 | 06/08/2024 | Resource Division | 4.07 | 0 | 0 | 0
9 | MALDAH | Harischandrapur-II | Malda Division | MALIOR PWSS | SM/12192 | New | Formal work order for the work of Implementation of MALIOR Water Supply Scheme at HarishchandrapurII Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000066/2023-2024 | 2021/MD | 18/05/2023 | 31/12/2025 | JAHANGIR ALAM | 509.49 | 193.36 | 37.95 | 95
10 | MALDAH | Harischandrapur-II | Malda Mechanical | MALIOR PWSS | SM/12192 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Malior Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/013022) | Assistant Engineer - II | Junior Engineer-05 | ORD/000242/2023-2024 | 2259/MLMD | 18/07/2023 | 29/08/2025 | NIRMAN. | 26.34 | 17.93 | 68.05 | 83
11 | MALDAH | Harischandrapur-II | Malda Division | MALIOR PWSS | SM/12192 | New | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Malior Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000736/2024-2025 | 55 | 08/01/2025 | 15/11/2025 | ABHIJIT PAUL | 28.77 | 0 | 0 | 70
12 | MALDAH | Harischandrapur-II | Malda Division | MALIOR PWSS | SM/12192 | New | Construction of Boundary Wall at Head Work site of Malior Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. (3rd Call). | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000012/2025-2026 | 2420/MD | 27/05/2025 | 11/07/2025 | JAHANGIR ALAM | 27.3 | 0 | 0 | 0
13 | MALDAH | Harischandrapur-II | Malda Division | MALIOR PWSS | SM/12192 | New | Construction of Boundary Wall at 2nd Tube Well site of Malior Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000183/2024-2025 | 2958/MD | 10/06/2024 | 10/07/2024 | M/S MAA TARA ENTERPRISE | 7.24 | 0 | 0 | 100
14 | MALDAH | Harischandrapur-II | Malda Division | MALIOR PWSS | SM/12192 | New | Erection of Property board related to Jal Jeevan Mission works of Talsur, Sadlichak, Dakhin Bhakuria, Malior, Harishchandrapur Zone-I PWSS under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000961/2024-2025 | 650/MD | 19/02/2025 | 26/02/2025 | M/S SABANA CONSTRUCTION | 0.9 | 0 | 0 | 100
Total | [13 empty] | 704.35 | 238.96 | 33.93