## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Harischandrapur-I | Malda Mechanical | BANGRUA PWSS | SM/12193 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Bangrua Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/013018) | Assistant Engineer - II | Junior Engineer-05 | ORD/000243/2023-2024 | 2260/MLMD | 18/07/2023 | 16/11/2025 | SOUMEN ELECTRIC, | 26.41 | 20.86 | 78.99 | 84
2 | MALDAH | Harischandrapur-I | Malda Division | BANGRUA PWSS | SM/12193 | New | Formal work order for the work of Implementation of BANGRUA Piped Water Supply Scheme at Harishchandrapur-I Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation,Mr. Tilok Roy, Junior Engineer | ORD/000389/2023-2024 | 3289/MD | 23/08/2023 | 01/07/2025 | KUNDU CONSTRUCTION | 148.48 | 0 | 0 | 65
3 | MALDAH | Harischandrapur-I | Malda Division | BANGRUA PWSS | SM/12193 | New | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. Big dia. and 135 Mtr. deep Tube Well Drilling by Direct Rotary method with 150 mm dia upvc strainer of 30m length all complete including cost of materials at Heads Work Site of BANGRUA Piped Water Supply Scheme at Harishchandrapur-I Block of Malda District under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000371/2022-2023 | 778/MD | 17/02/2023 | 19/03/2023 | SAUDAGAR (INDIA) | 9.2 | 8.87 | 96.35 | 100
4 | MALDAH | Harischandrapur-I | Malda Mechanical | BANGRUA PWSS | SM/12193 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of BANGRUA PWSS, Harishchandrapur C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II |  | ORD/001018/2023-2024 | 3004401750 | 12/09/2023 | 11/12/2023 | W.B.S.E.D.C.LTD | 5.47 | 5.47 | 100 | 100
5 | MALDAH | Harischandrapur-I | Malda Division | BANGRUA PWSS | SM/12193 | New | Material Requisition To Resource Division |  |  | RTOR000088/2023-2024 | 1811/MD | 27/04/2023 | 27/04/2023 | Resource Division | 6.97 | 0 | 0 | 0
6 | MALDAH | Harischandrapur-I | Malda Division | BANGRUA PWSS | SM/12193 | New | Construction of Boundary Wall at 2nd Tube Well site of Bangrua Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer ,Sri Susanta Saha, Assistant Engineer | Mr. Susanta Pal, JE_Deputation,Mr. Tilok Roy, Junior Engineer | ORD/000188/2024-2025 | 2967/MD | 10/06/2024 | 01/07/2025 | BINA CONSTRUCTION | 7.26 | 0 | 0 | 100
7 | MALDAH | Harischandrapur-I | Malda Division | BANGRUA PWSS | SM/12193 | New | Material Requisition To Resource Division |  |  | RTOR000124/2023-2024 | 94/MD | 05/01/2024 | 05/01/2024 | Resource Division | 3.08 | 0 | 0 | 0
8 | MALDAH | Harischandrapur-I | Malda Division | BANGRUA PWSS | SM/12193 | New | Material Requisition To Resource Division |  |  | RTOR000017/2024-2025 | 3993/MD | 08/08/2024 | 08/08/2024 | Resource Division | 3.7 | 0 | 0 | 0
9 | MALDAH | Harischandrapur-I | Malda Mechanical | BANGRUA PWSS | SM/12193 | New | New service connection at BANGRUA PWSS T/W NO II Under EE/MLMD PHE DTE DIST. Malda.( Harishchandrapur c c c) |  |  | BILL/00765/2024-2025 | BP-2024-25-201 | 22/05/2024 | 22/05/2024 | W.B.S.E.D.C.LTD | 3.27 | 0 | 0 | 0
10 | MALDAH | Harischandrapur-I | Malda Division | BANGRUA PWSS | SM/12193 | New | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Bangrua Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation,Mr. Tilok Roy, Junior Engineer | ORD/000573/2024-2025 | 1150/MD | 21/03/2025 | 01/11/2025 | A. B. CONSTRUCTION | 26.08 | 0 | 0 | 60
11 | MALDAH | Harischandrapur-I | Malda Division | BANGRUA PWSS | SM/12193 | New | Construction of Boundary Wall at Head Work site of BANGURA Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation,Mr. Tilok Roy, Junior Engineer | ORD/000207/2025-2026 | 3704/MD | 29/07/2025 | 27/09/2025 | M/S GHOSH CONSTRUCTION | 22.26 | 0 | 0 | 0
Total | [13 empty] | 262.17 | 35.2 | 13.43