## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Harischandrapur-II | Malda Division | PUTIA PWSS | SM/12194 | New | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. dia. and 150 Mtr. Deep Big dia Tube well (1 No) at PUTIA Water Supply Scheme under Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Junior Engineer | ORD/000608/2022-2023 | 926/MD | 27/02/2023 | 29/03/2023 | DUTTA ENTERPRISE | 10.13 | 0 | 0 | 100
2 | MALDAH | Harischandrapur-II | Malda Mechanical | PUTIA PWSS | SM/12194 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Putia, Harishchandrapur C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II |  | ORD/000296/2023-2024 | 3004353826 | 20/07/2023 | 18/10/2023 | W.B.S.E.D.C.LTD | 3.3 | 0 | 0 | 100
3 | MALDAH | Harischandrapur-II | Malda Division | PUTIA PWSS | SM/12194 | New | Material Requisition To Resource Division |  |  | RTOR000019/2023-2024 | 1609/MD | 11/04/2023 | 11/04/2023 | Resource Division | 0.81 | 0 | 0 | 0
4 | MALDAH | Harischandrapur-II | Malda Division | PUTIA PWSS | SM/12194 | New | Acceptance cum formal work order for Implementation of PUTIA Piped Water Supply Scheme at Harishchandrapur-II Block of Malda district under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000489/2022-2023 | 593/MD | 09/02/2023 | 10/05/2023 | PARIJAT RAY | 41.34 | 0 | 0 | 95
5 | MALDAH | Harischandrapur-II | Malda Mechanical | PUTIA PWSS | SM/12194 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I and making compound lighting arrangement at T/W no. I of Putia Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/013011) | Assistant Engineer - II | Junior Engineer-05 | ORD/000325/2023-2024 | 2327/MLMD | 26/07/2023 | 23/11/2023 | NEOGI ENTERPRISE. | 13.5 | 0 | 0 | 78
6 | MALDAH | Harischandrapur-II | Malda Division | PUTIA PWSS | SM/12194 | New | Material Requisition To Resource Division |  |  | RTOR000006/2024-2025 | 3918/MD | 06/08/2024 | 06/08/2024 | Resource Division | 0.22 | 0 | 0 | 0
7 | MALDAH | Harischandrapur-II | Malda Division | PUTIA PWSS | SM/12194 | New | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Putia Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000738/2024-2025 | 57 | 08/01/2025 | 22/02/2025 | CHOWDHURY CONSTRUCTION | 1.61 | 0 | 0 | 0
Total | [13 empty] | 70.92 | 0 | 0