## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Harischandrapur - I | Malda Division | PARO PWSS | SM/12195 | New | Material Requisition To Resource Division |  |  | RTOR000089/2023-2024 | 1811/MD | 27/04/2023 |  | Resource Division | 12.8 | 0 | 0 | 0
2 | MALDAH | Harischandrapur - I | Malda Mechanical | PARO PWSS | SM/12195 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Paro Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/012960) | Assistant Engineer - II | Junior Engineer-05 | ORD/000239/2023-2024 | 2256/MLMD | 18/07/2023 | 15/11/2023 | ALPHA ENTERPRISE. | 26.3 | 0 | 0 | 0
3 | MALDAH | Harischandrapur - I | Malda Division | PARO PWSS | SM/12195 | New | Material Requisition To Resource Division |  |  | RTOR000132/2023-2024 | 109/MD | 05/01/2024 |  | Resource Division | 6.16 | 0 | 0 | 0
4 | MALDAH | Harischandrapur - I | Malda Division | PARO PWSS | SM/12195 | New | Laying of Distribution of UPVC Pipeline of PARO Piped Water Supply Scheme at Harishchandrapur-I Block of Malda District under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000932/2023-2024 | 598/MD | 06/02/2024 | 06/04/2024 | MD. TALEB ALI | 64.62 | 0 | 0 | 80
5 | MALDAH | Harischandrapur - I | Malda Division | PARO PWSS | SM/12195 | New | Construction of Boundary Wall at 2nd Tube Well site of Paro Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000166/2024-2025 | 2941/MD | 10/06/2024 | 10/07/2024 | VISCOUS ENGINEERS PVT. LTD. | 8.24 | 0 | 0 | 0
6 | MALDAH | Harischandrapur - I | Malda Division | PARO PWSS | SM/12195 | New | Material Requisition To Resource Division |  |  | RTOR000018/2024-2025 | 3994/MD | 08/08/2024 |  | Resource Division | 7.39 | 0 | 0 | 0
7 | MALDAH | Harischandrapur - I | Malda Division | PARO PWSS | SM/12195 | New | Formal work order for the work of Implementation of PARO Piped Water Supply Scheme at Harishchandrapur-I Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000309/2023-2024 | 2873/MD | 26/07/2023 | 21/04/2024 | VISCOUS ENGINEERS PVT. LTD. | 228.95 | 0 | 0 | 71
Total | [13 empty] | 354.46 | 0 | 0