## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Harischandrapur-I | Malda Division | PARO PWSS | SM/12195 | New | Material Requisition To Resource Division |  |  | RTOR000089/2023-2024 | 1811/MD | 27/04/2023 | 27/04/2023 | Resource Division | 12.8 | 0 | 0 | 0
2 | MALDAH | Harischandrapur-I | Malda Division | PARO PWSS | SM/12195 | New | Construction of Boundary Wall at 2nd Tube Well site of Paro Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000166/2024-2025 | 2941/MD | 10/06/2024 | 10/07/2024 | VISCOUS ENGINEERS PVT. LTD. | 8.24 | 0 | 0 | 0
3 | MALDAH | Harischandrapur-I | Malda Division | PARO PWSS | SM/12195 | New | Material Requisition To Resource Division |  |  | RTOR000132/2023-2024 | 109/MD | 05/01/2024 | 05/01/2024 | Resource Division | 6.16 | 0 | 0 | 0
4 | MALDAH | Harischandrapur-I | Malda Division | PARO PWSS | SM/12195 | New | Material Requisition To Resource Division |  |  | RTOR000018/2024-2025 | 3994/MD | 08/08/2024 | 08/08/2024 | Resource Division | 7.39 | 0 | 0 | 0
5 | MALDAH | Harischandrapur-I | Malda Mechanical | PARO PWSS | SM/12195 | New | New service connection at PARO PWSS T/W NO I Under EE/MLMD PHE DTE DIST. Malda.( Harishchandrapur c c c) |  |  | BILL/02561/2024-2025 | BP-2024-25-576 | 28/11/2024 | 28/11/2024 | W.B.S.E.D.C.LTD | 11.55 | 0 | 0 | 0
6 | MALDAH | Harischandrapur-I | Malda Mechanical | PARO PWSS | SM/12195 | New | New service connection at PARO PWSS T/W NO II Under EE/MLMD PHE DTE DIST. Malda.( Harishchandrapur c c c) |  |  | BILL/02560/2024-2025 | BP-2024-25-575 | 28/11/2024 | 28/11/2024 | W.B.S.E.D.C.LTD | 4.05 | 0 | 0 | 0
7 | MALDAH | Harischandrapur-I | Malda Division | PARO PWSS | SM/12195 | New | Formal work order for the work of Implementation of PARO Piped Water Supply Scheme at Harishchandrapur-I Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000309/2023-2024 | 2873/MD | 26/07/2023 | 01/04/2026 | VISCOUS ENGINEERS PVT. LTD. | 228.95 | 112.13 | 48.98 | 72
8 | MALDAH | Harischandrapur-I | Malda Division | PARO PWSS | SM/12195 | New | Laying of Distribution of UPVC Pipeline of PARO Piped Water Supply Scheme at Harishchandrapur-I Block of Malda District under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000932/2023-2024 | 598/MD | 06/02/2024 | 06/04/2024 | MD. TALEB ALI | 64.62 | 54.3 | 84.03 | 80
9 | MALDAH | Harischandrapur-I | Malda Division | PARO PWSS | SM/12195 | New | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Paro Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000479/2024-2025 | 4994/MD | 27/09/2024 | 31/01/2025 | S. R. CONSTRUCTION | 52.14 | 0 | 0 | 0
10 | MALDAH | Harischandrapur-I | Malda Division | PARO PWSS | SM/12195 | New | Construction of Boundary Wall at Head Work site of Paro Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. (2nd Call) | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000148/2025-2026 | 2686/MD | 04/06/2025 | 19/07/2025 | VISCOUS ENGINEERS PVT. LTD. | 25.78 | 0 | 0 | 0
Total | [13 empty] | 421.67 | 166.44 | 39.47