## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Harischandrapur-II | Malda Division | SULTANNAGAR PWSS | SM/12196 | New | Material Requisition To Resource Division |  |  | RTOR000037/2022-2023 | 3049/MD | 12/12/2022 | 12/12/2022 | Resource Division | 25.94 | 0 | 0 | 0
2 | MALDAH | Harischandrapur-II | Malda Division | SULTANNAGAR PWSS | SM/12196 | New | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. Big dia. and 135 Mtr. deep Tube Well Drilling by Direct Rotary method with 150 mm dia upvc strainer of 30m length all complete including cost of materials at Heads Work Site of SULTANNAGAR Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer |  | ORD/000370/2022-2023 | 2699/MD | 17/11/2022 | 17/12/2022 | ASHIS CONSTRUCTION | 9.2 | 8.55 | 92.88 | 1
3 | MALDAH | Harischandrapur-II | Malda Division | SULTANNAGAR PWSS | SM/12196 | New | Continuation work order for Hiring of inspection Vehicle (Non-Air-Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long jurney and should be covered any where without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, Malda Sadar Sub-Division, PHE Dte. under Malda Division, PHE Dte. (Period from 01/01/2023 to 30/06/2023). | Mr. Arnab Giri, Assistant Engineer |  | ORD/000819/2022-2023 | 519/MSD | 30/12/2022 | 30/06/2023 | ARUN KUMAR DAS | 0.86 | 1.04 | 122 | 71
4 | MALDAH | Harischandrapur-II | Malda Mechanical | SULTANNAGAR PWSS | SM/12196 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Sultannagar PWSS, Harishchandrapur C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II |  | ORD/000091/2023-2024 | 3004232824 | 17/05/2023 | 15/08/2023 | W.B.S.E.D.C.LTD | 5.28 | 5.28 | 100 | 0
5 | MALDAH | Harischandrapur-II | Malda Division | SULTANNAGAR PWSS | SM/12196 | New | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. dia. and 150 Mtr. Deep Big dia Tube well (1 No) at SULTANNAGAR Water Supply Scheme under Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000605/2022-2023 | 923/MD | 27/02/2023 | 29/03/2023 | DUTTA ENTERPRISE | 10.13 | 10.13 | 99.92 | 100
6 | MALDAH | Harischandrapur-II | Malda Mechanical | SULTANNAGAR PWSS | SM/12196 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of SULTANNAGAR, Harishchandrapur C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II |  | ORD/000295/2023-2024 | 3004353821 | 20/07/2023 | 18/10/2023 | W.B.S.E.D.C.LTD | 2.66 | 2.66 | 100 | 100
7 | MALDAH | Harischandrapur-II | Malda Division | SULTANNAGAR PWSS | SM/12196 | New | Material Requisition To Resource Division |  |  | RTOR000013/2023-2024 | 1620/MD | 11/04/2023 | 11/04/2023 | Resource Division | 10.22 | 0 | 0 | 0
8 | MALDAH | Harischandrapur-II | Malda Mechanical | SULTANNAGAR PWSS | SM/12196 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Sultannagar Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/012936) | Assistant Engineer - II | Junior Engineer-05 | ORD/000028/2023-2024 | 785/ MLMD | 27/04/2023 | 29/10/2025 | M/S SAJAHAN CHOWDHURY | 28.18 | 24.3 | 86.24 | 85
9 | MALDAH | Harischandrapur-II | Malda Division | SULTANNAGAR PWSS | SM/12196 | New | Formal work order for the work of Implementation of SULTANNAGAR Water Supply Scheme at HARISHCHANDRAPUR-II Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000030/2023-2024 | 1845/MD | 02/05/2023 | 28/09/2026 | M/S ALISA CONSTRUCTIION | 289.64 | 159.22 | 54.97 | 89
10 | MALDAH | Harischandrapur-II | Malda Division | SULTANNAGAR PWSS | SM/12196 | New | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Sultannagar Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation,Mr. Tilok Roy, Junior Engineer | ORD/000660/2024-2025 | 1261/MD | 28/03/2025 | 01/04/2026 | M/S AYUSH BUILDERS | 22.7 | 0 | 0 | 0
Total | [13 empty] | 404.81 | 211.18 | 52.17