## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Harischandrapur-I | Malda Division | MABARAKPUR PWSS | SM/12197 | New | Material Requisition To Resource Division |  |  | RTOR000033/2022-2023 | 3045/MD | 12/12/2022 | 12/12/2022 | Resource Division | 24.43 | 0 | 0 | 0
2 | MALDAH | Harischandrapur-I | Malda Mechanical | MABARAKPUR PWSS | SM/12197 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. III of MABARAKPUR PWSS, Old Malda C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II |  | ORD/001517/2023-2024 | 3004375733 | 01/09/2023 | 30/11/2023 | W.B.S.E.D.C.LTD | 5.77 | 5.77 | 100 | 100
3 | MALDAH | Harischandrapur-I | Malda Mechanical | MABARAKPUR PWSS | SM/12197 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. IV of MABARAKPUR PWSS, Old Malda C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II |  | ORD/001518/2023-2024 | 3004375650 | 01/09/2023 | 30/11/2023 | W.B.S.E.D.C.LTD | 3.11 | 3.11 | 100 | 100
4 | MALDAH | Harischandrapur-I | Malda Division | MABARAKPUR PWSS | SM/12197 | New | Material Requisition To Resource Division |  |  | RTOR000011/2023-2024 | 1619/MD | 11/04/2023 | 11/04/2023 | Resource Division | 16.07 | 0 | 0 | 0
5 | MALDAH | Harischandrapur-I | Malda Division | MABARAKPUR PWSS | SM/12197 | New | Construction of Boundary Wall at 2nd Tube Well site of Mabarakpur Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000168/2024-2025 | 2943/MD | 10/06/2024 | 10/07/2024 | SUBHAS CHANDRA KESHARI | 8.39 | 0 | 0 | 0
6 | MALDAH | Harischandrapur-I | Malda Division | MABARAKPUR PWSS | SM/12197 | New | Construction of Boundary Wall at Head Work site of Mabarakpur Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000215/2024-2025 | 3036/MD | 13/06/2024 | 13/07/2024 | SUBHAS CHANDRA KESHARI | 25.86 | 0 | 0 | 0
7 | MALDAH | Harischandrapur-I | Malda Division | MABARAKPUR PWSS | SM/12197 | New | Material Requisition To Resource Division |  |  | RTOR000181/2023-2024 | 774/MD | 20/02/2024 | 20/02/2024 | Resource Division | 5.54 | 0 | 0 | 0
8 | MALDAH | Harischandrapur-I | Malda Mechanical | MABARAKPUR PWSS | SM/12197 | New | New service connection at MABARAKPURPUR Pwss pH NO II EE/MLMD PHE DTE DIST. Malda.( kushida c c c) |  |  | BILL/03676/2023-2024 | BP-2023-24-659 | 11/03/2024 | 11/03/2024 | W.B.S.E.D.C.LTD | 7.69 | 0 | 0 | 0
9 | MALDAH | Harischandrapur-I | Malda Mechanical | MABARAKPUR PWSS | SM/12197 | New | New service connection at MABARAKPUR Pwss pH NO I under EE/MLMD PHE DTE DIST. Malda.( kushida c c c) |  |  | BILL/03677/2023-2024 | BP-2023-24-660 | 11/03/2024 | 11/03/2024 | W.B.S.E.D.C.LTD | 5.44 | 0 | 0 | 0
10 | MALDAH | Harischandrapur-I | Malda Division | MABARAKPUR PWSS | SM/12197 | New | Formal work order for the work of Implementation of MOBARAKPUR Water Supply Scheme at Harishchandrapur-I Block of Malda district under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000067/2023-2024 | 2035/MD | 19/05/2023 | 01/04/2026 | SUBHAS CHANDRA KESHARI | 501.69 | 0 | 0 | 64
11 | MALDAH | Harischandrapur-I | Malda Mechanical | MABARAKPUR PWSS | SM/12197 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Mabarakpur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/012922) | Assistant Engineer - II | Junior Engineer-05 | ORD/000321/2023-2024 | 2323/MLMD | 26/07/2023 | 14/10/2025 | M/S. KUNDU CONSTRACTION | 28.45 | 0 | 0 | 57
12 | MALDAH | Harischandrapur-I | Malda Division | MABARAKPUR PWSS | SM/12197 | New | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Mabarakpur Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000755/2024-2025 | 73 | 13/01/2025 | 27/02/2025 | SUBHAS CHANDRA KESHARI | 38.17 | 0 | 0 | 0
13 | MALDAH | Harischandrapur-I | Malda Division | MABARAKPUR PWSS | SM/12197 | New | Dedicated/Parallel Pipe Line for better functionality and road restoration and providing balance FHTC of Mobarakpur Water Supply Scheme under Harishchandrapur -I Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000691/2025-2026 | 5920/MD | 26/11/2025 | 25/01/2026 | SUBHAS CHANDRA KESHARI | 28.7 | 0 | 0 | 0
Total | [13 empty] | 699.32 | 8.88 | 1.27