## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Harischandrapur-I | Malda Division | GOCHIYA PWSS , Harischandrapur_I Block in Malda Division. | SM/12267 | New | Material Requisition To Resource Division |  |  | RTOR000030/2022-2023 | 3042/MD | 12/12/2022 | 12/12/2022 | Resource Division | 26.32 | 0 | 0 | 0
2 | MALDAH | Harischandrapur-I | Malda Division | GOCHIYA PWSS , Harischandrapur_I Block in Malda Division. | SM/12267 | New | Material Requisition To Resource Division |  |  | RTOR000023/2023-2024 | 1608/MD | 11/04/2023 | 11/04/2023 | Resource Division | 15.61 | 0 | 0 | 0
3 | MALDAH | Harischandrapur-I | Malda Division | GOCHIYA PWSS , Harischandrapur_I Block in Malda Division. | SM/12267 | New | Sinking of 200mm. (all through) Big dia. Tube Well of 180m Deep at Head Work Site by D.R. Rig Method using P.V.C. pipe including supply of materials at GOCHIYA Water Supply Scheme of Harishchandrapur-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000651/2024-2025 | 6044/MD | 02/12/2024 | 16/01/2025 | A. L. ENGINEERING SOLUTION | 10.84 | 0 | 0 | 0
4 | MALDAH | Harischandrapur-I | Malda Mechanical | GOCHIYA PWSS , Harischandrapur_I Block in Malda Division. | SM/12267 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of GOCHIYA PWSS, Kushida C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. |  |  | BILL/02540/2023-2024 | BP-2023-24-443 | 10/01/2024 | 10/01/2024 | W.B.S.E.D.C.LTD | 3.79 | 0 | 0 | 0
5 | MALDAH | Harischandrapur-I | Malda Mechanical | GOCHIYA PWSS , Harischandrapur_I Block in Malda Division. | SM/12267 | New | New service connection at GOCHIYA Pwss pH NO II Under EE/MLMD PHE DTE DIST. Malda.( kushida c c c) |  |  | BILL/03681/2023-2024 | BP-2023-24-664 | 11/03/2024 | 11/03/2024 | W.B.S.E.D.C.LTD | 9.63 | 0 | 0 | 0
6 | MALDAH | Harischandrapur-I | Malda Division | GOCHIYA PWSS , Harischandrapur_I Block in Malda Division. | SM/12267 | New | Formal work order for the work of Implementation of GOCHIYA Water Supply Scheme at Harishchandrapur-I Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000097/2023-2024 | 2319/MD | 08/06/2023 | 07/06/2024 | M/S PARIMAL DAS | 508.24 | 174.7 | 34.37 | 35
7 | MALDAH | Harischandrapur-I | Malda Division | GOCHIYA PWSS , Harischandrapur_I Block in Malda Division. | SM/12267 | New | Providing Functional Household Tap Connection (FHTC) and Laying of Distribution pipeline in connection with Jal Jeevan Mission (JJM) at Gochiya Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000656/2024-2025 | 1259/MD | 28/03/2025 | 12/05/2025 | M/S PARIMAL DAS | 48.34 | 0 | 0 | 0
Total | [13 empty] | 622.77 | 174.7 | 28.05