## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | Operational Charges of PHED & NGO Managed Laboratories Related to water quality monitoring & surveillance under Jal Jeevan Mission. | SM/12272 | Support-WQMSP | Acceptance cum formal work order for Engagement of Chemist/Bacteriologist and Laboratory Assistant for testing, entry and collection, of New Water Testing Laboratory of BULBULCHANDI Water Supply Scheme under Malda Division, PHE Dte. in the district of Malda. (Period from 01/10/2021 to 30/09/2022). | Mr. Amit Biswas, Assistant Engineer,Mr. Arnab Giri, Assistant Engineer | Junior Engineer,Shreya Das, Junior Engineer | ORD/000386/2021-2022 | 2563/MD | 31/08/2021 | 31/08/2022 | S. N. CONSTRUCTION | 3.7 | 0 | 0 | 0
2 | MALDAH |  | Malda Division | Operational Charges of PHED & NGO Managed Laboratories Related to water quality monitoring & surveillance under Jal Jeevan Mission. | SM/12272 | Support-WQMSP | Acceptance cum formal work order for Engagement of personnel for testing, entry and collection of Water Testing Laboratory of BALUPUR Water Supply Scheme under Malda Division, PHE Dte. in the district of Malda. (Period from 01/11/2021 to 31/07/2022) | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000441/2021-2022 | 3035/MD | 26/10/2021 | 26/07/2022 | HANNAN BUILDERS PVT. LTD. | 4.46 | 0 | 0 | 0
3 | MALDAH |  | Malda Division | Operational Charges of PHED & NGO Managed Laboratories Related to water quality monitoring & surveillance under Jal Jeevan Mission. | SM/12272 | Support-WQMSP | Acceptance cum formal work order for Engagement of personnel for testing, entry and collection of water for Malda District water Testing Laboratory under Malda Division, PHE Dte. in the district of Malda. (Period From 01/08/2021 to 31/02/2022). | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000293/2021-2022 | 2257/MD | 30/07/2021 | 26/01/2022 | SUDEB KARMAKAR | 3.54 | 0 | 0 | 0
4 | MALDAH |  | Malda Division | Operational Charges of PHED & NGO Managed Laboratories Related to water quality monitoring & surveillance under Jal Jeevan Mission. | SM/12272 | Support-WQMSP | Acceptance cum formal work order for Engagement of Chemist/Bacteriologist and Laboratory Assistant for testing, entry and collection, of New Water Testing Laboratory of GAZOLE Water Supply Scheme under Malda Division, PHE Dte. in the district of Malda. (Period from 01/10/2021 to 30/09/2022). | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000385/2021-2022 | 2562/MD | 31/08/2021 | 31/08/2022 | M/S MAHABIR ENTERPRISE | 3.7 | 0 | 0 | 0
5 | MALDAH |  | Malda Division | Operational Charges of PHED & NGO Managed Laboratories Related to water quality monitoring & surveillance under Jal Jeevan Mission. | SM/12272 | Support-WQMSP | Acceptance cum formal work order for Engagement of Chemist, Bacteriologist and Laboratory Assistant including related upkeeping works for Sahapur Sub-District Laboratory (erstwhile PBVM) under Malda Division, PHE Dte. in the district of Malda. (Period from 01/06/2022 to 31/03/2023). | Mr. Amit Biswas, Assistant Engineer |  | ORD/000041/2022-2023 | 1277/MD | 31/05/2022 | 31/03/2023 | M/S MAA TARA ENTERPRISE | 4.66 | 0 | 0 | 0
6 | MALDAH |  | Malda Division | Operational Charges of PHED & NGO Managed Laboratories Related to water quality monitoring & surveillance under Jal Jeevan Mission. | SM/12272 | Support-WQMSP | Acceptance cum Formal Work Order of Supply, Delivery, Fitting and Fixing of Vinyl Glow Sign Boards for 8(eight) no. of Laboratories under Malda Division, PHE Dte. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000078/2023-2024 | 133/RWS | 31/05/2023 | 30/06/2023 | M/S PARIMAL DAS | 0.81 | 0 | 0 | 100
7 | MALDAH |  | Malda Division | Operational Charges of PHED & NGO Managed Laboratories Related to water quality monitoring & surveillance under Jal Jeevan Mission. | SM/12272 | Support-WQMSP | Continuation work order for Engagement of Chemist, Bacteriologist and Laboratory Assistant including related upkeeping works for Manikchak Sub-District Laboratory (erstwhile CDTP) under Malda Division, PHE Dte. in the district of Malda. (Period from 01/04/2023 to 30/06/2023). | Mr. Amit Biswas, Assistant Engineer | Rahul Das Biswas, Junior Engineer | ORD/000807/2022-2023 | 1465/MD | 29/03/2023 | 29/06/2023 | NABODAYA MULTIPURPOSE CO-OPERATIVE SOCIETY LTD. | 1.42 | 0 | 0 | 100
8 | MALDAH |  | Malda Division | Operational Charges of PHED & NGO Managed Laboratories Related to water quality monitoring & surveillance under Jal Jeevan Mission. | SM/12272 | Support-WQMSP | Acceptance cum formal work order for Annual maintenance of Chanchal Sub-District Laboratory under Malda Division, PHE Dte. (Period from 06/01/2023 to 05/01/2024) | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000439/2022-2023 | 195/RWS | 05/01/2023 | 05/01/2024 | NABODAYA MULTIPURPOSE CO-OPERATIVE SOCIETY LTD. | 0.75 | 0 | 0 | 100
9 | MALDAH |  | Malda Division | Operational Charges of PHED & NGO Managed Laboratories Related to water quality monitoring & surveillance under Jal Jeevan Mission. | SM/12272 | Support-WQMSP | Acceptance cum formal work order for Annual maintenance of Manikchak Sub-District Laboratory under Malda Division, PHE Dte. (Period from 06/01/2023 to 05/01/2024) | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000440/2022-2023 | 196/RWS | 05/01/2023 | 05/01/2024 | NABODAYA MULTIPURPOSE CO-OPERATIVE SOCIETY LTD. | 0.75 | 0 | 0 | 100
10 | MALDAH |  | Malda Division | Operational Charges of PHED & NGO Managed Laboratories Related to water quality monitoring & surveillance under Jal Jeevan Mission. | SM/12272 | Support-WQMSP | Acceptance cum formal work order for Annual maintenance of Gazole Sub-District Laboratory under Malda Division, PHE Dte. (Period from 06/01/2023 to 05/01/2024) | Mr. Amit Biswas, Assistant Engineer,Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer ,Shreya Das, Junior Engineer | ORD/000441/2022-2023 | 197/RWS | 05/01/2023 | 05/01/2024 | NABODAYA MULTIPURPOSE CO-OPERATIVE SOCIETY LTD. | 0.75 | 0 | 0 | 100
11 | MALDAH |  | Malda Division | Operational Charges of PHED & NGO Managed Laboratories Related to water quality monitoring & surveillance under Jal Jeevan Mission. | SM/12272 | Support-WQMSP | Acceptance cum formal work order for Annual maintenance of Sahapur Sub-District Laboratory under Malda Division, PHE Dte. (Period from 06/01/2023 to 05/01/2024) | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000442/2022-2023 | 198/RWS | 05/01/2023 | 05/01/2024 | M/S MAA TARA ENTERPRISE | 0.75 | 0 | 0 | 100
12 | MALDAH |  | Malda Division | Operational Charges of PHED & NGO Managed Laboratories Related to water quality monitoring & surveillance under Jal Jeevan Mission. | SM/12272 | Support-WQMSP | Acceptance cum formal work order for Annual maintenance of Balupur WTP Sub-District Laboratory under Malda Division, PHE Dte. (Period from 06/01/2023 to 05/01/2024) | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000443/2022-2023 | 199/RWS | 05/01/2023 | 05/01/2024 | NABODAYA MULTIPURPOSE CO-OPERATIVE SOCIETY LTD. | 0.75 | 0 | 0 | 100
13 | MALDAH |  | Malda Division | Operational Charges of PHED & NGO Managed Laboratories Related to water quality monitoring & surveillance under Jal Jeevan Mission. | SM/12272 | Support-WQMSP | Acceptance cum formal work order for Annual maintenance of Sanskrity-O-Samaj Unnayan Parishad Sub-District Laboratory. (Period from 06/01/2023 to 05/01/2024) | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000444/2022-2023 | 200/RWS | 05/01/2023 | 05/01/2024 | NABODAYA MULTIPURPOSE CO-OPERATIVE SOCIETY LTD. | 0.75 | 0 | 0 | 100
14 | MALDAH |  | Malda Division | Operational Charges of PHED & NGO Managed Laboratories Related to water quality monitoring & surveillance under Jal Jeevan Mission. | SM/12272 | Support-WQMSP | Acceptance cum formal work order for Annual maintenance of Bulbulchandi Sub-District Laboratory under Malda Division, PHE Dte. (Period from 06/01/2023 to 05/01/2024) | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000445/2022-2023 | 201/RWS | 05/01/2023 | 05/01/2024 | NABODAYA MULTIPURPOSE CO-OPERATIVE SOCIETY LTD. | 0.75 | 0 | 0 | 100
15 | MALDAH |  | Malda Division | Operational Charges of PHED & NGO Managed Laboratories Related to water quality monitoring & surveillance under Jal Jeevan Mission. | SM/12272 | Support-WQMSP | Engagement of Chemist, Bacteriologist and Laboratory Assistant including related upkeeping works for Manikchak Sub-District Laboratory (erstwhile CDTP) under Malda Division, PHE Dte. In the district of Malda. (Period from 01/10/2023 to 31/03/2024). | Mr. Amit Biswas, Assistant Engineer,Mr. Prosanta Mandal, Assistant Engineer | Rahul Das Biswas, Junior Engineer | ORD/000551/2023-2024 | 3722/MD | 26/09/2023 | 27/03/2024 | NABODAYA MULTIPURPOSE CO-OPERATIVE SOCIETY LTD. | 2.84 | 0 | 0 | 100
16 | MALDAH |  | Malda Division | Operational Charges of PHED & NGO Managed Laboratories Related to water quality monitoring & surveillance under Jal Jeevan Mission. | SM/12272 | Support-WQMSP | Engagement of Chemist, Bacteriologist, Laboratory Assistant and Sampling Assistant for testing, entry and collection of Chanchal Sub-District Laboratory under Malda Division, PHE Dte. in the district of Malda (Period from 01/10/2023 to 31/03/2024). | Mr. Amit Biswas, Assistant Engineer,Mr. Sumit Kumar Ghosh, Assistant Engineer | Yusuf Sk, Junior Engineer | ORD/000552/2023-2024 | 3723/MD | 26/09/2023 | 27/03/2024 | GOBINDA ENTERPRISE | 3.81 | 0 | 0 | 100
17 | MALDAH |  | Malda Division | Operational Charges of PHED & NGO Managed Laboratories Related to water quality monitoring & surveillance under Jal Jeevan Mission. | SM/12272 | Support-WQMSP | Engagement of personnel for testing, entry, collection of water and Double Beam Atomic Absorption Spectrophotometer (AAS) for Malda District water Testing Laboratory under Malda Division, PHE Dte. in the district of Malda (Period from 01/10/2023 to 31/03/2024). | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000556/2023-2024 | 3727/MD | 26/09/2023 | 27/03/2024 | SUDEB KARMAKAR | 5.18 | 0 | 0 | 100
18 | MALDAH |  | Malda Division | Operational Charges of PHED & NGO Managed Laboratories Related to water quality monitoring & surveillance under Jal Jeevan Mission. | SM/12272 | Support-WQMSP | Continuation work order for maintenance of Chanchal Sub-District Laboratory under Malda Division, PHE Dte. for 6(Six) months.(Period from 06/01/2024 to 30/06/2024) | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000933/2023-2024 | 432/RWS | 29/12/2023 | 29/06/2024 | NABODAYA MULTIPURPOSE CO-OPERATIVE SOCIETY LTD. | 0.37 | 0 | 0 | 100
19 | MALDAH |  | Malda Division | Operational Charges of PHED & NGO Managed Laboratories Related to water quality monitoring & surveillance under Jal Jeevan Mission. | SM/12272 | Support-WQMSP | Continuation work order for Maintenance of Manikchak Sub-District Laboratory under Malda Division, PHE Dte. for 6(Six) months(Period from 06/01/2024 to 30/06/2024) | Mr. Amit Biswas, Assistant Engineer | Rahul Das Biswas, Junior Engineer,Shreya Das, Junior Engineer | ORD/000940/2023-2024 | 433/RWS | 29/12/2023 | 29/06/2024 | NABODAYA MULTIPURPOSE CO-OPERATIVE SOCIETY LTD. | 0.37 | 0 | 0 | 100
20 | MALDAH |  | Malda Division | Operational Charges of PHED & NGO Managed Laboratories Related to water quality monitoring & surveillance under Jal Jeevan Mission. | SM/12272 | Support-WQMSP | Continuation work order for maintenance of Gazole sub-District Laboratory under Malda Division,PHE Dte. for 6(Six) months (Period from 06/01/2024 to 30/06/20204) | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000943/2023-2024 | 434/RWS | 29/12/2023 | 29/06/2024 | NABODAYA MULTIPURPOSE CO-OPERATIVE SOCIETY LTD. | 0.37 | 0 | 0 | 100
21 | MALDAH |  | Malda Division | Operational Charges of PHED & NGO Managed Laboratories Related to water quality monitoring & surveillance under Jal Jeevan Mission. | SM/12272 | Support-WQMSP | Continuation work order for maintenance of Balupur WTP Sub-District Laboratory under Malda Division, PHE Dte. for 06(Six) months( period from 06/01/2024 to 30/06/2024) | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000944/2023-2024 | 435/RWS | 29/12/2023 | 29/06/2024 | NABODAYA MULTIPURPOSE CO-OPERATIVE SOCIETY LTD. | 0.37 | 0 | 0 | 100
22 | MALDAH |  | Malda Division | Operational Charges of PHED & NGO Managed Laboratories Related to water quality monitoring & surveillance under Jal Jeevan Mission. | SM/12272 | Support-WQMSP | Continuation of work order for maintenance of Sanskrity-O-Samaj Unnayan Parishad Sub-District Laboratory under Malda Division, PHE Dte. for 6(Six) months.(Period from 06/01/2024 to 30/06/2024). | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000967/2023-2024 | 436/RWS | 29/12/2023 | 29/06/2024 | NABODAYA MULTIPURPOSE CO-OPERATIVE SOCIETY LTD. | 0.37 | 0 | 0 | 100
23 | MALDAH |  | Malda Division | Operational Charges of PHED & NGO Managed Laboratories Related to water quality monitoring & surveillance under Jal Jeevan Mission. | SM/12272 | Support-WQMSP | Acceptance cum formal work order for Annual Maintenance Contract (AMC) for software upgradation, other software related issues in existing computers, refilling of cartridge of the printers, replacement of battery of UPS and other related peripherals in 8 nos. i.e. District, Sub-District & NGO Laboratories under Malda Division, PHE Dte. in the district of Malda. (Period from 01/04/2023 to 31/03/2024). | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000797/2022-2023 | 1481/MD | 30/03/2023 | 29/03/2024 | DIGITAL CONSULTANTS | 1.19 | 0 | 0 | 100
Total | [13 empty] | 42.44 | 0 | 0