## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Habibpur | Malda Division | KANTHALANPUR PWSS at Habibpur in Malda Division P.H.E.Dte | SM/12304 | New | Material Requisition To Resource Division |  |  | RTOR000043/2023-2024 | 1809/MD | 27/04/2023 |  | Resource Division | 14.46 | 0 | 0 | 0
2 | MALDAH | Habibpur | Malda Mechanical | KANTHALANPUR PWSS at Habibpur in Malda Division P.H.E.Dte | SM/12304 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of KANTHALANPUR, Aiho C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. |  |  | BILL/02491/2023-2024 | BP-2023-24-426 | 04/01/2024 |  | W.B.S.E.D.C.LTD | 7.65 | 0 | 0 | 0
3 | MALDAH | Habibpur | Malda Mechanical | KANTHALANPUR PWSS at Habibpur in Malda Division P.H.E.Dte | SM/12304 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of KANTHALANPUR, Aiho C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. |  |  | BILL/02490/2023-2024 | BP-2023-24-425 | 04/01/2024 |  | W.B.S.E.D.C.LTD | 5.24 | 0 | 0 | 0
4 | MALDAH | Habibpur | Malda Division | KANTHALANPUR PWSS at Habibpur in Malda Division P.H.E.Dte | SM/12304 | New | Formal work order for the work of Implementation of KANTHALANPUR Piped Water Supply Scheme at Habibpur Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Mukaddar Parvage, Junior Engineer | ORD/000035/2023-2024 | 1849/MD | 03/05/2023 | 28/01/2024 | SOVON KUMAR DAS | 322.9 | 173.39 | 53.7 | 60
5 | MALDAH | Habibpur | Malda Mechanical | KANTHALANPUR PWSS at Habibpur in Malda Division P.H.E.Dte | SM/12304 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Kanthalanpur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/013454) | Assistant Engineer - II | Junior Engineer-03 | ORD/000381/2023-2024 | 2389/MLMD | 28/07/2023 | 24/01/2024 | HANNAN BUILDERS PVT. LTD. | 30 | 10.45 | 34.82 | 19
6 | MALDAH | Habibpur | Malda Division | KANTHALANPUR PWSS at Habibpur in Malda Division P.H.E.Dte | SM/12304 | New | Laying of Distribution of UPVC Pipeline of KANTHALANPUR Piped Water Supply Scheme at Habibpur Block of Malda District under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Mukaddar Parvage, Junior Engineer | ORD/000564/2023-2024 | 2328/MD | 08/06/2023 | 07/08/2023 | UTTAM KUMAR GHOSH | 64.73 | 21.4 | 33.07 | 80
7 | MALDAH | Habibpur | Malda Division | KANTHALANPUR PWSS at Habibpur in Malda Division P.H.E.Dte | SM/12304 | New | Construction of Boundary Wall at 2nd Tubewell site of Kanthalanpur Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Mukaddar Parvage, Junior Engineer | ORD/001035/2023-2024 | 1261/MD | 15/03/2024 | 14/04/2024 | SOVON KUMAR DAS | 7.07 | 0 | 0 | 0
8 | MALDAH | Habibpur | Malda Division | KANTHALANPUR PWSS at Habibpur in Malda Division P.H.E.Dte | SM/12304 | New | Construction of Boundary Wall at Head Work site of Kanthalanpur Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Mukaddar Parvage, Junior Engineer | ORD/000155/2024-2025 | 2924/MD | 10/06/2024 | 10/07/2024 | SOVON KUMAR DAS | 35.67 | 0 | 0 | 0
Total | [13 empty] | 487.73 | 205.24 | 42.08