## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Habibpur | Malda Division | KANTHALANPUR PWSS at Habibpur in Malda Division P.H.E.Dte | SM/12304 | New | Material Requisition To Resource Division |  |  | RTOR000043/2023-2024 | 1809/MD | 27/04/2023 | 27/04/2023 | Resource Division | 14.46 | 0 | 0 | 0
2 | MALDAH | Habibpur | Malda Division | KANTHALANPUR PWSS at Habibpur in Malda Division P.H.E.Dte | SM/12304 | New | Laying of Distribution of UPVC Pipeline of KANTHALANPUR Piped Water Supply Scheme at Habibpur Block of Malda District under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Mukaddar Parvage, Junior Engineer | ORD/000564/2023-2024 | 2328/MD | 08/06/2023 | 07/08/2023 | UTTAM KUMAR GHOSH | 64.73 | 42.81 | 66.13 | 80
3 | MALDAH | Habibpur | Malda Division | KANTHALANPUR PWSS at Habibpur in Malda Division P.H.E.Dte | SM/12304 | New | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Kanthalanpur Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000620/2024-2025 | 5790/MD | 21/11/2024 | 05/01/2025 | DHRITIPALI | 60.57 | 0 | 0 | 0
4 | MALDAH | Habibpur | Malda Mechanical | KANTHALANPUR PWSS at Habibpur in Malda Division P.H.E.Dte | SM/12304 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of KANTHALANPUR, Aiho C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. |  |  | BILL/02491/2023-2024 | BP-2023-24-426 | 04/01/2024 | 04/01/2024 | W.B.S.E.D.C.LTD | 7.65 | 0 | 0 | 0
5 | MALDAH | Habibpur | Malda Mechanical | KANTHALANPUR PWSS at Habibpur in Malda Division P.H.E.Dte | SM/12304 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of KANTHALANPUR, Aiho C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. |  |  | BILL/02490/2023-2024 | BP-2023-24-425 | 04/01/2024 | 04/01/2024 | W.B.S.E.D.C.LTD | 5.24 | 0 | 0 | 0
6 | MALDAH | Habibpur | Malda Division | KANTHALANPUR PWSS at Habibpur in Malda Division P.H.E.Dte | SM/12304 | New | Formal work order for the work of Implementation of KANTHALANPUR Piped Water Supply Scheme at Habibpur Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Mukaddar Parvage, Junior Engineer | ORD/000035/2023-2024 | 1849/MD | 03/05/2023 | 31/07/2025 | SOVON KUMAR DAS | 322.9 | 231.44 | 71.68 | 100
7 | MALDAH | Habibpur | Malda Mechanical | KANTHALANPUR PWSS at Habibpur in Malda Division P.H.E.Dte | SM/12304 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Kanthalanpur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/013454) | Assistant Engineer - II | Junior Engineer-03,Junior Engineer-06 | ORD/000381/2023-2024 | 2389/MLMD | 28/07/2023 | 10/07/2026 | HANNAN BUILDERS PVT. LTD. | 30 | 23.48 | 78.26 | 19
8 | MALDAH | Habibpur | Malda Division | KANTHALANPUR PWSS at Habibpur in Malda Division P.H.E.Dte | SM/12304 | New | Erection of Property board and dissemination of Property information through wall painting related to Jal Jeevan Mission works of Oltara, Mianagar, Kadirpur, Bhabuk, Kanthalanpur PWSS under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000954/2024-2025 | 643/MD | 19/02/2025 | 26/02/2025 | DHRITIPALI | 0.88 | 0 | 0 | 0
9 | MALDAH | Habibpur | Malda Division | KANTHALANPUR PWSS at Habibpur in Malda Division P.H.E.Dte | SM/12304 | New | Construction of Boundary Wall at 2nd Tubewell site of Kanthalanpur Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Mukaddar Parvage, Junior Engineer | ORD/001035/2023-2024 | 1261/MD | 15/03/2024 | 02/05/2025 | SOVON KUMAR DAS | 7.07 | 0 | 0 | 100
10 | MALDAH | Habibpur | Malda Division | KANTHALANPUR PWSS at Habibpur in Malda Division P.H.E.Dte | SM/12304 | New | Construction of Boundary Wall at Head Work site of Kanthalanpur Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Mukaddar Parvage, Junior Engineer | ORD/000155/2024-2025 | 2924/MD | 10/06/2024 | 02/05/2025 | SOVON KUMAR DAS | 35.67 | 0 | 0 | 100
Total | [13 empty] | 549.18 | 297.73 | 54.21