## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | Source Augmentation of Rajarampur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12305 | Augmentation | Acceptance cum formal work order for Sinking of ( 250mm. Dia. x 200mm. Dia ) Big dia Tube Well no-3 ( 115 Mtr. deep ) by D.R. Rig method using P.V.C. pipe & Gravel Filter including supply of Materials at RAJARAMPUR Water Supply Scheme of Habibpur Block .under Malda Division, PHE Dte. in the District of Malda. | Mr. Arnab Giri, Assistant Engineer | Ramen Karmakar, Junior Engineer | ORD/000306/2022-2023 | 2301/MD | 28/09/2022 | 28/10/2022 | DUTTA ENTERPRISE | 8.24 | 8.2 | 99.51 | 1
2 | MALDAH |  | Malda Division | Source Augmentation of Rajarampur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12305 | Augmentation | Acceptance cum formal work order for Construction of 5.40 mtr.X 3.6mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at Head Work site of RAJARAMPUR Water Supply Scheme of Habibpur Block. under Malda Division, PHE Dte. in the District of Malda. | Mr. Arnab Giri, Assistant Engineer | Ramen Karmakar, Junior Engineer | ORD/000342/2022-2023 | 3109/MD | 20/12/2022 | 03/02/2023 | M/S SRINJOYEE | 6.68 | 6.49 | 97.02 | 1
3 | MALDAH |  | Malda Mechanical | Source Augmentation of Rajarampur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12305 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at P/H-III site of Rajarampur C.C.C Aiho in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II |  | ORD/001150/2022-2023 | 3004231191 | 21/03/2023 | 28/03/2023 | W.B.S.E.D.C.LTD | 0.71 | 0.71 | 100 | 1
4 | MALDAH |  | Malda Mechanical | Source Augmentation of Rajarampur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12305 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Rajarampur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/012802) | Assistant Engineer - II | Junior Engineer-03 | ORD/000030/2023-2024 | 821/MLMD | 03/05/2023 | 30/10/2023 | SUDIP DEY | 11.22 | 11.05 | 98.51 | 98
5 | MALDAH |  | Malda Division | Source Augmentation of Rajarampur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12305 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000018/2022-2023 | 2406/MD | 17/10/2022 | 17/10/2022 | Resource Division | 5.56 | 0 | 0 | 0
6 | MALDAH |  | Malda Division | Source Augmentation of Rajarampur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12305 | Augmentation | Acceptance cum formal work order for Extension of Pipe line and replacing of damage A.C /upvc pipe line by different dia UPVC pipe for RAJARAMPUR Piped Water Supply Scheme of Habibpur Block in the District of Malda under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000356/2022-2023 | 2505//MD | 03/11/2022 | 18/12/2022 | GOBINDA ENTERPRISE | 43.92 | 43.21 | 98.37 | 100
7 | MALDAH |  | Malda Mechanical | Source Augmentation of Rajarampur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12305 | Augmentation | Hiring of Inspection vehicle (Diesel driven) for official use of AE-II for the office of the Executive Engineer, Malda Mechanical Division, P.H.E. Dte. | Assistant Engineer - II | Junior Engineer-03 | ORD/001074/2023-2024 | 1130/MLMD | 23/06/2023 | 30/06/2023 | SUBRATA SAHA | 0.86 | 0.86 | 100 | 100
8 | MALDAH |  | Malda Division | Source Augmentation of Rajarampur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12305 | Augmentation | Augmentation of Head work site Pump House, PUMP House No.-2 ,Earth filling and 2 Nos. Boundary wall at RAJARAMPUR Water Supply scheme at Habibpur Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000883/2024-2025 | 1122/MD | 21/03/2025 | 25/12/2025 | THREE BROTHERS CONSTRUCTION & CO | 9.43 | 0 | 0 | 0
Total | [13 empty] | 86.63 | 70.51 | 81.39