## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | Source Augmentation of Saiyadpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12311 | Augmentation | Acceptance cum formal work order for Sinking of ( 250mm. Dia. x 200mm. Dia ) Big dia Tube Well ( 135 Mtr. deep ) by D.R. Rig method using P.V.C. pipe & Gravel Filter including supply of Materials at SAIYADPUR Water Supply Scheme of Old Malda Block .under Malda Division, PHE Dte. in the District of Malda. | Mr. Amit Biswas, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000308/2022-2023 | 2303/MD | 28/09/2022 | 28/10/2022 | DUTTA ENTERPRISE | 9 | 8.58 | 95.43 | 1
2 | MALDAH |  | Malda Mechanical | Source Augmentation of Saiyadpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12311 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III & IV of Source Augmentation of Saiyadpur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/012800) | Assistant Engineer - II |  | ORD/001129/2022-2023 | 512/MLMD | 20/03/2023 | 18/07/2023 | DEVI ENTERPRISE... | 21.57 | 18.36 | 85.11 | 0
3 | MALDAH |  | Malda Mechanical | Source Augmentation of Saiyadpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12311 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T/W No.III of Saiyadpur PWSS, Old Malda C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II |  | ORD/000048/2023-2024 | 3004243242 | 27/04/2023 | 26/07/2023 | W.B.S.E.D.C.LTD | 4.41 | 4.41 | 100 | 0
4 | MALDAH |  | Malda Division | Source Augmentation of Saiyadpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12311 | Augmentation | Acceptance cum formal work order for Sinking of ( 250mm. Dia. x 200mm. Dia ) Big dia Tube Well No - 4 ( 132.00 Mtr. deep ) by D.R. Rig method using P.V.C. pipe including supply of Materials at SAIYADPUR Supply Scheme under Malda Division P.H.E Dte in the District of Malda. | Mr. Amit Biswas, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000717/2022-2023 | 1175/MD | 20/03/2023 | 19/04/2023 | A. D. D. ASSOCIATES | 9.15 | 9.13 | 99.84 | 100
5 | MALDAH |  | Malda Division | Source Augmentation of Saiyadpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12311 | Augmentation | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Saiyadpur Piped Water Supply Scheme at Old Malda Block of Malda District under Malda Division, PHE Dte. | Mr. Amit Biswas, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000733/2022-2023 | 1207/MD | 21/03/2023 | 05/05/2023 | M/S. NAYAMEE ENGINEERING & CONSTRUCTIONS | 4.15 | 4.14 | 99.53 | 100
6 | MALDAH |  | Malda Mechanical | Source Augmentation of Saiyadpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12311 | Augmentation | Claim for purchase of fuel for hiring of inspection for different site visit (diesel driven for official) use for Under Mechanical Division, P.H.E. Dte. | Assistant Engineer - I | Junior Engineer-04 | ORD/001394/2022-2023 | 917./MLMD | 12/09/2022 | 12/11/2022 | MAA LAXMI FUEL STATION | 0.51 | 0.51 | 100 | 100
7 | MALDAH |  | Malda Mechanical | Source Augmentation of Saiyadpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12311 | Augmentation | Claim for purchase of fuel for hiring of inspection for different site visit (diesel driven for official) use for AE-I, Under Mechanical Division, P.H.E. Dte. | Assistant Engineer - I | Junior Engineer-04 | ORD/001924/2023-2024 | 1145./MLMD | 26/06/2023 | 26/07/2023 | RAMCHANDRA BASAK | 0.26 | 0.26 | 100 | 100
8 | MALDAH |  | Malda Division | Source Augmentation of Saiyadpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12311 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000023/2022-2023 | 2410/MD | 17/10/2022 | 17/10/2022 | Resource Division | 10.98 | 0 | 0 | 0
9 | MALDAH |  | Malda Mechanical | Source Augmentation of Saiyadpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12311 | Augmentation | NEW SERVICE CONNECTION FOR TE NO. IV OF SAIYEDPUR W S SCHEME |  |  | BILL/01072/2023-2024 | BP-2023-24-95 | 13/07/2023 | 13/07/2023 | W.B.S.E.D.C.LTD | 3.18 | 0 | 0 | 0
10 | MALDAH |  | Malda Division | Source Augmentation of Saiyadpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12311 | Augmentation | Acceptance cum formal work order for Extension of Pipe line and replacing of damage A.C pipe line by different dia UPVC pipe for SAIYADPUR Piped Water Supply Scheme (Dhalsana JL-48, Horkhorka JL-49, & Saiyadpur ) under Old Malda Block in the District of Malda under Malda Division, PHE Dte. | Mr. Amit Biswas, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000363/2022-2023 | 2603/MD | 10/11/2022 | 25/12/2022 | A. K. CONSTRUCTION | 46.61 | 41.9 | 89.9 | 80
11 | MALDAH |  | Malda Division | Source Augmentation of Saiyadpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12311 | Augmentation | Acceptance cum formal work order for Construction of 5.40 mtr.X 3.6mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at Head Work site of SAIYADPUR Water Supply Scheme of Old Malda Block .under Malda Division, PHE Dte. in the District of Malda. | Mr. Amit Biswas, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000344/2022-2023 | 2549/MD | 03/11/2022 | 18/12/2022 | J. M. CONSTRUCTION | 6.69 | 6.52 | 97.46 | 90
12 | MALDAH |  | Malda Division | Source Augmentation of Saiyadpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12311 | Augmentation | Acceptance cum formal work order for Extension of Pipe line and replacing of damage A.C/uPVC pipe line by different dia UPVC pipe for SAIYADPUR Piped Water Supply scheme ( Kutubpur JL-79, Basudevpur JL-80,Ijjatpur ,JL-81 & Minapara JL-92 ) under Old Malda Block in the District of Malda under Malda Division, PHE Dte. | Mr. Amit Biswas, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000013/2023-2024 | 1638/MD | 12/04/2023 | 27/05/2023 | SHREE BISHNU CONSTRUCTION | 56.31 | 52.38 | 93.01 | 90
13 | MALDAH |  | Malda Mechanical | Source Augmentation of Saiyadpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12311 | Augmentation | Installation, Commissioning and trail operation of electro-mechanical components at T/W no-III & IV Source Augmentation of Saiyadpur W/S Scheme in the district of Malda under Malda Mechanical Division, P.H.Engineering Directorate. | Assistant Engineer - II | Junior Engineer-07 | ORD/002022/2023-2024 | 4756/MLMD | 28/12/2023 | 27/01/2024 | PABITRA MANDAL | 3.01 | 1.48 | 49.24 | 49
14 | MALDAH |  | Malda Division | Source Augmentation of Saiyadpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12311 | Augmentation | Construction of Boundary Wall and pathway at 3rd Tube well Site of SAIYADPUR Piped Water Supply Scheme at Old Malda Block under Malda Division, P.H.E.Dte. in the District of Malda. | Mr. Amit Biswas, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000909/2023-2024 | 287/MD | 11/01/2024 | 25/02/2024 | KANAN CONSTRUCTION ENTERPRISE | 6.32 | 0 | 0 | 0
15 | MALDAH |  | Malda Division | Source Augmentation of Saiyadpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12311 | Augmentation | Laying of additional pipeline for retrofitting and Installation of Functional House Connection of Saiyadpur Piped Water Supply Scheme at Old Malda Block under Malda Division PHE. Dte. | Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000643/2024-2025 | 5919/MD | 26/11/2024 | 10/01/2025 | SHREE BISHNU CONSTRUCTION | 88.25 | 0 | 0 | 0
16 | MALDAH |  | Malda Division | Source Augmentation of Saiyadpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12311 | Augmentation | Extension of pipe line and replacing of damage A.C./uPVC pipe line by different dia. UPVC pipe for SAIYEDPUR Piped Water Supply Scheme at Old Malda Block under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Amit Biswas, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000975/2023-2024 | 884/MD | 27/02/2024 | 12/04/2024 | M/S. NAYAMEE ENGINEERING & CONSTRUCTIONS | 12.59 | 12.2 | 96.94 | 100
17 | MALDAH |  | Malda Division | Source Augmentation of Saiyadpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12311 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000183/2023-2024 | 777/MD | 20/02/2024 | 20/02/2024 | Resource Division | 3.08 | 0 | 0 | 0
18 | MALDAH |  | Malda Division | Source Augmentation of Saiyadpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12311 | Augmentation | Augmentation work of Boundary wall, Pump House, Blower Room, RCC Over Head Reservior and Construction Pathway & Approch Road at Head Work Site of SAIYADPUR Water Supply Scheme of Old Malda Block under Malda Division, P.H.E.Dte. in the District of Malda. | Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000004/2025-2026 | 2376/MD | 26/05/2025 | 09/08/2025 | M/S T. K. CONSTRUCTION | 21.59 | 0 | 0 | 0
19 | MALDAH |  | Malda Division | Source Augmentation of Saiyadpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12311 | Augmentation | Augmentation work of Boundary wall, Pump House and Construction of Toilet at 2nd Tube Well Site of SAIYADPUR Water Supply Scheme of Old Malda Block under Malda Division, P.H.E.Dte. in the District of Malda. | Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000005/2025-2026 | 2288/MD | 21/05/2025 | 04/08/2025 | M/S. NAYAMEE ENGINEERING & CONSTRUCTIONS | 7.42 | 0 | 0 | 0
Total | [13 empty] | 315.08 | 159.88 | 50.74