## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Mechanical | Source Augmentation of Altor Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12312 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at P/H No. III of Altor, Gazol C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II |  | ORD/000294/2023-2024 | 3004279849 | 04/05/2023 | 02/08/2023 | W.B.S.E.D.C.LTD | 2.87 | 2.87 | 100 | 100
2 | MALDAH |  | Malda Division | Source Augmentation of Altor Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12312 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000017/2022-2023 | 2408/MD | 17/10/2022 | 17/10/2022 | Resource Division | 5.56 | 0 | 0 | 0
3 | MALDAH |  | Malda Division | Source Augmentation of Altor Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12312 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000019/2022-2023 | 2404/MD | 17/10/2022 | 17/10/2022 | Resource Division | 5.56 | 0 | 0 | 0
4 | MALDAH |  | Malda Division | Source Augmentation of Altor Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12312 | Augmentation | Acceptance cum formal work order for Sinking of (250mm. Dia. x 200mm. Dia ) Tube Well no-3 ( 160 Mtr. deep ) by D.R. Rig method using P.V.C. pipe & Gravel Filter including supply of Materials at ALTOR Water Supply Scheme of Gazole Block .under Malda Division P.H.E Dte in the District of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000337/2022-2023 | 2509/MD | 03/11/2022 | 03/12/2022 | A. D. D. ASSOCIATES | 9.91 | 8.39 | 84.6 | 100
5 | MALDAH |  | Malda Division | Source Augmentation of Altor Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12312 | Augmentation | Acceptance cum formal work order for Construction of 5.40 mtr.X 3.6mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at Head Work site of ALTOR Water Supply Scheme of Gazole Block .under Malda Division P.H.E Dte in the District of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000347/2022-2023 | 2550/MD | 03/11/2022 | 18/12/2022 | SUDEB KARMAKAR | 6.69 | 6.67 | 99.7 | 100
6 | MALDAH |  | Malda Mechanical | Source Augmentation of Altor Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12312 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Altore Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/012799) | Assistant Engineer - II | Junior Engineer-06,Junior Engineer-07 | ORD/000308/2023-2024 | 2310/MLMD | 26/07/2023 | 23/11/2023 | JIBON GHOSH. | 11.54 | 11.22 | 97.24 | 100
7 | MALDAH |  | Malda Division | Source Augmentation of Altor Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12312 | Augmentation | Construction of Boundary Wall at 2nd Tube well site of Altore Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000687/2024-2025 | 6204/MD | 09/12/2024 | 15/10/2025 | MOSTAKIM ANSARI | 7.17 | 0 | 0 | 0
8 | MALDAH |  | Malda Division | Source Augmentation of Altor Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12312 | Augmentation | Augmentation of ensure proper functioning of 450 M³ capacity 20 Mtr. staging height RCC Over Head Reservoir of ALTOR Water Supply scheme under Malda Division, P.H.E.Dte. in the District of Malda. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000889/2024-2025 | 1128/MD | 21/03/2025 | 05/05/2025 | GOBINDA ENTERPRISE | 8.15 | 0 | 0 | 0
9 | MALDAH |  | Malda Division | Source Augmentation of Altor Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12312 | Augmentation | Acceptance cum formal work order for Extension of Pipe line and replacing of damage A.C /upvc pipe line by different dia UPVC pipe for ALTOR Piped Water Supply Scheme of Gazole Block in the District of Malda under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Ramen Karmakar, Junior Engineer,Ziaur Rahaman, Junior Engineer | ORD/000358/2022-2023 | 2507/MD | 03/11/2022 | 21/02/2024 | M/S STAR INDIA CONSTRUTION | 40.04 | 35.34 | 88.28 | 1
Total | [13 empty] | 97.49 | 64.5 | 66.16