## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | Source Augmentation of Purba Binodpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12313 | Augmentation | Acceptance cum formal work order for Sinking of ( 250mm. Dia. x 200mm. Dia ) Big dia Tube Well No-3 ( 135 Mtr. deep ) by D.R. Rig method using P.V.C. pipe & Gravel Filter including supply of Materials at PURBA BINODPUR Water Supply Scheme of Gazole Block .under Malda Division, PHE Dte. in the District of Malda. | Mr. Arnab Giri, Assistant Engineer | Ramen Karmakar, Junior Engineer | ORD/000310/2022-2023 | 2305/MD | 28/09/2022 | 28/10/2022 | DUTTA ENTERPRISE | 9.06 | 9.02 | 99.57 | 1
2 | MALDAH |  | Malda Division | Source Augmentation of Purba Binodpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12313 | Augmentation | Acceptance cum formal work order for Construction of 5.40 mtr.X 3.6mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at Head Work site of PURBA BINODPUR Water Supply Scheme of Gazole Block .under Malda Division, PHE Dte. in the District of Malda. | Mr. Arnab Giri, Assistant Engineer | Ramen Karmakar, Junior Engineer | ORD/000346/2022-2023 | 2801/MD | 24/11/2022 | 08/01/2023 | LABANYA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 6.69 | 6.53 | 97.65 | 0
3 | MALDAH |  | Malda Mechanical | Source Augmentation of Purba Binodpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12313 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T/W No. III of Purba Binodpur PWSS, Pandua C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II |  | ORD/000094/2023-2024 | 3004293401 | 16/05/2023 | 14/08/2023 | W.B.S.E.D.C.LTD | 3.63 | 3.63 | 100 | 0
4 | MALDAH |  | Malda Mechanical | Source Augmentation of Purba Binodpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12313 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Source Augmentation of Purba Binodpur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/012798) | Assistant Engineer - II | Junior Engineer-06,Junior Engineer-07 | ORD/001128/2022-2023 | 511/MLMD | 20/03/2023 | 18/07/2023 | M/S PARIMAL DAS. | 10.57 | 10.36 | 98.08 | 100
5 | MALDAH |  | Malda Division | Source Augmentation of Purba Binodpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12313 | Augmentation | Acceptance cum formal work order for Extension of Pipe line and replacing of damage A.C /upvc pipe line by different dia UPVC pipe for PURBA BINODPUR Piped Water Supply Scheme of Gazole Block in the District of Malda under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Ramen Karmakar, Junior Engineer,Ziaur Rahaman, Junior Engineer | ORD/000357/2022-2023 | 2506/MD | 03/11/2022 | 16/04/2024 | TARUN KUMAR DEY | 41.23 | 38.6 | 93.62 | 1
6 | MALDAH |  | Malda Division | Source Augmentation of Purba Binodpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12313 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Purba Binodpur Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000996/2023-2024 | 1511/MD | 16/03/2024 | 01/11/2024 | SARAJ TRADERS | 26.4 | 0 | 0 | 100
7 | MALDAH |  | Malda Division | Source Augmentation of Purba Binodpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12313 | Augmentation | Augmentation of Head work site Pump House, Pump House No.-2, Earth filling and 2 Nos. Boundary wall at Purba Biniodpur Water Supply scheme at Gazole Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000838/2024-2025 | 1004/MD | 12/03/2025 | 11/05/2025 | SAHA CONSTRUCTION | 8.61 | 0 | 0 | 100
Total | [13 empty] | 106.19 | 68.14 | 64.17