## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | Source Augmentation of Akalpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12314 | Augmentation | Acceptance cum formal work order for Sinking of ( 250mm. Dia. x 200mm. Dia ) Big dia Tube Well No-3 ( 135 Mtr. deep ) by D.R. Rig method using P.V.C. pipe & Gravel Filter including supply of Materials at AKALPUR Water Supply Scheme of Gazole Block .under Malda Division, PHE Dte. in the District of Malda. | Mr. Arnab Giri, Assistant Engineer | Ramen Karmakar, Junior Engineer | ORD/000309/2022-2023 | 2304/MD | 28/09/2022 | 28/10/2022 | DUTTA ENTERPRISE | 9.04 | 9.03 | 99.85 | 1
2 | MALDAH |  | Malda Division | Source Augmentation of Akalpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12314 | Augmentation | Acceptance cum formal work order for Extension of Pipe line and replacing of damage A.C /upvc pipe line by different dia UPVC pipe for AKALPUR Piped Water Supply Scheme of Gazole Block in the District of Malda under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Ramen Karmakar, Junior Engineer | ORD/000359/2022-2023 | 2508/MD | 03/11/2022 | 18/12/2022 | M/S. TEWARI CONSTRUCTION | 28.05 | 23.11 | 82.41 | 1
3 | MALDAH |  | Malda Mechanical | Source Augmentation of Akalpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12314 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T/W No. III of Akalpur, Pandua C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II |  | ORD/000095/2023-2024 | 3004293392 | 16/05/2023 | 14/08/2023 | W.B.S.E.D.C.LTD | 5.14 | 5.14 | 100 | 0
4 | MALDAH |  | Malda Division | Source Augmentation of Akalpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12314 | Augmentation | Acceptance cum formal work order for Construction of 5.40 mtr.X 3.6mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at Head Work site of AKALPUR Water Supply Scheme of Gazole Block. under Malda Division, PHE Dte. in the District of Malda. | Mr. Arnab Giri, Assistant Engineer | Ramen Karmakar, Junior Engineer | ORD/000345/2022-2023 | 3113/MD | 20/12/2022 | 03/02/2023 | THREE BROTHERS CONSTRUCTION | 6.69 | 6.67 | 99.71 | 0
5 | MALDAH |  | Malda Division | Source Augmentation of Akalpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12314 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000016/2022-2023 | 2411/MD | 17/10/2022 |  | Resource Division | 5.56 | 0 | 0 | 0
6 | MALDAH |  | Malda Mechanical | Source Augmentation of Akalpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12314 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Source Augmentation Akalpur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/012797) | Assistant Engineer - II | Junior Engineer-07 | ORD/001124/2022-2023 | 507/MLMD | 20/03/2023 | 18/07/2023 | SUBHAS CHANDRA KESHORI | 11.42 | 10.63 | 93.12 | 100
7 | MALDAH |  | Malda Division | Source Augmentation of Akalpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12314 | Augmentation | Construction of Boundary Wall at Akalpur Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000209/2024-2025 | 3030/MD | 13/06/2024 | 13/07/2024 | BENGAL ENGINEERING COMPANY | 15.69 | 0 | 0 | 0
8 | MALDAH |  | Malda Division | Source Augmentation of Akalpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12314 | Augmentation | Placement of fund against the work for road restoration for laying pipe line for Eklakhi to Rashikpur road from 2.400 KM to 7.900 Km under AKALPUR PWSS under Malda Division,PHE Dte. |  |  | BILL/00515/2024-2025 | null | 04/09/2024 |  | EXECUTIVE ENGINEER, PUBLIC WORKS (ROADS) DIRECTORATE. | 9.95 | 0 | 0 | null
Total | [13 empty] | 91.54 | 54.58 | 59.63