## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | Source Augmentation of Pannapur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12315 | Augmentation | Acceptance cum formal work order for Sinking of (200mm. Dia. x 150mm. Dia) Tube Well no-3 ( 70 Mtr. deep ) by D.R. Rig method using P.V.C. pipe & Gravel Filter including supply of Materials at PANNAPUR Water Supply Scheme of Habibpur Block under Malda Division, PHE Dte. in the District of Malda. | Mr. Arnab Giri, Assistant Engineer | Ramen Karmakar, Junior Engineer | ORD/000304/2022-2023 | 2299/MD | 28/09/2022 | 28/10/2022 | MECHANO TRADING CO. | 5.25 | 0 | 0 | 0
2 | MALDAH |  | Malda Division | Source Augmentation of Pannapur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12315 | Augmentation | Acceptance cum formal work order for Construction of 5.40 mtr.X 3.6mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at Head Work site of PANNAPUR Water Supply Scheme of Habibpur Block under Malda Division, PHE Dte. in the District of Malda. | Mr. Arnab Giri, Assistant Engineer | Ramen Karmakar, Junior Engineer | ORD/000340/2022-2023 | 3112/MD | 20/12/2022 | 03/02/2023 | HIRAK ROY CHOUDHURY | 6.69 | 0 | 0 | 0
3 | MALDAH |  | Central Drilling | Source Augmentation of Pannapur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12315 | Augmentation | Resistivity survey for Sankail PWSS, Basara PWSS and Pannapur PWSS at Habibipur & Bamongola block under Malda district, CMSD-II (D), CDD, PHE Dte. |  |  | ORD/000012/2023-2024 | 135/CMSD-II(D) | 24/05/2023 | 08/06/2023 | S B S ENTERPRISE | 0.82 | 0 | 0 | 100
4 | MALDAH |  | Malda Mechanical | Source Augmentation of Pannapur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12315 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Pannapur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/012801) | Assistant Engineer - II | Junior Engineer-03 | ORD/000385/2023-2024 | 2393/MLMD | 28/07/2023 | 25/11/2023 | SUBRATA KUMAR DAS. | 10.44 | 4.5 | 43.15 | 0
5 | MALDAH |  | Malda Division | Source Augmentation of Pannapur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12315 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000020/2022-2023 | 2405/MD | 17/10/2022 |  | Resource Division | 5.56 | 0 | 0 | 0
6 | MALDAH |  | Malda Mechanical | Source Augmentation of Pannapur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12315 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T/W No. III of Pannapur, Aiho C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. |  |  | BILL/02486/2023-2024 | BP-2023-24-421 | 04/01/2024 |  | W.B.S.E.D.C.LTD | 8.39 | 0 | 0 | 0
7 | MALDAH |  | Malda Division | Source Augmentation of Pannapur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12315 | Augmentation | Sinking of ( 250 mm Dia. X 200 mm Dia.) Tubewell No.-3 (250 M deep) by D.R Rig. Method using P.V.C. pipe & Gravel Filter including Supply of materials at PANNAPUR Water Supply Scheme of Habibpur Block under Malda Division, P.H.E Dte in the District of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000976/2023-2024 | 885/MD | 27/02/2024 | 12/04/2024 | A. L. ENGINEERING SOLUTION | 14.82 | 0 | 0 | 0
8 | MALDAH |  | Malda Division | Source Augmentation of Pannapur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12315 | Augmentation | Acceptance cum formal work order for Extension of Pipe line and Replacing of damage A.C pipe lineby different dia UPVC pipe for PANNAPUR Piped Water Supply Scheme ( Nimnail, Jahanabad) of Habibpur Block in the District of Malda under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000364/2022-2023 | 2605/MD | 10/11/2022 | 25/12/2022 | MANIK CHANDRA SAHA | 69.14 | 66.84 | 96.68 | 88
Total | [13 empty] | 121.1 | 71.35 | 58.91