## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | Source Augmentation of Mianagar Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12316 | Augmentation | Acceptance cum formal work order for Sinking of (250mm. Dia. x 200mm. Dia) Tube Well no-3 (100 Mtr. deep )by D.R. Rig method using P.V.C. pipe & Gravel Filter including supply of Materials at MIANAGAR Water Supply Scheme of Habibpur Block under Malda Division, PHE Dte. in the District of Malda. | Mr. Arnab Giri, Assistant Engineer | Ramen Karmakar, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000305/2022-2023 | 2300/MD | 28/09/2022 | 28/10/2022 | MECHANO TRADING CO. | 7.59 | 0 | 0 | 100
2 | MALDAH |  | Malda Mechanical | Source Augmentation of Mianagar Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12316 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T/W No. of Mianagar, Aiho C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II |  | ORD/000462/2023-2024 | 3004369303 | 28/07/2023 | 26/10/2023 | W.B.S.E.D.C.LTD | 4.64 | 0 | 0 | 100
3 | MALDAH |  | Malda Division | Source Augmentation of Mianagar Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12316 | Augmentation | Construction of Boundary Wall at Mianagar Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/001027/2023-2024 | 1253/MD | 15/03/2024 | 14/04/2024 | CHARU CONSTRUCTION | 9.61 | 0 | 0 | 0
4 | MALDAH |  | Malda Division | Source Augmentation of Mianagar Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12316 | Augmentation | Acceptance cum formal work order for Extension of Pipe line and replacing of damage A.C /upvc pipe line by different dia UPVC pipe for MIANAGAR Piped Water Supply Scheme of Habibpur Block in the District of Malda under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000355/2022-2023 | 2504/MD | 03/11/2022 | 18/12/2022 | DEBAPRIYA SAHA | 76.83 | 0 | 0 | 100
5 | MALDAH |  | Malda Division | Source Augmentation of Mianagar Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12316 | Augmentation | Acceptance cum formal work order for Construction of 5.40 mtr.X 3.6mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at Head Work site of MIANAGAR Water Supply Scheme of Habibpur Block under Malda Division, PHE Dte. in the District of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000341/2022-2023 | 2548/MD | 03/11/2022 | 18/12/2022 | ANJIMA CONSTRUCTION CO. | 6.69 | 0 | 0 | 100
6 | MALDAH |  | Malda Mechanical | Source Augmentation of Mianagar Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12316 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Mianagar Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/014342) | Assistant Engineer - II | Junior Engineer-03 | ORD/000192/2023-2024 | 2144/MLMD | 07/07/2023 | 04/11/2023 | A.S. ENGINEERING | 10.52 | 0 | 0 | 100
7 | MALDAH |  | Malda Mechanical | Source Augmentation of Mianagar Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12316 | Augmentation | Quotation Payment of MIYANAGAR Under AIHO CCC Under the district of Malda. |  |  | BILL/00204/2024-2025 | BP-2024-25-63 | 09/04/2024 | 09/04/2024 | W.B.S.E.D.C.LTD | 3.17 | 0 | 0 | 0
8 | MALDAH |  | Malda Division | Source Augmentation of Mianagar Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12316 | Augmentation | Augmentation of Head work site Pump House,PUMP House No.-2 ,Earth filling and 2 Nos. Boundary wall at MIANAGAR Water Supply scheme at Habibpur Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000880/2024-2025 | 1119/MD | 21/03/2025 | 05/05/2025 | CHARU CONSTRUCTION | 9.63 | 0 | 0 | 0
Total | [13 empty] | 128.68 | 0 | 0