## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Mechanical | Source Augmentation of Kutub Sahar Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12317 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of Kutubsahar PWSS, Pandua C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II |  | ORD/000860/2023-2024 | 3004402679 | 29/08/2023 | 27/11/2023 | W.B.S.E.D.C.LTD | 3.54 | 3.54 | 100 | 100
2 | MALDAH |  | Malda Mechanical | Source Augmentation of Kutub Sahar Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12317 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T/W No. V of Kutub Sahar , Pandua C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II | Junior Engineer-07 | ORD/001890/2023-2024 | 3004496749 | 28/11/2023 | 26/02/2024 | W.B.S.E.D.C.LTD | 5.28 | 5.28 | 100 | 100
3 | MALDAH |  | Malda Division | Source Augmentation of Kutub Sahar Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12317 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000022/2022-2023 | 2409/MD | 17/10/2022 | 17/10/2022 | Resource Division | 5.56 | 0 | 0 | 0
4 | MALDAH |  | Malda Division | Source Augmentation of Kutub Sahar Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12317 | Augmentation | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 35 m³/hr. capacity Pressure type IRON ELIMINATION Plant with Construction of Blower room & backwash water disposal at 5th Tube Well Site of Kutub Sahar Water Supply Scheme of Gazole Block under Malda Division P.H.E Dte in the District of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000720/2024-2025 | 6411/MD | 19/12/2024 | 02/02/2025 | ZEOLITE FRESH INDIA | 17.27 | 0 | 0 | 0
5 | MALDAH |  | Malda Division | Source Augmentation of Kutub Sahar Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12317 | Augmentation | Acceptance cum formal work order for Extension of Pipe line and replacing of damage A.C pipe line (damage due to widening of road) by different dia UPVC pipe for KUTUB SAHAR Piped Water Supply Scheme of Gazole Block in the District of Malda under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000361/2022-2023 | 2604/MD | 10/11/2022 | 30/09/2024 | BEE GEE CONSTRUCTION | 55.12 | 45.37 | 82.31 | 65
6 | MALDAH |  | Malda Division | Source Augmentation of Kutub Sahar Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12317 | Augmentation | Acceptance cum formal work order for Sinking of (250mm. Dia. x 200mm. Dia ) Tube Well no-4 & 5 ( 160 Mtr. deep ) by D.R. Rig method using P.V.C. pipe & Gravel Filter including supply of Materials at KUTUB SAHAR Water Supply Scheme of Gazole Block. under Malda Division P.H.E Dte in the District of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000338/2022-2023 | 2510/MD | 03/11/2022 | 03/12/2022 | A. D. D. ASSOCIATES | 10.01 | 8.57 | 85.63 | 100
7 | MALDAH |  | Malda Division | Source Augmentation of Kutub Sahar Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12317 | Augmentation | Acceptance cum formal work order for Construction of 5.40 mtr.X 3.6mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at Head Work site of KUTUB SAHAR Water Supply Scheme of Gazole Block .under Malda Division P.H.E Dte in the District of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000348/2022-2023 | 2802/MD | 24/11/2022 | 08/01/2023 | MARSS INTERNATIONAL | 6.69 | 6.69 | 99.95 | 100
8 | MALDAH |  | Malda Mechanical | Source Augmentation of Kutub Sahar Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12317 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. IV & V of Source Augmentation Kutub Sahar Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/014339) | Assistant Engineer - II | Junior Engineer-07 | ORD/000506/2023-2024 | 2577/MLMD | 04/08/2023 | 02/12/2023 | MAA BHABOTARINE ENTERPRISE. | 23.05 | 22.7 | 98.48 | 100
9 | MALDAH |  | Malda Division | Source Augmentation of Kutub Sahar Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12317 | Augmentation | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at Tube Well No.-5 site in connection with Source Augmentation of KUTUB SAHAR Piped Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000366/2023-2024 | 3055/MD | 09/08/2023 | 23/09/2023 | A. L. ENGINEERING SOLUTION | 4.15 | 3.94 | 94.85 | 100
10 | MALDAH |  | Malda Division | Source Augmentation of Kutub Sahar Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12317 | Augmentation | Sinking of (250mm. Dia. x 200 mm. dia.) Big dia. Tube Well No. - 5 (160 Mtr. Deep) by D.R. Rig method using P.V.C. pipe and Gravel Filter including supply of Materials at KUTUB SAHAR Water Supply Scheme of Gazole Block of Malda District under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000445/2023-2024 | 3352/MD | 29/08/2023 | 28/09/2023 | A. L. ENGINEERING SOLUTION | 11.88 | 11.63 | 97.83 | 100
11 | MALDAH |  | Malda Division | Source Augmentation of Kutub Sahar Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12317 | Augmentation | Construction of Boundary Wall of Tubewell site at Misipur Mouza of Kutubsahar Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/001024/2023-2024 | 1250/MD | 15/03/2024 | 01/04/2025 | SATELLITE CONSTRUCTION | 9.6 | 0 | 0 | 100
12 | MALDAH |  | Malda Division | Source Augmentation of Kutub Sahar Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12317 | Augmentation | Construction of Boundary Wall of Tubewell site at Khord Babupur Mouza of Kutub Sahar Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/001006/2023-2024 | 1193/MD | 14/03/2024 | 01/01/2025 | AHONA ENTERPRISE | 10.71 | 0 | 0 | 100
13 | MALDAH |  | Malda Division | Source Augmentation of Kutub Sahar Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12317 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000027/2025-2026 | 2828/MD | 11/06/2025 | 11/06/2025 | Resource Division | 7.85 | 0 | 0 | 0
14 | MALDAH |  | Malda Division | Source Augmentation of Kutub Sahar Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12317 | Augmentation | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 35m³/hr. capacity Pressure type IRON ELIMINATION Plant with Construction of Blower room & backwash water disposal at Tubewell no. 4 site of Kutubshar Water Supply Scheme of Gazole Block under Malda Division P.H.E Dte in the District of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/001005/2023-2024 | 1183/MD | 14/03/2024 | 10/09/2024 | M/S JHA CONSTRUCTION | 17.28 | 0 | 0 | 0
15 | MALDAH |  | Malda Division | Source Augmentation of Kutub Sahar Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12317 | Augmentation | Augmentation of Head work site Pump House, Pump House No.-2, Pump House No.-3, Earth filling and 3 Nos. Boundary wall at Kutub Sahar Water Supply scheme at Gazole Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000836/2024-2025 | 1072/MD | 19/03/2025 | 18/05/2025 | M. S. AGENCY | 12.92 | 0 | 0 | 100
Total | [13 empty] | 200.92 | 107.71 | 53.61