## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Central Drilling | Source Augmentation of Sankail Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12323 | Augmentation | Resistivity survey for Sankail PWSS, Basara PWSS and Pannapur PWSS at Habibipur & Bamongola block under Malda district, CMSD-II (D), CDD, PHE Dte. |  |  | ORD/000012/2023-2024 | 135/CMSD-II(D) | 24/05/2023 | 08/06/2023 | S B S ENTERPRISE | 0.82 | 0 | 0 | 100
2 | MALDAH |  | Malda Mechanical | Source Augmentation of Sankail Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12323 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Sankail Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/014344) | Assistant Engineer - II | Junior Engineer-03,Junior Engineer-06 | ORD/000387/2023-2024 | 2395/MLMD | 28/07/2023 | 03/08/2025 | SUDIP DEY | 11.1 | 0 | 0 | 30
3 | MALDAH |  | Malda Division | Source Augmentation of Sankail Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12323 | Augmentation | Construction of Boundary Wall of Sankail Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000485/2024-2025 | 4998/MD | 27/09/2024 | 11/11/2024 | BALAJI ENGINEERS CO OPERATIVE SOCIETY LT | 10.15 | 0 | 0 | 0
4 | MALDAH |  | Malda Division | Source Augmentation of Sankail Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12323 | Augmentation | Sinking of ( 250 mm Dia. X 200 mm Dia.) Tubewell No.-3 (130 M deep) by D.R Rig. Method using P.V.C. pipe & Gravel Filter including Supply of materials at SANKAIL Water Supply Scheme of Habibpur Block under Malda Division, P.H.E Dte in the District of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000920/2023-2024 | 381/MD | 17/01/2024 | 02/03/2024 | A. L. ENGINEERING SOLUTION | 11.77 | 0 | 0 | 100
5 | MALDAH |  | Malda Division | Source Augmentation of Sankail Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12323 | Augmentation | Acceptance cum formal work order for Extension of Pipe line and replacing of damage A.C /upvc pipe line by different dia UPVC pipe for SANKAIL Piped Water Supply Scheme of Habibpur Block in the District of Malda under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Ramen Karmakar, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer,Ziaur Rahaman, Junior Engineer | ORD/000365/2022-2023 | 2606/MD | 10/11/2022 | 01/11/2025 | M/S KUNDU CONSTRUCTION | 71.98 | 0 | 0 | 0
6 | MALDAH |  | Malda Division | Source Augmentation of Sankail Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12323 | Augmentation | Replacement of (200 mm Dia. All through) Tubewell No:-1 (130 m deep) at Headwork Site by D.R Rig Method using P.V.C. pipe & Filter including Supply of materials at SANKAIL water supply scheme of Habibpur Block under Malda Division, P.H.E Dte in the District of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000785/2024-2025 | 350/MD | 30/01/2025 | 01/03/2025 | A. L. ENGINEERING SOLUTION | 9.06 | 0 | 0 | 0
7 | MALDAH |  | Malda Division | Source Augmentation of Sankail Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12323 | Augmentation | Acceptance cum formal work order for Construction of 5.40 mtr.X 3.6mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at Head Work site of SANKAIL Water Supply Scheme of Habibpur Block. under Malda Division, PHE Dte. in the District of Malda. | Mr. Arnab Giri, Assistant Engineer | Ramen Karmakar, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer,Ziaur Rahaman, Junior Engineer | ORD/000343/2022-2023 | 2800/MD | 24/11/2022 | 03/10/2024 | M/S N. N. ENTERPRISE | 6.68 | 0 | 0 | 100
Total | [13 empty] | 121.56 | 0 | 0