## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Maldah (Old) | Malda Division | Sanjail PWSS in Old Malda Block in District Malda | SM/12337 | New | Material Requisition To Resource Division |  |  | RTOR000025/2022-2023 | 2752/MD | 22/11/2022 | 22/11/2022 | Resource Division | 17.38 | 0 | 0 | 0
2 | MALDAH | Maldah (Old) | Malda Division | Sanjail PWSS in Old Malda Block in District Malda | SM/12337 | New | Acceptance cum formal work order for Bamboo Pile Walling and Horizontal Road Crossing for piped water supply scheme of SANJAIL Piped Water Supply Scheme at Old Malda Dev. Block under Malda Division P.H.E Dte in the District of Malda. | Mr. Arnab Giri, Assistant Engineer | Biswajit Gosh, Junior Engineer,Mukaddar Parvage, Junior Engineer | ORD/000789/2022-2023 | 1447/MD | 29/03/2023 | 28/04/2023 | M/S PARIMAL DAS | 3.44 | 3.44 | 100 | 0
3 | MALDAH | Maldah (Old) | Malda Mechanical | Sanjail PWSS in Old Malda Block in District Malda | SM/12337 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of Sanjail PWSS , Old Malda C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II |  | ORD/000051/2023-2024 | 3004243252 | 27/04/2023 | 26/07/2023 | W.B.S.E.D.C.LTD | 3.12 | 3.12 | 100 | 0
4 | MALDAH | Maldah (Old) | Malda Division | Sanjail PWSS in Old Malda Block in District Malda | SM/12337 | New | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150mm. dia., 140 Mtr. deep Big dia Tube Well at Head Work Site by D.R. Rig method using PVC pipe & Gravel Filter including supply of Materials at Sanjail Water Supply Scheme of Old Malda Dev. Block under Malda Division, PHE Dte. in the District of Malda. | Mr. Arnab Giri, Assistant Engineer | Biswajit Gosh, Junior Engineer,Mukaddar Parvage, Junior Engineer | ORD/000291/2022-2023 | 2237/MD | 16/09/2022 | 01/10/2022 | M/S DEBASISH GHOSH | 8.81 | 8.44 | 95.84 | 100
5 | MALDAH | Maldah (Old) | Malda Division | Sanjail PWSS in Old Malda Block in District Malda | SM/12337 | New | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. dia. and 140 Mtr. Deep Big dia Tube well (1 Nos.) at SANJAIL Water Supply Scheme under Old Malda Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Biswajit Gosh, Junior Engineer,Mukaddar Parvage, Junior Engineer | ORD/000019/2023-2024 | 1676/MD | 18/04/2023 | 18/05/2023 | A. L. ENGINEERING SOLUTION | 9.83 | 9.83 | 99.91 | 100
6 | MALDAH | Maldah (Old) | Malda Mechanical | Sanjail PWSS in Old Malda Block in District Malda | SM/12337 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. II of Sanjail Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. | Assistant Engineer - II | Junior Engineer-07 | ORD/002485/2023-2024 | 811/MLMD | 15/02/2024 | 13/08/2024 | UTTAM KUMAR GHOSH | 10.74 | 9.01 | 83.9 | 83
7 | MALDAH | Maldah (Old) | Malda Division | Sanjail PWSS in Old Malda Block in District Malda | SM/12337 | New | Laying of Rising Main including Specials and Valves for Sanjail Piped Water Supply Scheme at Old Malda Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Mukaddar Parvage, Junior Engineer | ORD/000957/2023-2024 | 705/MD | 09/02/2024 | 25/03/2024 | SADHANA CONSTRUCTION | 5.8 | 0 | 0 | 65
8 | MALDAH | Maldah (Old) | Malda Division | Sanjail PWSS in Old Malda Block in District Malda | SM/12337 | New | Acceptance cum formal work order for Construction of 5.40 mtr.X 3.6mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at Head Work site of SANJAIL & its adjoining mouza Water Scheme under Malda Division,PHE Dte. In the District of Malda. | Mr. Arnab Giri, Assistant Engineer | Mukaddar Parvage, Junior Engineer | ORD/000290/2022-2023 | 2236/MD | 16/09/2022 | 31/10/2022 | SARIF BUILDERS | 6.14 | 6.12 | 99.7 | 98
9 | MALDAH | Maldah (Old) | Malda Division | Sanjail PWSS in Old Malda Block in District Malda | SM/12337 | New | Acceptance cum formal work order for Construction of 100 M³ Capacity 20 mtr. staging height RCC Elevated service reservoir as per Departmental Design & drawing ( Ref FRG No-PC/-I/OHR/3/2012) including pipe connection and cost of pipes, specials delivery inlet, washout & overflow pipe etc, all complete with Geotechnical Investigation for SANJAIL Piped Water Supply Scheme at Old Malda Dev. Block under Malda Division P.H.E Dte in the District of Malda. | Mr. Arnab Giri, Assistant Engineer | Biswajit Gosh, Junior Engineer,Mukaddar Parvage, Junior Engineer | ORD/000436/2022-2023 | 44/MD | 16/01/2023 | 15/07/2023 | M/S PARIMAL DAS | 55.12 | 51.84 | 94.06 | 99
10 | MALDAH | Maldah (Old) | Malda Division | Sanjail PWSS in Old Malda Block in District Malda | SM/12337 | New | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of SANJAIL Water Supply Scheme at Old Malda Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Mukaddar Parvage, Junior Engineer | ORD/000923/2023-2024 | 455/MD | 19/01/2024 | 04/03/2024 | M/S SHREE CONSORTIUM | 20.24 | 16.75 | 82.74 | 99
11 | MALDAH | Maldah (Old) | Malda Division | Sanjail PWSS in Old Malda Block in District Malda | SM/12337 | New | Construction of Boundary Wall at Head Work site of Sanjail Water Supply Scheme under Old Malda Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Mukaddar Parvage, Junior Engineer | ORD/000886/2023-2024 | 270/MD | 11/01/2024 | 25/02/2024 | M/S BHARATI CONSTRUCTION | 18.49 | 17.97 | 97.18 | 95
12 | MALDAH | Maldah (Old) | Malda Mechanical | Sanjail PWSS in Old Malda Block in District Malda | SM/12337 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II and making compound lighting arrangement at T/W no. I of Sanjail Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/011706) | Assistant Engineer - II | Junior Engineer-07 | ORD/000025/2023-2024 | 778/ MLMD | 27/04/2023 | 25/08/2023 | DEVI ENTERPRISE... | 25.41 | 9.01 | 35.45 | 0
13 | MALDAH | Maldah (Old) | Malda Mechanical | Sanjail PWSS in Old Malda Block in District Malda | SM/12337 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- II of Sanjail, Old Malda CCC in the dist of Malda, Under Malda Mechanical Division PHE Dte. |  |  | BILL/03566/2023-2024 | BP-2023-24-592 | 22/02/2024 | 22/02/2024 | W.B.S.E.D.C.LTD | 4.69 | 0 | 0 | 0
14 | MALDAH | Maldah (Old) | Malda Division | Sanjail PWSS in Old Malda Block in District Malda | SM/12337 | New | Providing balance Functional Household Tap Connection (FHTC) and Construction of Pump House in 2nd Tubewell site in connection with Jal Jeevan Mission (JJM) at Sanjail Water Supply Scheme under Old Malda Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000174/2025-2026 | 2890/MD | 17/06/2025 | 16/08/2025 | MADHUMITA ENTERPRISE | 19.36 | 0 | 0 | 0
15 | MALDAH | Maldah (Old) | Malda Division | Sanjail PWSS in Old Malda Block in District Malda | SM/12337 | New | Formal work order for the work of Laying of Distribution pipe line SANJAIL its adjoining mouzas Pipe Water Supply Scheme at Old Malda Block in the District of Malda under Malda Division P.H.E. Dte. | Mr. Arnab Giri, Assistant Engineer | Biswajit Gosh, Junior Engineer,Mukaddar Parvage, Junior Engineer | ORD/000302/2022-2023 | 2170/MD | 21/09/2022 | 01/04/2024 | M/S PARIMAL DAS | 124.75 | 123.89 | 99.31 | 100
Total | [13 empty] | 333.3 | 259.4 | 77.83