## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Chanchal-I | Malda Division | Daudpur Piped water supply scheme in Chanchal-I Block, Dist-Malda | SM/12338 | New | Acceptance cum formal work order for Construction of 5.40 mtr.X 3.6mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at Head Work site of DAUDPUR & its adjoining mouza Water Scheme under Malda Division,PHE Dte. In the District of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Rajashree Banarjee, Junior Engineer | ORD/000288/2022-2023 | 2234/MD | 16/09/2022 | 31/10/2022 | M/S. TEWARI CONSTRUCTION | 6.19 | 0 | 0 | 0
2 | MALDAH | Chanchal-I | Malda Division | Daudpur Piped water supply scheme in Chanchal-I Block, Dist-Malda | SM/12338 | New | Material Requisition To Resource Division |  |  | RTOR000026/2022-2023 | 2756/MD | 22/11/2022 | 22/11/2022 | Resource Division | 34.78 | 0 | 0 | 0
3 | MALDAH | Chanchal-I | Malda Division | Daudpur Piped water supply scheme in Chanchal-I Block, Dist-Malda | SM/12338 | New | Acceptance cum formal work order for Sinking of 01 (One) Nos. 250mm. Dia. x 150mm. Big dia. Tube Well 160 Mtr. deep by Direct Rotary method using UPVC pipe & Strainer at Daudpur Piped Water Supply Scheme under Malda Division, P.H.E. Dte. in the District of Malda . | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer,Rajashree Banarjee, Junior Engineer | ORD/000289/2022-2023 | 2235/MD | 16/09/2022 | 01/10/2022 | SNEHASISH GHOSH | 8.09 | 0 | 0 | 100
4 | MALDAH | Chanchal-I | Malda Mechanical | Daudpur Piped water supply scheme in Chanchal-I Block, Dist-Malda | SM/12338 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Daudpur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/011680) | Assistant Engineer - II | Junior Engineer-05 | ORD/001796/2023-2024 | 3683/MLMD | 29/11/2023 | 28/01/2026 | MUKHERJEE ART CENTRE | 29.89 | 0 | 0 | 65
5 | MALDAH | Chanchal-I | Malda Division | Daudpur Piped water supply scheme in Chanchal-I Block, Dist-Malda | SM/12338 | New | Sinking of 250mm. Dia. x 150 mm. Big dia. Tube Well of 160m Deep at Daudpur PWSS under Chanchal-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000303/2024-2025 | 4741/MD | 11/09/2024 | 26/10/2024 | A. L. ENGINEERING SOLUTION | 10.44 | 0 | 0 | 0
6 | MALDAH | Chanchal-I | Malda Division | Daudpur Piped water supply scheme in Chanchal-I Block, Dist-Malda | SM/12338 | New | Sinking of 200 mm (all through) Big dia. Tube Well of 160 m Deep by D.R Rig. Method using P.V.C. pipe & Filter including Supply of materials at head work site under DAUDPUR Water Supply Scheme of Chanchal-I Block under Malda Division, P.H.E Dte in the District of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000467/2024-2025 | 4822/MD | 13/09/2024 | 13/10/2024 | SAUDAGAR INDIA | 10.21 | 0 | 0 | 0
7 | MALDAH | Chanchal-I | Malda Division | Daudpur Piped water supply scheme in Chanchal-I Block, Dist-Malda | SM/12338 | New | Material Requisition To Resource Division |  |  | RTOR000129/2023-2024 | 99/MD | 05/01/2024 | 05/01/2024 | Resource Division | 4.93 | 0 | 0 | 0
8 | MALDAH | Chanchal-I | Malda Mechanical | Daudpur Piped water supply scheme in Chanchal-I Block, Dist-Malda | SM/12338 | New | New service connection at daudpur w/s sch. T/W no I Under EE/ MLMD PHE DTE District - malda. (chanchal c. c. c) |  |  | BILL/03549/2023-2024 | BP-2023-24-562 | 16/02/2024 | 16/02/2024 | W.B.S.E.D.C.LTD | 14.26 | 0 | 0 | 0
9 | MALDAH | Chanchal-I | Malda Division | Daudpur Piped water supply scheme in Chanchal-I Block, Dist-Malda | SM/12338 | New | Formal work order for the work of Implementation of DAUDPUR ZONE-I Piped Water Supply Scheme at Chanchal-I Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer,Yusuf Sk, Junior Engineer | ORD/000388/2023-2024 | 3288/MD | 23/08/2023 | 30/08/2025 | A. K. CONSTRUCTION | 151.6 | 0 | 0 | 60
10 | MALDAH | Chanchal-I | Malda Division | Daudpur Piped water supply scheme in Chanchal-I Block, Dist-Malda | SM/12338 | New | Laying of Distribution Line, Providing FHTC, Construction of Pump House at Daudpur Piped Water Supply Scheme at Chanchal-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer,Yusuf Sk, Junior Engineer | ORD/000143/2024-2025 | 2902/MD | 07/06/2024 | 01/08/2025 | M/S MOON LIGHT CONSTRUCTION & CO. | 93.32 | 0 | 0 | 51
11 | MALDAH | Chanchal-I | Malda Division | Daudpur Piped water supply scheme in Chanchal-I Block, Dist-Malda | SM/12338 | New | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Daudpur Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000762/2024-2025 | 71 | 13/01/2025 | 27/02/2025 | THREE BROTHERS CONSTRUCTION & CO | 31.61 | 0 | 0 | 0
12 | MALDAH | Chanchal-I | Malda Division | Daudpur Piped water supply scheme in Chanchal-I Block, Dist-Malda | SM/12338 | New | Construction of Boundary Wall at Head Work site of Daudpur Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Yusuf Sk, Junior Engineer | ORD/000867/2024-2025 | 1223/MD | 26/03/2025 | 25/04/2025 | M/S MADHU CONSTRUCTION | 19.79 | 0 | 0 | 0
Total | [13 empty] | 415.11 | 0 | 0