## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Mechanical | Augmentation of Maheshpur piped water supply scheme | SM/12362 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T/W No. IV of Maheshpur, Mokdumpur C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte | Assistant Engineer - II |  | ORD/000863/2023-2024 | 3004405173 | 28/08/2023 | 26/11/2023 | W.B.S.E.D.C.LTD | 7.66 | 7.66 | 100 | 100
2 | MALDAH |  | Malda Division | Augmentation of Maheshpur piped water supply scheme | SM/12362 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000028/2023-2024 | 1810/MD | 27/04/2023 | 27/04/2023 | Resource Division | 28.61 | 0 | 0 | 0
3 | MALDAH |  | Malda Division | Augmentation of Maheshpur piped water supply scheme | SM/12362 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000049/2023-2024 | 1811/MD | 27/04/2023 | 27/04/2023 | Resource Division | 28.61 | 0 | 0 | 0
4 | MALDAH |  | Malda Division | Augmentation of Maheshpur piped water supply scheme | SM/12362 | Augmentation | Formal work order for the work of Augmentation of MAHESHPUR Piped water supply scheme for the work of Geotechnical Study,construction of 600 Cum RCC OHR, Laying Distribution of pipe line and providing Functional Household Tap connection (FHTC) within English Bazar Block under Malda Division PH Engg.Dte. In the District of Malda . | Mr. Amit Biswas, Assistant Engineer,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Shreya Das, Junior Engineer | ORD/000421/2022-2023 | 3179/MD | 23/12/2022 | 02/04/2025 | M/S NIRAPADA BHATTACHARJEE | 631.46 | 568.82 | 90.08 | 95
5 | MALDAH |  | Malda Mechanical | Augmentation of Maheshpur piped water supply scheme | SM/12362 | Augmentation | Supply, installation and commissioning of electro-mechanical components at T/W no. II of Augmentation of Maheshpur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. | Assistant Engineer - II | Junior Engineer-03 | ORD/002486/2023-2024 | 808/MLMD | 15/02/2024 | 28/12/2025 | BEE GEE CONSTRUCTION. | 12.42 | 9.73 | 78.33 | 35
6 | MALDAH |  | Malda Division | Augmentation of Maheshpur piped water supply scheme | SM/12362 | Augmentation | Construction of 5.40 mtr.X 3.6mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at Head Work site at Maheshpur PWSS of Englishbazar Block under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Amit Biswas, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000463/2023-2024 | 3396/MD | 31/08/2023 | 15/10/2023 | SADHANA CONSTRUCTION | 6.52 | 6.28 | 96.2 | 100
7 | MALDAH |  | Malda Division | Augmentation of Maheshpur piped water supply scheme | SM/12362 | Augmentation | Construction of Boundary Wall at Head Work Site of MAHESHPUR Piped Water Supply Scheme at Englishbazar Block under Malda Division, P.H.E.Dte. in the District of Malda. | Mr. Amit Biswas, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000916/2023-2024 | 378/MD | 17/01/2024 | 31/10/2024 | M/S SRINJOYEE | 15.94 | 12.54 | 78.69 | 100
8 | MALDAH |  | Malda Division | Augmentation of Maheshpur piped water supply scheme | SM/12362 | Augmentation | Additional Laying of Distribution pipe line of MAHESHPUR Water Supply Scheme under Malda Division PHE. Dte in The District of Malda. | Mr. Amit Biswas, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000915/2023-2024 | 388/MD | 17/01/2024 | 25/11/2024 | DEBAPRIYA SAHA | 37.78 | 9.95 | 26.34 | 100
9 | MALDAH |  | Malda Division | Augmentation of Maheshpur piped water supply scheme | SM/12362 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000188/2023-2024 | 823/MD | 21/02/2024 | 21/02/2024 | Resource Division | 17.76 | 0 | 0 | 0
10 | MALDAH |  | Malda Division | Augmentation of Maheshpur piped water supply scheme | SM/12362 | Augmentation | Laying of Rising Main including Specials and Valves for MAHESHPUR Piped Water Supply Scheme at Englishbazar Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Amit Biswas, Assistant Engineer,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Shreya Das, Junior Engineer | ORD/000914/2023-2024 | 387/MD | 17/01/2024 | 11/04/2025 | S. N. CONSTRUCTION | 19.15 | 0 | 0 | 35
11 | MALDAH |  | Malda Division | Augmentation of Maheshpur piped water supply scheme | SM/12362 | Augmentation | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 135m³/hr. capacity Pressure type IRON ELIMINATION Plant with Construction of Blower room & backwash water disposal at head work site of Maheshpur Water Supply Scheme of Englishbazar Block under Malda Division P.H.E Dte in the District of Malda. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000157/2024-2025 | 2926/MD | 10/06/2024 | 01/04/2025 | MERCURY ENGINEERING COMPANY | 47.11 | 0 | 0 | 18
12 | MALDAH |  | Malda Division | Augmentation of Maheshpur piped water supply scheme | SM/12362 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Maheshpur Water Supply Scheme under Englishbazar Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000741/2024-2025 | 25/MD | 06/01/2025 | 17/11/2025 | M/S STAR INDIA CONSTRUTION | 60.76 | 0 | 0 | 85
13 | MALDAH |  | Malda Division | Augmentation of Maheshpur piped water supply scheme | SM/12362 | Augmentation | Augmentation work of Construction of Boundary Wall at Head Work site of MAHISHBATHANI Water Supply Scheme under Old Malda Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer, | ORD/000008/2025-2026 | 2411/MD | 27/05/2025 | 10/08/2025 | M/S EHAN ENTERPRISE | 10.94 | 0 | 0 | 0
14 | MALDAH |  | Malda Division | Augmentation of Maheshpur piped water supply scheme | SM/12362 | Augmentation | Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, RWS Malda Sub-Division Division, PHE Dte. (Car-2) (Period from 01/07/2025 to 31/12/2025). | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000285/2025-2026 | 3117/MD | 30/06/2025 | 28/12/2025 | RUQAIYA ENTERPRISE | 0.86 | 0 | 0 | 0
15 | MALDAH |  | Malda Division | Augmentation of Maheshpur piped water supply scheme | SM/12362 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and laying of 90 mm OD diameter UPVC Pipeline under command area of Augmentation of Maheshpur Piped Water Supply Scheme at Englishbazar Dev. Block in the District Malda under Malda Division, PHE Dte. | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000196/2025-2026 | 3630/MD | 24/07/2025 | 22/09/2025 | M/S STAR INDIA CONSTRUTION | 70.86 | 0 | 0 | 0
16 | MALDAH |  | Malda Division | Augmentation of Maheshpur piped water supply scheme | SM/12362 | Augmentation | Acceptance cum formal work order for Sinking of 300 mm. Dia. x 200 mm. dia. and 95 Mtr. Deep Big dia Tube well (2 No) at MAHESHPUR Water Supply Scheme under English Bazar Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Amit Biswas, Assistant Engineer,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000603/2022-2023 | 921/MD | 27/02/2023 | 04/09/2024 | ASHIS CONSTRUCTION | 21.48 | 8.9 | 41.44 | 100
Total | [13 empty] | 1017.93 | 623.89 | 61.29